## pmr
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | DSWD FO IX Procurement Monitoring Report as of January 14, 2021
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
[38 empty] | 0 |  |  | 0
| Construction of Playground and Repair of Multi Purpose Building (RSCC) | [19 empty] | RSCC/ CRCF | NO | Competitive Bidding | 2020-06-25 | 2020-05-22 | 2020-05-29 | 2020-06-10 | 2020-06-10 | 15-16 Jun-2020 | 2020-06-24 | 2020-06-25 | 2020-07-30 | 2020-09-14 | 2020-09-14 | Dec. 7, 2020 |  | GoP | 745698.13 |  | 745698.13 | 730840.32 |  | 730840.32 | COA, PICE and Los Contratistas de la Ciudad de Zamboanga | 2020-05-22 | 2020-05-22 | 2020-05-22 | 2020-05-22 | 2020-06-18
| Embankment (PCDP) | [19 empty] | PCDP | NO | Competitive Bidding | 2020-06-25 | 2020-07-01 | 2020-07-07 | 2020-07-24 | 2020-07-24 | 2020-07-28 | 2020-08-06 | 2020-08-12 | 2020-09-11 | 2020-10-05 | 2020-10-06 | Oct. 27, 2020 |  | GoP | 616674.08 |  | 616674.08 | 603990.38 |  | 603990.38 | COA, PICE and Los Contratistas de la Ciudad de Zamboanga | 2020-06-29 | 2020-06-29 | 2020-06-29 | 2020-06-29 | 2021-07-30
| 2nd Public Bidding: Construction of Kitchen and Laundry Pathwalk and 2nd Public Bidding: Construction of Covered Path Walk | [19 empty] | AVRC/ CRCF | NO | Competitive Bidding | 2020-01-25 | 2020-05-22 | 2020-07-07 | 2020-07-20 | 2020-07-20 | 2020-07-20 | 2020-08-06 | 2020-08-12 | 2020-09-11 | 2020-10-01 | 2020-10-01 | Dec. 28, 2020 |  | GoP | 1538063.27 |  | 1538063.27 | 1361169.63 |  | 1361169.63 | COA, PICE and Los Contratistas de la Ciudad de Zamboanga | 2020-06-29 | 2020-06-29 | 2020-06-29 | 2020-06-29 | 2020-07-30
[38 empty] | 0 |  |  | 0
[38 empty] | 0 |  |  | 0
Total Alloted Budget of Procurement Activities | [37 empty] | 2900435.48
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 2696000.33
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 204435.15
0N-GOING PROCUREMENT ACTIVITIES
| Upgrading of Admin Building (HE) | [19 empty] | HOME FOR ELDERLY/ CRCF | NO | Competitive Bidding | 2019-12-18 | 2020-05-23 | 2020-05-29 | 2020-06-10 | 2020-06-10 | 15-16 Jun-2020 | 2020-06-26 | 2020-07-01 | 2020-07-30 | 2020-09-07 | 2020-09-09 |  |  | GoP | 4449485.92 |  | 4449485.92 | 4441004.24 |  | 4441004.24 | COA, PICE and Los Contratistas de la Ciudad de Zamboanga | 2020-05-22 | 2020-05-22 | 2020-05-22 | 2020-05-22 | 2020-06-18
| Upgrading of Residents' Quarter Phase II (HE) | [19 empty] | HOME FOR ELDERLY/ CRCF | NO | Competitive Bidding | 2019-12-18 | 2020-05-22 | 2020-05-29 | 2020-06-10 | 2020-06-10 | 15-16 Jun-2020 | 2020-06-24 | 2020-06-25 | 2020-07-29 | 2020-09-10 | 2020-09-14 |  |  | GoP | 2601662.15 |  | 2601662.15 | 2600518.71 |  | 2600518.71 | COA, PICE and Los Contratistas de la Ciudad de Zamboanga | 2020-05-22 | 2020-05-22 | 2020-05-22 | 2020-05-22 | 2020-06-18
| Upgrading of Electrical System in DSWD Compound | [19 empty] | AVRC/ CRCF | NO | Competitive Bidding | 2019-12-18 | 2020-05-22 | 2020-05-29 | 2020-06-10 | 2020-06-10 | 15-16 Jun-2020 | 2020-06-26 | 2020-07-01 | 2020-07-30 | 2020-09-07 | 2020-09-09 |  |  | GoP | 25772663.7 |  | 25772663.7 | 24411873.76 |  | 24411873.76 | COA, PICE and Los Contratistas de la Ciudad de Zamboanga | 2020-05-22 | 2020-05-22 | 2020-05-22 | 2020-05-22 | 2020-06-18
| Construction of Multi Purpose Building (RRCY) | [19 empty] | RRCY/ CRCF | NO | Competitive Bidding | 2019-12-18 | 2020-05-22 | 2020-05-29 | 2020-06-10 | 2020-06-10 | 15-16 Jun-2020 | 2020-06-25 | 2020-07-01 | 2020-07-30 | 2020-09-11 | 2020-09-11 |  |  | GoP | 7755383.34 |  | 7755383.34 | 7740750.55 |  | 7740750.55 | COA, PICE and Los Contratistas de la Ciudad de Zamboanga | 2020-05-22 | 2020-05-22 | 2020-05-22 | 2020-05-22 | 2020-06-18
| Construction of Perimeter Fence (RRCY) | [19 empty] | RRCY/CRCF | NO | Competitive Bidding | 2019-12-18 | 2020-05-22 | 2020-05-29 | 2020-06-10 | 2020-06-10 | 15-16 Jun-2020 | 2020-06-26 | 2020-07-01 | 2020-09-18 | 2020-10-07 | 2020-10-07 |  |  | GoP | 6128010.06 |  | 6128010.06 | 5015976 |  | 5015976 | COA, PICE and Los Contratistas de la Ciudad de Zamboanga | 2020-05-22 | 2020-05-22 | 2020-05-22 | 2020-05-22 | 2020-06-18
| Upgrading and Construction of Perimeter Fence, Three Main Gate Entrance (BDSK) | [19 empty] | BDSK/CRCF | NO | Competitive Bidding | 2019-12-18 | 2020-05-22 | 2020-05-29 | 2020-06-10 | 2020-06-10 | 15-16 Jun-2020 | 2020-06-26 | 2020-07-01 | 2020-09-18 | 2020-09-30 | 2020-10-01 |  |  | GoP | 3759704.82 |  | 3759704.82 | 3196673.02 |  | 3196673.02 | COA, PICE and Los Contratistas de la Ciudad de Zamboanga | 2020-05-22 | 2020-05-22 | 2020-05-22 | 2020-05-22 | 2020-06-18
| 2nd Public Bidding: Construction of Water Tower for PCDP, HFW, HE AND RSCC | [19 empty] | CRCF/PCDP/HFW/HE/RSCC | NO | Competitive Bidding | 2020-01-25 | 2020-05-22 | 2020-07-07 | 2020-07-20 | 2020-07-20 | 2020-07-20 | 2020-08-06 | 2020-08-12 | 2020-09-18 | 2020-10-07 | 2020-10-07 |  |  | GoP | 3005951.81 |  | 3005951.81 |  |  | 2846419.38 | COA, PICE and Los Contratistas de la Ciudad de Zamboanga | 2020-06-29 | 2020-06-29 | 2020-06-29 | 2020-06-29 | 2020-07-30
| Upgrading Of Electrical System in Home for the Elderly. | [19 empty] | HFE/CRCF | NO | Competitive Bidding | 2020-07-08 | 2020-07-09 | 2020-07-23 | 2020-08-04 | 2020-08-04 | 2020-08-05 | 2020-09-01 | 2020-09-02 | 2020-09-18 | 2020-10-09 | 2020-10-09 |  |  | GoP | 2064946.44 |  | 2064946.44 | 1781498.35 |  | 1781498.35 | COA, PICE and Los Contratistas de la Ciudad de Zamboanga | 2020-07-08 | 2020-07-08 | 2020-07-08 | 2020-07-08 | 2020-08-24
| Provision of Service Provider for the Digitization of Permanent and Valuable Records of DSWD FO IX | [19 empty] | Records | NO | Competitive Bidding | 2020-07-08 | 2020-07-09 | 2020-07-23 | 2020-08-04 | 2020-08-05 | 2020-09-09 | 2020-09-04 | 2020-09-22 | 2020-10-05 | 2020-10-30 | 2020-10-30 |  |  | GoP | 1500000 | 1500000 |  | 1372500 | 1372500 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-07-09 | 2020-07-09 | 2020-07-09 | 2020-07-09 | 2020-08-28
| Procurement of Grocery Items for BANGUN Implementation in Basilan Province | [19 empty] | BangUN | NO | Competitive Bidding | 2020-07-21 | 2020-08-04 | 2020-08-07 | 2020-09-02 | 2020-09-02 | 2020-09-09 | 2020-12-14 | 2020-12-14 | 2020-12-16 | 2020-12-23 | 2020-12-23 |  |  | GoP | 3408935 | 3408935 |  | 3299996 | 3299996 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-07-30 | 2020-07-30 | 2020-07-30 | 2020-07-30
| Procurement of Semi-Perishable Items for BANGUN Implementation in Basilan Province | [19 empty] | BangUN | NO | Competitive Bidding | 2020-07-21 | 2020-08-04 | 2020-08-07 | 2020-09-02 | 2020-09-02 | 2020-09-09 | 2020-12-14 | 2020-12-14 | 2020-12-16 | 2020-12-23 | 2020-12-23 |  |  | GoP | 6409325 | 6409325 |  | 6368700 | 6368700 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-07-30 | 2020-07-30 | 2020-07-30 | 2020-07-30
| Procurement of Grocery Items for BANGUN Implementation in Tawi-Tawi Province | [19 empty] | BangUN | NO | Competitive Bidding | 2020-07-21 | 2020-08-04 | 2020-08-07 | 2020-09-02 | 2020-09-02 | 2020-09-09 | 2020-12-14 | 2020-12-14 | 2020-12-16 | 2020-12-23 | 2020-12-23 |  |  | GoP | 3349185 | 3349185 |  | 3301496 | 3301496 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-07-30 | 2020-07-30 | 2020-07-30 | 2020-07-30
| Procurement of Semi-Perishable Items for BANGUN Implementation in Tawi-Tawi Province | [19 empty] | BangUN | NO | Competitive Bidding | 2020-07-21 | 2020-08-04 | 2020-08-07 | 2020-09-02 | 2020-09-02 | 2020-09-09 | 2020-12-14 | 2020-12-14 | 2020-12-16 | 2020-12-23 | 2020-12-23 |  |  | GoP | 6580675 | 6580675 |  | 6368700 | 6368700 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-07-30 | 2020-07-30 | 2020-07-30 | 2020-07-30
| Procurement of Grocery Items for BANGUN Implementation in Sulu Province | [19 empty] | BangUN | NO | Competitive Bidding | 2020-07-21 | 2020-08-04 | 2020-08-07 | 2020-09-02 | 2020-09-02 | 2020-09-09 | 2020-12-14 | 2020-12-14 | 2020-12-16 | 2020-12-23 | 2020-12-23 |  |  | GoP | 4410284 | 4410284 |  | 4394210 | 4394210 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-07-30 | 2020-07-30 | 2020-07-30 | 2020-07-30
| Procurement of Perishable Items for BANGUN Implementation in Sulu Province | [19 empty] | BangUN | NO | Competitive Bidding | 2020-07-21 | 2020-08-04 | 2020-08-07 | 2020-09-02 | 2020-09-02 | 2020-09-09 | 2020-12-14 | 2020-12-14 | 2020-12-16 | 2020-12-23 | 2020-12-23 |  |  | GoP | 5099585 | 5099585 |  | 4948590 | 4948590 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-07-30 | 2020-07-30 | 2020-07-30 | 2020-07-30
| Procurement of Commercial Rice for SFP 10th Cycle Implementation in Zamboanga Del Sur (ZDS) District 1 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-15 | 2020-10-15 | 2020-10-20 | 2020-11-06 | 2020-11-12 | 2020-12-04 | 2020-12-18 | 2020-12-22 |  |  | GoP | 4152500 | 4152500 |  | 4119280 | 4119280 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-01
| Procurement of Whole Dressed Chicken for SFP 10th Cycle Implementation in Zamboanga Del Sur (ZDS) District 1 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-15 | 2020-10-15 | 2020-10-20 | 2020-11-06 | 2020-11-12 | 2020-12-04 | 2020-12-18 | 2020-12-22 |  |  | GoP | 6239000 | 6239000 |  | 6207805 | 6207805 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-01
| Procurement of Eggs for SFP 10th Cycle Implementation in Zamboanga Del Sur (ZDS) District 1 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-15 | 2020-10-15 | 2020-10-20 | 2020-11-06 | 2020-11-12 | 2020-12-04 | 2020-12-18 | 2020-12-22 |  |  | GoP | 3996776 | 3996776 |  | 3968227.6 | 3968227.6 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-01
| Procurement of Grocery Items for SFP 10th Cycle Implementation in Zamboanga Del Sur (ZDS) District 1 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-15 | 2020-10-15 | 2020-10-20 | 2020-11-06 | 2020-11-12 | 2020-12-04 | 2020-12-18 | 2020-12-22 |  |  | GoP | 13002373 | 13002373 |  | 12986801 | 12986801 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-01
| Procurement of Commercial Rice for SFP 10th Cycle Implementation in Zamboanga Del Sur (ZDS) District 2 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-15 | 2020-10-15 | 2020-10-20 | 2020-11-06 | 2020-11-12 | 2020-12-04 | 2020-12-18 | 2020-12-22 |  |  | GoP | 3060000 | 3060000 |  | 3035520 | 3035520 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-01
| Procurement of Whole Dressed Chicken for SFP 10th Cycle Implementation in Zamboanga Del Sur (ZDS) District 2 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-15 | 2020-10-15 | 2020-10-20 | 2020-11-06 | 2020-11-12 | 2020-12-04 | 2020-12-18 | 2020-12-22 |  |  | GoP | 4598400 | 4598400 |  | 4575408 | 4575408 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-01
| Procurement of Eggs for SFP 10th Cycle Implementation in Zamboanga Del Sur (ZDS) District 2 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-15 | 2020-10-15 | 2020-10-20 | 2020-11-06 | 2020-11-12 | 2020-12-04 | 2020-12-18 | 2020-12-22 |  |  | GoP | 2945712 | 2945712 |  | 2924671.2 | 2924671.2 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-01
| Procurement of Grocery Items for SFP 10th Cycle Implementation in Zamboanga Del Sur (ZDS) District 2 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-15 | 2020-10-15 | 2020-10-20 | 2020-11-06 | 2020-11-12 | 2020-12-04 | 2020-12-21 | 2020-12-22 |  |  | GoP | 9583438 | 9583438 |  | 9564306 | 9564306 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-01
| Procurement of Commercial Rice for SFP 10th Cycle Implementation in Zamboanga Sibugay Province (ZSP) District 1 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-16 | 2020-10-16 | 2020-10-20 | 2020-11-11 | 2020-11-12 | 2020-12-04 | 2020-12-21 | 2020-12-22 |  |  | GoP | 2502500 | 2502500 |  | 2492490 | 2492490 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-02
| Procurement of Whole Dressed Chicken for SFP 10th Cycle Implementation in Zamboanga Sibugay Province (ZSP) District 1 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-16 | 2020-10-16 | 2020-10-20 | 2020-11-11 | 2020-11-12 | 2020-12-04 | 2020-12-21 | 2020-12-22 |  |  | GoP | 3761200 | 3761200 |  | 3723588 | 3723588 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-02
| Procurement of Eggs for SFP 10th Cycle Implementation in Zamboanga Sibugay Province (ZSP) District 1 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-16 | 2020-10-16 | 2020-10-20 | 2020-11-11 | 2020-11-12 | 2020-12-04 | 2020-12-21 | 2020-12-22 |  |  | GoP | 2409099 | 2409099 |  | 2409099 | 2409099 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-02
| Procurement of Perishable Goods for SFP 10th Cycle Implementation in Zamboanga Sibugay Province (ZSP) District 1 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-16 | 2020-10-16 | 2020-10-20 | ONLINE | 2020-11-12 | 2020-12-04 | 2020-12-21 | 2020-12-22 |  |  | GoP | 2262130 | 2262130 |  | 2213670 | 2213670 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-02
| Procurement of Grocery Items for SFP 10th Cycle Implementation in Zamboanga Sibugay Province (ZSP) District 1 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-16 | 2020-10-16 | 2020-10-20 | 2020-11-11 | 2020-11-12 | 2020-12-04 | 2020-12-21 | 2020-12-22 |  |  | GoP | 7837271 | 7837271 |  | 7827923 | 7827923 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-02
| Procurement of Commercial Rice for SFP 10th Cycle Implementation in Zamboanga Sibugay Province (ZSP) District 2 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-16 | 2020-10-16 | 2020-10-20 | 2020-11-11 | 2020-11-12 | 2020-12-04 | 2020-12-18 | 2020-12-22 |  |  | GoP | 3710000 | 3710000 |  | 3695160 | 3695160 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-02
| Procurement of Whole Dressed Chicken for SFP 10th Cycle Implementation in Zamboanga Sibugay Province (ZSP) District 2 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-16 | 2020-10-16 | 2020-10-20 | 2020-11-11 | 2020-11-12 | 2020-12-04 | 2020-12-18 | 2020-12-22 |  |  | GoP | 5574400 | 5574400 |  | 5546528 | 5546528 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-02
| Procurement of Eggs for SFP 10th Cycle Implementation in Zamboanga Sibugay Province (ZSP) District 2 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-16 | 2020-10-16 | 2020-10-20 | 2020-11-11 | 2020-11-12 | 2020-12-04 | 2020-12-18 | 2020-12-22 |  |  | GoP | 3570798 | 3570798 |  | 3545292.3 | 3545292.3 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-02
| Procurement of Perishable Goods for SFP 10th Cycle Implementation in Zamboanga Sibugay Province (ZSP) District 2 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-16 | 2020-10-16 | 2020-10-20 | ONLINE | 2020-11-12 | 2020-12-04 | 2020-12-21 | 2020-12-22 |  |  | GoP | 3352760 | 3352760 |  | 3280890 | 3280890 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-02
| Procurement of Grocery Items for SFP 10th Cycle Implementation in Zamboanga Sibugay Province (ZSP) District 2 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-16 | 2020-10-16 | 2020-10-20 | 2020-11-11 | 2020-11-12 | 2020-12-04 | 2020-12-18 | 2020-12-22 |  |  | GoP | 11616442 | 11616442 |  | 11607186 | 11607186 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-02
| Procurement of Commercial Rice for SFP 10th Cycle Implementation in Zamboanga Del Norte (ZDN) District 1 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-17 | 2020-10-17 | 2020-10-20 | 2020-11-11 | 2020-11-12 | 2020-12-04 | 2020-12-21 | 2020-12-22 |  |  | GoP | 1746250 | 1746250 |  | 1739265 | 1739265 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
| Procurement of Eggs for SFP 10th Cycle Implementation in Zamboanga Del Norte (ZDN) District 1 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-17 | 2020-10-17 | 2020-10-20 | 2020-11-09 | 2020-11-12 | 2020-12-04 | 2020-12-15 | 2020-12-22 |  |  | GoP | 1681400 | 1681400 |  | 1633360 | 1633360 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
| Procurement of Perishable Goods for SFP 10th Cycle Implementation in Zamboanga Del Norte (ZDN) District 1 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-17 | 2020-10-17 | 2020-10-20 | 2020-11-09 | 2020-11-12 | 2020-12-04 | 2020-12-15 | 2020-12-22 |  |  | GoP | 1579019 | 1579019 |  | 1535507 | 1535507 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
| Procurement of Grocery Items for SFP 10th Cycle Implementation in Zamboanga Del Norte (ZDN) District 1 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-17 | 2020-10-17 | 2020-10-20 | ONLINE | 2020-11-12 | 2020-12-04 | 2020-12-21 | 2020-12-22 |  |  | GoP | 5470331 | 5470331 |  | 5437554.1 | 5437554.1 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
| Procurement of Whole Dressed Chicken for SFP 10th Cycle Implementation in Zamboanga Del Norte (ZDN) District 2 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-17 | 2020-10-17 | 2020-10-20 | ONLINE | 2020-11-12 | 2020-12-04 | 2020-12-23 | 2020-12-23 |  |  | GoP | 3966400 | 3966400 |  | 3867240 | 3867240 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
| Procurement of Eggs for SFP 10th Cycle Implementation in Zamboanga Del Norte (ZDN) District 2 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-17 | 2020-10-17 | 2020-10-20 | 2020-11-11 | 2020-11-12 | 2020-12-04 | 2020-12-21 | 2020-12-22 |  |  | GoP | 2540524 | 2540524 |  | 1814660 | 1814660 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
| Procurement of Perishable Goods for SFP 10th Cycle Implementation in Zamboanga Del Norte (ZDN) District 2 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-17 | 2020-10-17 | 2020-10-20 | 2020-11-09 | 2020-11-12 | 2020-12-04 | 2020-12-15 | 2020-12-22 |  |  | GoP | 2385684 | 2385684 |  | 2319733 | 2319733 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
| Procurement of Grocery Items for SFP 10th Cycle Implementation in Zamboanga Del Norte (ZDN) District 2 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-17 | 2020-10-17 | 2020-10-20 | ONLINE | 2020-11-12 | 2020-12-04 | 2020-12-21 | 2020-12-22 |  |  | GoP | 8265042 | 8265042 |  | 8215536.2 | 8215536.2 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
| Procurement of Whole Dressed Chicken for SFP 10th Cycle Implementation in Zamboanga Del Norte (ZDN) District 3 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-17 | 2020-10-17 | 2020-10-20 | ONLINE | 2020-11-12 | 2020-12-04 | 2020-12-23 | 2020-12-23 |  |  | GoP | 4863600 | 4863600 |  | 4742010 | 4742010 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
| Procurement of Eggs for SFP 10th Cycle Implementation in Zamboanga Del Norte (ZDN) District 3 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-17 | 2020-10-17 | 2020-10-20 | ONLINE | 2020-11-12 | 2020-12-04 | 2020-12-23 | 2020-12-23 |  |  | GoP | 3115504 | 3115504 |  | 3115504 | 3115504 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
| Procurement of Perishable Goods for SFP 10th Cycle Implementation in Zamboanga Del Norte (ZDN) District 3 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-17 | 2020-10-17 | 2020-10-20 | ONLINE | 2020-11-12 | 2020-12-04 | 2020-12-23 | 2020-12-23 |  |  | GoP | 2925573 | 2925573 |  | 2862910 | 2862910 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
| Procurement of Grocery Items for SFP 10th Cycle Implementation in Zamboanga Del Norte (ZDN) District 3 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-17 | 2020-10-17 | 2020-10-20 | ONLINE | 2020-11-12 | 2020-12-04 | 2020-12-23 | 2020-12-23 |  |  | GoP | 10135673 | 10135673 |  | 10074974.3 | 10074974.3 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
| Procurement of Commercial Rice for SFP 10th Cycle Implementation in Zamboanga City and Sibuco | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-19 | 2020-10-19 | 2020-10-20 | 2020-11-11 | 2020-12-04 | 2020-12-07 | 2020-12-14 | 2020-12-16 |  |  | GoP | 3882500 | 3882500 |  | 3416600 | 3416600 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
| Procurement of Whole Dressed Chicken for SFP 10th Cycle Implementation in Zamboanga City and Sibuco | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-19 | 2020-10-19 | 2020-10-20 | 2020-11-11 | 2020-12-04 | 2020-12-04 | 2020-12-21 | 2020-12-22 |  |  | GoP | 5833800 | 5833800 |  | 5687955 | 5687955 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
| Procurement of Eggs for SFP 10th Cycle Implementation in Zamboanga City and Sibuco | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-19 | 2020-10-19 | 2020-10-20 | 2020-11-11 | 2020-12-04 | 2020-12-04 | 2020-12-21 | 2020-12-22 |  |  | GoP | 3737097 | 3737097 |  | 3737097 | 3737097 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
| Procurement of Grocery Items for SFP 10th Cycle Implementation in Zamboanga City and Sibuco | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-19 | 2020-10-19 | 2020-10-20 | ONLINE | 2020-12-04 | 2020-12-04 | 2020-12-23 | 2020-12-23 |  |  | GoP | 12157882 | 12157882 |  | 12089913.2 | 12089913.2 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
| Procurement of Commercial Rice for SFP 10th Cycle Implementation in Isabela City | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-19 | 2020-10-19 | 2020-10-20 | 2020-11-11 | 2020-12-04 | 2020-12-07 | 2020-12-14 | 2020-12-16 |  |  | GoP | 1131570 | 1131570 |  | 1005048 | 1005048 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
| Procurement of Whole Dressed Chicken for SFP 10th Cycle Implementation in Isabela City | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-19 | 2020-10-19 | 2020-10-20 | ONLINE | 2020-12-04 | 2020-12-04 | 2020-12-23 | 2020-12-23 |  |  | GoP | 1600000 | 1600000 |  | 1560000 | 1560000 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
| Procurement of Perishable Goods for SFP 10th Cycle Implementation in Isabela City | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-19 | 2020-10-19 | 2020-10-20 | ONLINE | 2020-12-04 | 2020-12-04 | 2020-12-23 | 2020-12-23 |  |  | GoP | 1467210 | 1467210 |  | 1466571 | 1466571 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
| Procurement of Electrical Works of DSWD Fo IX | [19 empty] | GENSERVE | YES | Competitive Bidding | 2020-10-15 | 2020-11-13 | 2020-11-21 | 2020-12-03 | 2020-12-03 | 2020-12-03 | 2020-12-11 | 2020-12-12 | 2020-12-14 | 2020-12-23 | 2020-12-28 |  |  | GoP | 1569763.5 |  | 1569763.5 | 1540843.84 |  | 1540843.84 | COA, TZU Chi Foundation and ZC Chamber of Commerce & PICE ZC Chapter | 2020-11-13 | 2020-11-13 | 2020-11-13 | 2020-11-13 | 2020-12-03
| Provision of Security and Janitorial Services for CY 2021 | [19 empty] | GENSERVE | YES | Competitive Bidding | 2020-10-15 | 2020-11-14 | 2020-11-21 | 2020-12-03 | 2020-12-03 | 2020-12-03 | 2020-12-11 | 2020-12-11 | 2020-12-30 | 2021-01-01 | 2020-12-31 |  |  | GoP | 23235084 | 23235084 |  | 23232672.24 | 23232672.24 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-11-13 | 2020-11-13 | 2020-11-13 | 2020-11-13 | 2020-12-03
| Procurement of Perishable Goodsfor the SFP 10th Cycle Implementation in District 1 Zamboanga del Sur (ZDS) District 1 (Negotiated Procurement 2 failed Bidding) | [19 empty] | SFP | NO | NP-53.1 Two Failed Biddings | 2020-12-03 | 2020-12-15 | 2020-12-21 | 2020-12-26 | 2020-12-26 | 2020-12-26 | n/a | 2020-12-26 | DEC. 26, 2020 | DEC. 28, 2020 | DEC. 28, 2020 |  |  | GoP | 3752951 | 3752951 |  | 3174198.6 | 3174198.6 |  | n/a | n/a | n/a | n/a | n/a | n/a
| Procurement of Perishable Goods for SFP 10th Cycle Implementation in District 2 Zamboanga Del Sur (ZDS) District 2 (Negotiated Procurement 2 failed Bidding) | [19 empty] | SFP | NO | NP-53.1 Two Failed Biddings | 2020-12-03 | 2020-12-15 | 2020-12-21 | 2020-12-26 | 2020-12-26 | 2020-12-26 | n/a | 2020-12-26 | DEC. 26, 2020 | DEC. 28, 2020 | DEC. 28, 2020 |  |  | GoP | 2766050 | 2766050 |  | 2284940 | 2284940 |  | n/a | n/a | n/a | n/a | n/a | n/a
| 2nd Public Bidding: Procurement of Commercial Rice for SFP 10th Cycle Implementation in District 2 Zamboanga Del Norte (ZDN) | [19 empty] | SFP | NO | Competitive Bidding | 2020-11-12 | 2020-11-12 | 2020-11-21 | 2020-12-03 | 2020-12-03 | 2020-12-03 | 2020-12-11 | 2020-12-11 | DEC. 26, 2020 | DEC. 28, 2020 | DEC. 28, 2020 |  |  | GoP | 2638750 | 2638750 |  | 2461426 | 2461426 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-11-13 | 2020-11-13 | 2020-11-13 | 2020-11-13 | 2020-12-03
| Procurement of Commercial Rice for SFP 10th Cycle Implementation in District 3 Zamboanga Del Norte (ZDN) (Negotiated Procurement 2 failed Bidding) | [19 empty] | SFP | NO | NP-53.1 Two Failed Biddings | 2020-12-03 | 2020-12-15 | 2020-12-21 | 2020-12-26 | 2020-12-26 | 2020-12-26 | n/a | 2020-12-26 | DEC. 26, 2020 | DEC. 28, 2020 | DEC. 28, 2020 |  |  | GoP | 3236250 | 3236250 |  | 3223305 | 3223305 |  | n/a | n/a | n/a | n/a | n/a | n/a
| Procurement of Perishable Goods for SFP 10th Cycle Implementation in Zamboanga City & Sibuco (Negotiated Procurement 2 failed Bidding) | [19 empty] | SFP | NO | NP-53.1 Two Failed Biddings | 2020-12-03 | 2020-12-15 | 2020-12-21 | 2020-12-26 | 2020-12-26 | 2020-12-26 | n/a | 2020-12-26 | DEC. 26, 2020 | DEC. 28, 2020 | DEC. 28, 2020 |  |  | GoP | 3509121 | 3509121 |  | 3506699 | 3506699 |  | n/a | n/a | n/a | n/a | n/a | n/a
| 2ND PUBLIC BIDDING: PROCUREMENT OF PERISHABLE ITEMS FOR BANGUN IMPLEMENTATION IN BASILAN PROVINCE | [19 empty] | BangUN | NO | Competitive Bidding | 2020-11-27 | 2020-11-29 | 2020-12-07 | 2020-12-19 | 2020-12-19 | 2020-12-19 | ONLINE | 2020-12-26 | Dec. 28, 2020 | Dec. 28, 2020 | Dec. 28, 2020 |  |  | GoP | 5679740 | 5679740 |  | 4589590 | 4589590 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-12-01 | 2020-12-01 | 2020-12-01 | 2020-12-01
| PROCUREMENT OF PERISHABLE ITEMS FOR BANGUN IMPLEMENTATION IN SULU PROVINCE | [19 empty] | BangUN | NO | Competitive Bidding | 2020-11-27 | 2020-11-29 | 2020-12-07 | 2020-12-19 | 2020-12-19 | 2020-12-19 | ONLINE | 2020-12-26 | Dec. 28, 2020 | Dec. 28, 2020 | Dec. 28, 2020 |  |  | GoP | 6474240 | 6474240 |  | 5335200 | 5335200 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-12-01 | 2020-12-01 | 2020-12-01 | 2020-12-01
| 2ND PUBLIC BIDDING: PROCUREMENT OF PERISHABLE ITEMS FOR BANGUN IMPLEMENTATION IN TAWITAWI PROVINCE | [19 empty] | BangUN | NO | Competitive Bidding | 2020-11-27 | 2020-11-29 | 2020-12-07 | 2020-12-19 | 2020-12-19 | 2020-12-19 | ONLINE | 2020-12-26 | Dec. 28, 2020 | Dec. 28, 2020 | Dec. 28, 2020 |  |  | GoP | 5568140 | 5568140 |  | 4589590 | 4589590 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-12-01 | 2020-12-01 | 2020-12-01 | 2020-12-01
| Procurement of Food Items Food Items for CY 2021 BangUN Implimentation in Basilan Province. | [19 empty] | BangUN | YES | Competitive Bidding | 2020-12-27 | 2020-12-27 | 2020-12-29 | 2021-01-11 | 2021-01-11 | 2021-01-12 | ONLINE | Jan. 20, 2021 | Jan. 21, 2021 | Jan. 28, 2021 | Jan. 28, 2021 |  |  | GoP | 15183800 | 15183800 |  | 14987401.2 | 14987401.2 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-12-21 | 2020-12-21 | 2020-12-21 | 2020-12-21 | 2021-01-12
| Procurement of Food Items Food Items for CY 2021 BangUN Implimentation in Tawi-Tawi Province. | [19 empty] | BangUN | YES | Competitive Bidding | 2020-12-27 | 2020-12-27 | 2020-12-29 | 2021-01-11 | 2021-01-11 | 2021-01-12 | ONLINE | Jan. 20, 2022 | Jan. 21, 2021 | Jan. 28, 2021 | Jan. 28, 2021 |  |  | GoP | 15183800 | 15183800 |  | 13677200 | 13677200 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-12-21 | 2020-12-21 | 2020-12-21 | 2020-12-21 | 2021-01-12
| Procurement of Food Items Food Items for CY 2021 BangUN Implimentation in Sulu Province. | [19 empty] | BangUN | YES | Competitive Bidding | 2020-12-27 | 2020-12-27 | 2020-12-29 | 2021-01-11 | 2021-01-11 | 2021-01-12 | ONLINE | Jan. 20, 2023 | Jan. 21, 2021 | Jan. 28, 2021 | Jan. 28, 2021 |  |  | GoP | 17849600 | 17849600 |  | 17814400 | 17814400 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-12-21 | 2020-12-21 | 2020-12-21 | 2020-12-21 | 2021-01-12
| Procurement of CY 2021 1st Semester Grocery Items for Home for the Elderly. | [19 empty] | HFE | YES | Competitive Bidding | 2020-12-28 | 2020-12-28 | 2020-12-29 | 2021-01-12 | 2021-01-12 | 2021-01-12 | Jan. 19, 2021 | Jan. 20, 2024 | Jan. 21, 2021 | Jan. 28, 2021 | Jan. 28, 2021 |  |  | GoP | 1609425 | 1609425 |  | 1412718.56 | 1412718.56 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-12-21 | 2020-12-21 | 2020-12-21 | 2020-12-21 | 2021-01-12
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 367212369.7
| Prepared by: | [22 empty] | 2020-12-11: Recommended for Approval by: | [11 empty] | APPROVED:
| XANTHI ROMEILLA J. VALLECER | [20 empty] | MA. SOCORRO S. MACASO |  | 2020-11-12: MA. LOURDEZ U. AMILHAMJA; 2020-12-11: FE L. DELA CRUZ |  | MARIA CORAZON G. SUMICAD | [9 empty] | FATIMA S. CAMINAN
| BAC Secretariat | [20 empty] | BAC MEMBER |  | 2020-11-12: BAC MEMBER; 2020-12-11: BAC VICE CHAIR |  | BAC Chairperson | [9 empty] | OIC-REGIONAL DIRECTOR/HOPE

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement

## Sheet2
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | (Name of Agency) Procurement Monitoring Report as of month/day/year
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
[38 empty] | 0 |  |  | 0
ITB-2020-05-040 | Construction of Playground and Repair of Multi Purpose Building (RSCC) | [19 empty] | RSCC/ CRCF | NO | Competitive Bidding | 2019-12-18 | 2020-05-22 | 2020-05-29 | 2020-06-10 | 2020-06-10 | 15-16 Jun-2020 | 2020-06-24 | 2020-06-25 | 2020-07-30 | 2020-09-14 | 2020-09-14 |  |  | GoP | 745698.13 |  | 745698.13 | 730840.32 |  | 730840.32 | COA, PICE and Los Contratistas de la Ciudad de Zamboanga | May 22, 2020 | May 22, 2020 | May 22, 2020 | May 22, 2020 | June 18, 2020
ITB-2020-05-042 | Upgrading of Admin Building (HE) | [19 empty] | HOME FOR ELDERLY/ CRCF | NO | Competitive Bidding | 2019-12-18 | 2020-05-23 | 2020-05-29 | 2020-06-10 | 2020-06-10 | 15-16 Jun-2020 | 2020-06-26 | 2020-07-01 | 2020-07-30 | 2020-09-07 | 2020-09-09 |  |  | GoP | 4449485.92 |  | 4449485.92 | 4441004.24 |  | 4441004.24 | COA, PICE and Los Contratistas de la Ciudad de Zamboanga | May 22, 2020 | May 22, 2020 | May 22, 2020 | May 22, 2020 | June 18, 2020
ITB-2020-05-043 | Upgrading of Residents' Quarter Phase II (HE) | [19 empty] | HOME FOR ELDERLY/ CRCF | NO | Competitive Bidding | 2019-12-18 | 2020-05-22 | 2020-05-29 | 2020-06-10 | 2020-06-10 | 15-16 Jun-2020 | 2020-06-24 | 2020-06-25 | 2020-07-29 | 2020-09-10 | 2020-09-14 |  |  | GoP | 2601662.15 |  | 2601662.15 | 2600518.71 |  | 2600518.71 | COA, PICE and Los Contratistas de la Ciudad de Zamboanga | May 22, 2020 | May 22, 2020 | May 22, 2020 | May 22, 2020 | June 18, 2020
ITB-2020-05-046 | Embankment (PCDP) | [19 empty] | PCDP | NO | Competitive Bidding | 2020-06-25 | 2020-07-01 | 2020-07-07 | 2020-07-24 | 2020-07-24 | 2020-07-28 | 2020-08-06 | 2020-08-12 | 2020-09-11 | 2020-10-05 | 2020-10-06 |  |  | GoP | 616674.08 |  | 616674.08 | 603990.38 |  | 603990.38 | COA, PICE and Los Contratistas de la Ciudad de Zamboanga | 2020-06-29 | 2020-06-29 | 2020-06-29 | 2020-06-29 | 2021-07-30
ITB-2020-05-047 | Upgrading of Electrical System in DSWD Compound | [19 empty] | AVRC/ CRCF | NO | Competitive Bidding | 2019-12-18 | 2020-05-22 | 2020-05-29 | 2020-06-10 | 2020-06-10 | 15-16 Jun-2020 | 2020-06-26 | 2020-07-01 | 2020-07-30 | 2020-09-07 | 2020-09-09 |  |  | GoP | 25772663.7 |  | 25772663.7 | 24411873.76 |  | 24411873.76 | COA, PICE and Los Contratistas de la Ciudad de Zamboanga | May 22, 2020 | May 22, 2020 | May 22, 2020 | May 22, 2020 | June 18, 2020
ITB-2020-05-048 | Construction of Multi Purpose Building (RRCY) | [19 empty] | RRCY/ CRCF | NO | Competitive Bidding | 2019-12-18 | 2020-05-22 | 2020-05-29 | 2020-06-10 | 2020-06-10 | 15-16 Jun-2020 | 2020-06-25 | 2020-07-01 | 2020-07-30 | 2020-09-11 | 2020-09-11 |  |  | GoP | 7755383.34 |  | 7755383.34 | 7740750.55 |  | 7740750.55 | COA, PICE and Los Contratistas de la Ciudad de Zamboanga | May 22, 2020 | May 22, 2020 | May 22, 2020 | May 22, 2020 | June 18, 2020
ITB-2020-05-049 | Construction of Perimeter Fence (RRCY) | [19 empty] | RRCY/CRCF | NO | Competitive Bidding | 2019-12-18 | 2020-05-22 | 2020-05-29 | 2020-06-10 | 2020-06-10 | 15-16 Jun-2020 | 2020-06-26 | 2020-07-01 | 2020-09-18 | 2020-10-07 | 2020-10-07 |  |  | GoP | 6128010.06 |  | 6128010.06 | 5015976 |  | 5015976 | COA, PICE and Los Contratistas de la Ciudad de Zamboanga | May 22, 2020 | May 22, 2020 | May 22, 2020 | May 22, 2020 | June 18, 2020
ITB-2020-05-050 | Upgrading and Construction of Perimeter Fence, Three Main Gate Entrance (BDSK) | [19 empty] | BDSK/CRCF | NO | Competitive Bidding | 2019-12-18 | 2020-05-22 | 2020-05-29 | 2020-06-10 | 2020-06-10 | 15-16 Jun-2020 | 2020-06-26 | 2020-07-01 | 2020-09-18 | 2020-09-30 | 2020-10-01 |  |  | GoP | 3759704.82 |  | 3759704.82 | 3196673.02 |  | 3196673.02 | COA, PICE and Los Contratistas de la Ciudad de Zamboanga | May 22, 2020 | May 22, 2020 | May 22, 2020 | May 22, 2020 | June 18, 2020
ITB-2020-05-051 | 2nd Public Bidding: Construction of Water Tower for PCDP, HFW, HE AND RSCC | [19 empty] | CRCF/PCDP/HFW/HE/RSCC | NO | Competitive Bidding | 2020-01-25 | 2020-05-22 | 2020-07-07 | 2020-07-20 | 2020-07-20 | 2020-07-20 | 2020-08-06 | 2020-08-12 | 2020-09-18 | 2020-10-07 | 2020-10-07 |  |  | GoP | 3005951.81 |  | 3005951.81 |  |  |  | COA, PICE and Los Contratistas de la Ciudad de Zamboanga | 2020-06-29 | 2020-06-29 | 2020-06-29 | 2020-06-29 | 2020-07-30
ITB-2020-06-052 | 2nd Public Bidding: Construction of Kitchen and Laundry Pathwalk and 2nd Public Bidding: Construction of Covered Path Walk | [19 empty] | AVRC/ CRCF | NO | Competitive Bidding | 2020-01-25 | 2020-05-22 | 2020-07-07 | 2020-07-20 | 2020-07-20 | 2020-07-20 | 2020-08-06 | 2020-08-12 | 2020-09-11 | 2020-10-01 | 2020-10-01 |  |  | GoP | 1538063.27 |  | 1538063.27 | 1361169.63 |  | 1361169.63 | COA, PICE and Los Contratistas de la Ciudad de Zamboanga | 2020-06-29 | 2020-06-29 | 2020-06-29 | 2020-06-29 | 2020-07-30
ITB-2020-07-053 | Upgrading Of Electrical System in Home for the Elderly. | [19 empty] | HFE/CRCF | NO | Competitive Bidding | 2020-07-08 | 2020-07-09 | 2020-07-23 | 2020-08-04 | 2020-08-04 | 2020-08-05 | 2020-09-01 | 2020-09-02 | 2020-09-18 | 2020-10-09 | 2020-10-09 |  |  | GoP | 2064946.44 |  | 2064946.44 | 1781498.35 |  | 1781498.35 | COA, PICE and Los Contratistas de la Ciudad de Zamboanga | 2020-07-08 | 2020-07-08 | 2020-07-08 | 2020-07-08 | 2020-08-24
[38 empty] | 0 |  |  | 0
[21 empty] | Prepared by: |  |  | 2020-09-18: Recommended for Approval by: | [8 empty] | APPROVED:
[21 empty] | BAC Secretariat |  |  | 2020-09-18: BAC Chairperson | [8 empty] | Head of the Procuring Entity

## Sheet3
ITB-2020-09-066 | Procurement of Eggs for SFP 10th Cycle Implementation in Zamboanga Del Sur (ZDS) District 1
ITB-2020-09-077 | Procurement of Perishable Goods for SFP 10th Cycle Implementation in Zamboanga Sibugay Province (ZSP) District 1

## Sheet4
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | (Name of Agency) Procurement Monitoring Report as of month/day/year
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
[38 empty] | 0 |  |  | 0
ITB-2020-05-040 | Construction of Playground and Repair of Multi Purpose Building (RSCC) | [19 empty] | RSCC/ CRCF | NO | Competitive Bidding | 2019-12-18 | 2020-05-22 | 2020-05-29 | 2020-06-10 | 2020-06-10 | 15-16 Jun-2020 | 2020-06-24 | 2020-06-25 | 2020-07-30 | 2020-09-14 | 2020-09-14 | Dec. 7, 2020 |  | GoP | 745698.13 |  | 745698.13 | 730840.32 |  | 730840.32 | COA, PICE and Los Contratistas de la Ciudad de Zamboanga | May 22, 2020 | May 22, 2020 | May 22, 2020 | May 22, 2020 | June 18, 2020
ITB-2020-05-046 | Embankment (PCDP) | [19 empty] | PCDP | NO | Competitive Bidding | 2020-06-25 | 2020-07-01 | 2020-07-07 | 2020-07-24 | 2020-07-24 | 2020-07-28 | 2020-08-06 | 2020-08-12 | 2020-09-11 | 2020-10-05 | 2020-10-06 | Oct. 27, 2020 |  | GoP | 616674.08 |  | 616674.08 | 603990.38 |  | 603990.38 | COA, PICE and Los Contratistas de la Ciudad de Zamboanga | 2020-06-29 | 2020-06-29 | 2020-06-29 | 2020-06-29 | 2021-07-30
ITB-2020-06-052 | 2nd Public Bidding: Construction of Kitchen and Laundry Pathwalk and 2nd Public Bidding: Construction of Covered Path Walk | [19 empty] | AVRC/ CRCF | NO | Competitive Bidding | 2020-01-25 | 2020-05-22 | 2020-07-07 | 2020-07-20 | 2020-07-20 | 2020-07-20 | 2020-08-06 | 2020-08-12 | 2020-09-11 | 2020-10-01 | 2020-10-01 | Dec. 28, 2020 |  | GoP | 1538063.27 |  | 1538063.27 | 1361169.63 |  | 1361169.63 | COA, PICE and Los Contratistas de la Ciudad de Zamboanga | 2020-06-29 | 2020-06-29 | 2020-06-29 | 2020-06-29 | 2020-07-30
[38 empty] | 0 |  |  | 0
[38 empty] | 0 |  |  | 0
Total Alloted Budget of Procurement Activities | [37 empty] | 2900435.48
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 2696000.33
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 204435.15
0N-GOING PROCUREMENT ACTIVITIES
ITB-2020-05-042 | Upgrading of Admin Building (HE) | [19 empty] | HOME FOR ELDERLY/ CRCF | NO | Competitive Bidding | 2019-12-18 | 2020-05-23 | 2020-05-29 | 2020-06-10 | 2020-06-10 | 15-16 Jun-2020 | 2020-06-26 | 2020-07-01 | 2020-07-30 | 2020-09-07 | 2020-09-09 |  |  | GoP | 4449485.92 |  | 4449485.92 | 4441004.24 |  | 4441004.24 | COA, PICE and Los Contratistas de la Ciudad de Zamboanga | May 22, 2020 | May 22, 2020 | May 22, 2020 | May 22, 2020 | June 18, 2020
ITB-2020-05-043 | Upgrading of Residents' Quarter Phase II (HE) | [19 empty] | HOME FOR ELDERLY/ CRCF | NO | Competitive Bidding | 2019-12-18 | 2020-05-22 | 2020-05-29 | 2020-06-10 | 2020-06-10 | 15-16 Jun-2020 | 2020-06-24 | 2020-06-25 | 2020-07-29 | 2020-09-10 | 2020-09-14 |  |  | GoP | 2601662.15 |  | 2601662.15 | 2600518.71 |  | 2600518.71 | COA, PICE and Los Contratistas de la Ciudad de Zamboanga | May 22, 2020 | May 22, 2020 | May 22, 2020 | May 22, 2020 | June 18, 2020
ITB-2020-05-047 | Upgrading of Electrical System in DSWD Compound | [19 empty] | AVRC/ CRCF | NO | Competitive Bidding | 2019-12-18 | 2020-05-22 | 2020-05-29 | 2020-06-10 | 2020-06-10 | 15-16 Jun-2020 | 2020-06-26 | 2020-07-01 | 2020-07-30 | 2020-09-07 | 2020-09-09 |  |  | GoP | 25772663.7 |  | 25772663.7 | 24411873.76 |  | 24411873.76 | COA, PICE and Los Contratistas de la Ciudad de Zamboanga | May 22, 2020 | May 22, 2020 | May 22, 2020 | May 22, 2020 | June 18, 2020
ITB-2020-05-048 | Construction of Multi Purpose Building (RRCY) | [19 empty] | RRCY/ CRCF | NO | Competitive Bidding | 2019-12-18 | 2020-05-22 | 2020-05-29 | 2020-06-10 | 2020-06-10 | 15-16 Jun-2020 | 2020-06-25 | 2020-07-01 | 2020-07-30 | 2020-09-11 | 2020-09-11 |  |  | GoP | 7755383.34 |  | 7755383.34 | 7740750.55 |  | 7740750.55 | COA, PICE and Los Contratistas de la Ciudad de Zamboanga | May 22, 2020 | May 22, 2020 | May 22, 2020 | May 22, 2020 | June 18, 2020
ITB-2020-05-049 | Construction of Perimeter Fence (RRCY) | [19 empty] | RRCY/CRCF | NO | Competitive Bidding | 2019-12-18 | 2020-05-22 | 2020-05-29 | 2020-06-10 | 2020-06-10 | 15-16 Jun-2020 | 2020-06-26 | 2020-07-01 | 2020-09-18 | 2020-10-07 | 2020-10-07 |  |  | GoP | 6128010.06 |  | 6128010.06 | 5015976 |  | 5015976 | COA, PICE and Los Contratistas de la Ciudad de Zamboanga | May 22, 2020 | May 22, 2020 | May 22, 2020 | May 22, 2020 | June 18, 2020
ITB-2020-05-050 | Upgrading and Construction of Perimeter Fence, Three Main Gate Entrance (BDSK) | [19 empty] | BDSK/CRCF | NO | Competitive Bidding | 2019-12-18 | 2020-05-22 | 2020-05-29 | 2020-06-10 | 2020-06-10 | 15-16 Jun-2020 | 2020-06-26 | 2020-07-01 | 2020-09-18 | 2020-09-30 | 2020-10-01 |  |  | GoP | 3759704.82 |  | 3759704.82 | 3196673.02 |  | 3196673.02 | COA, PICE and Los Contratistas de la Ciudad de Zamboanga | May 22, 2020 | May 22, 2020 | May 22, 2020 | May 22, 2020 | June 18, 2020
ITB-2020-05-051 | 2nd Public Bidding: Construction of Water Tower for PCDP, HFW, HE AND RSCC | [19 empty] | CRCF/PCDP/HFW/HE/RSCC | NO | Competitive Bidding | 2020-01-25 | 2020-05-22 | 2020-07-07 | 2020-07-20 | 2020-07-20 | 2020-07-20 | 2020-08-06 | 2020-08-12 | 2020-09-18 | 2020-10-07 | 2020-10-07 |  |  | GoP | 3005951.81 |  | 3005951.81 |  |  |  | COA, PICE and Los Contratistas de la Ciudad de Zamboanga | 2020-06-29 | 2020-06-29 | 2020-06-29 | 2020-06-29 | 2020-07-30
ITB-2020-07-053 | Upgrading Of Electrical System in Home for the Elderly. | [19 empty] | HFE/CRCF | NO | Competitive Bidding | 2020-07-08 | 2020-07-09 | 2020-07-23 | 2020-08-04 | 2020-08-04 | 2020-08-05 | 2020-09-01 | 2020-09-02 | 2020-09-18 | 2020-10-09 | 2020-10-09 |  |  | GoP | 2064946.44 |  | 2064946.44 | 1781498.35 |  | 1781498.35 | COA, PICE and Los Contratistas de la Ciudad de Zamboanga | 2020-07-08 | 2020-07-08 | 2020-07-08 | 2020-07-08 | 2020-08-24
ITB-2020-07-054 | Provision of Service Provider for the Digitization of Permanent and Valuable Records of DSWD FO IX | [19 empty] | Records | NO | Competitive Bidding | 2020-07-08 | 2020-07-09 | 2020-07-23 | 2020-08-04 | 2020-08-05 | 2020-09-09 | 2020-09-04 | 2020-09-22 | 2020-10-05 | 2020-10-30 | 2020-10-30 |  |  | GoP | 1500000 | 1500000 |  | 1372500 | 1372500 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-07-09 | 2020-07-09 | 2020-07-09 | 2020-07-09
ITB-2020-08-056 | Procurement of Grocery Items for BANGUN Implementation in Basilan Province | [19 empty] | BangUN | NO | Competitive Bidding | 2020-07-21 | 2020-08-04 | 2020-08-07 | 2020-09-02 | 2020-09-02 | 2020-09-09 | 2020-12-14 | 2020-12-14 | 2020-12-16 | 2020-12-23 | 2020-12-23 |  |  | GoP | 3408935 | 3408935 |  | 3299996 | 3299996 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-07-30 | 2020-07-30 | 2020-07-30 | 2020-07-30
ITB-2020-08-057 | Procurement of Semi-Perishable Items for BANGUN Implementation in Basilan Province | [19 empty] | BangUN | NO | Competitive Bidding | 2020-07-21 | 2020-08-04 | 2020-08-07 | 2020-09-02 | 2020-09-02 | 2020-09-09 | 2020-12-14 | 2020-12-14 | 2020-12-16 | 2020-12-23 | 2020-12-23 |  |  | GoP | 6409325 | 6409325 |  | 6368700 | 6368700 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-07-30 | 2020-07-30 | 2020-07-30 | 2020-07-30
ITB-2020-08-059 | Procurement of Grocery Items for BANGUN Implementation in Tawi-Tawi Province | [19 empty] | BangUN | NO | Competitive Bidding | 2020-07-21 | 2020-08-04 | 2020-08-07 | 2020-09-02 | 2020-09-02 | 2020-09-09 | 2020-12-14 | 2020-12-14 | 2020-12-16 | 2020-12-23 | 2020-12-23 |  |  | GoP | 3349185 | 3349185 |  | 3301496 | 3301496 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-07-30 | 2020-07-30 | 2020-07-30 | 2020-07-30
ITB-2020-08-060 | Procurement of Semi-Perishable Items for BANGUN Implementation in Tawi-Tawi Province | [19 empty] | BangUN | NO | Competitive Bidding | 2020-07-21 | 2020-08-04 | 2020-08-07 | 2020-09-02 | 2020-09-02 | 2020-09-09 | 2020-12-14 | 2020-12-14 | 2020-12-16 | 2020-12-23 | 2020-12-23 |  |  | GoP | 6580675 | 6580675 |  | 6368700 | 6368700 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-07-30 | 2020-07-30 | 2020-07-30 | 2020-07-30
ITB-2020-08-062 | Procurement of Grocery Items for BANGUN Implementation in Sulu Province | [19 empty] | BangUN | NO | Competitive Bidding | 2020-07-21 | 2020-08-04 | 2020-08-07 | 2020-09-02 | 2020-09-02 | 2020-09-09 | 2020-12-14 | 2020-12-14 | 2020-12-16 | 2020-12-23 | 2020-12-23 |  |  | GoP | 4410284 | 4410284 |  | 4394210 | 4394210 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-07-30 | 2020-07-30 | 2020-07-30 | 2020-07-30
ITB-2020-08-063 | Procurement of Semi-Perishable Items for BANGUN Implementation in Sulu Province | [19 empty] | BangUN | NO | Competitive Bidding | 2020-07-21 | 2020-08-04 | 2020-08-07 | 2020-09-02 | 2020-09-02 | 2020-09-09 | 2020-12-14 | 2020-12-14 | 2020-12-16 | 2020-12-23 | 2020-12-23 |  |  | GoP | 5099585 | 5099585 |  | 4948590 | 4948590 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-07-30 | 2020-07-30 | 2020-07-30 | 2020-07-30
ITB-2020-09-064 | Procurement of Commercial Rice for SFP 10th Cycle Implementation in Zamboanga Del Sur (ZDS) District 1 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-15 | 2020-10-15 | 2020-10-20 | 2020-11-06 | 2020-11-12 | 2020-12-04 | 2020-12-18 | 2020-12-22 |  |  | GoP | 4152500 | 4152500 |  | 4119280 | 4119280 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-01
ITB-2020-09-065 | Procurement of Whole Dressed Chicken for SFP 10th Cycle Implementation in Zamboanga Del Sur (ZDS) District 1 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-15 | 2020-10-15 | 2020-10-20 | 2020-11-06 | 2020-11-12 | 2020-12-04 | 2020-12-18 | 2020-12-22 |  |  | GoP | 6239000 | 6239000 |  | 6207805 | 6207805 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-01
ITB-2020-09-066 | Procurement of Eggs for SFP 10th Cycle Implementation in Zamboanga Del Sur (ZDS) District 1 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-15 | 2020-10-15 | 2020-10-20 | 2020-11-06 | 2020-11-12 | 2020-12-04 | 2020-12-18 | 2020-12-22 |  |  | GoP | 3996776 | 3996776 |  | 3968227.6 | 3968227.6 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-01
ITB-2020-09-068 | Procurement of Grocery Items for SFP 10th Cycle Implementation in Zamboanga Del Sur (ZDS) District 1 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-15 | 2020-10-15 | 2020-10-20 | 2020-11-06 | 2020-11-12 | 2020-12-04 | 2020-12-18 | 2020-12-22 |  |  | GoP | 13002373 | 13002373 |  | 12986801 | 12986801 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-01
ITB-2020-09-069 | Procurement of Commercial Rice for SFP 10th Cycle Implementation in Zamboanga Del Sur (ZDS) District 2 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-15 | 2020-10-15 | 2020-10-20 | 2020-11-06 | 2020-11-12 | 2020-12-04 | 2020-12-18 | 2020-12-22 |  |  | GoP | 3060000 | 3060000 |  | 3035520 | 3035520 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-01
ITB-2020-09-070 | Procurement of Whole Dressed Chicken for SFP 10th Cycle Implementation in Zamboanga Del Sur (ZDS) District 2 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-15 | 2020-10-15 | 2020-10-20 | 2020-11-06 | 2020-11-12 | 2020-12-04 | 2020-12-18 | 2020-12-22 |  |  | GoP | 4598400 | 4598400 |  | 4575408 | 4575408 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-01
ITB-2020-09-071 | Procurement of Eggs for SFP 10th Cycle Implementation in Zamboanga Del Sur (ZDS) District 2 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-15 | 2020-10-15 | 2020-10-20 | 2020-11-06 | 2020-11-12 | 2020-12-04 | 2020-12-18 | 2020-12-22 |  |  | GoP | 2945712 | 2945712 |  | 2924671.2 | 2924671.2 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-01
ITB-2020-09-073 | Procurement of Grocery Items for SFP 10th Cycle Implementation in Zamboanga Del Sur (ZDS) District 2 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-15 | 2020-10-15 | 2020-10-20 | 2020-11-06 | 2020-11-12 | 2020-12-04 | 2020-12-21 | 2020-12-22 |  |  | GoP | 9583438 | 9583438 |  | 9564306 | 9564306 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-01
ITB-2020-09-074 | Procurement of Commercial Rice for SFP 10th Cycle Implementation in Zamboanga Sibugay Province (ZSP) District 1 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-16 | 2020-10-16 | 2020-10-20 | 2020-11-11 | 2020-11-12 | 2020-12-04 | 2020-12-21 | 2020-12-22 |  |  | GoP | 2502500 | 2502500 |  | 2492490 | 2492490 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-02
ITB-2020-09-075 | Procurement of Whole Dressed Chicken for SFP 10th Cycle Implementation in Zamboanga Sibugay Province (ZSP) District 1 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-16 | 2020-10-16 | 2020-10-20 | 2020-11-11 | 2020-11-12 | 2020-12-04 | 2020-12-21 | 2020-12-22 |  |  | GoP | 3761200 | 3761200 |  | 3723588 | 3723588 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-02
ITB-2020-09-076 | Procurement of Eggs for SFP 10th Cycle Implementation in Zamboanga Sibugay Province (ZSP) District 1 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-16 | 2020-10-16 | 2020-10-20 | 2020-11-11 | 2020-11-12 | 2020-12-04 | 2020-12-21 | 2020-12-22 |  |  | GoP | 2409099 | 2409099 |  | 2409099 | 2409099 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-02
ITB-2020-09-077 | Procurement of Perishable Goods for SFP 10th Cycle Implementation in Zamboanga Sibugay Province (ZSP) District 1 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-16 | 2020-10-16 | 2020-10-20 | ONLINE | 2020-11-12 | 2020-12-04 |  |  |  |  | GoP | 2262130 | 2262130 |  | 2213670 | 2213670 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-02
ITB-2020-09-078 | Procurement of Grocery Items for SFP 10th Cycle Implementation in Zamboanga Sibugay Province (ZSP) District 1 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-16 | 2020-10-16 | 2020-10-20 | 2020-11-11 | 2020-11-12 | 2020-12-04 | 2020-12-21 | 2020-12-22 |  |  | GoP | 7837271 | 7837271 |  | 7827923 | 7827923 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-02
ITB-2020-09-079 | Procurement of Commercial Rice for SFP 10th Cycle Implementation in Zamboanga Sibugay Province (ZSP) District 2 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-16 | 2020-10-16 | 2020-10-20 | 2020-11-11 | 2020-11-12 | 2020-12-04 | 2020-12-18 | 2020-12-22 |  |  | GoP | 3710000 | 3710000 |  | 3695160 | 3695160 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-02
ITB-2020-09-080 | Procurement of Whole Dressed Chicken for SFP 10th Cycle Implementation in Zamboanga Sibugay Province (ZSP) District 2 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-16 | 2020-10-16 | 2020-10-20 | 2020-11-11 | 2020-11-12 | 2020-12-04 | 2020-12-18 | 2020-12-22 |  |  | GoP | 5574400 | 5574400 |  | 5546528 | 5546528 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-02
ITB-2020-09-081 | Procurement of Eggs for SFP 10th Cycle Implementation in Zamboanga Sibugay Province (ZSP) District 2 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-16 | 2020-10-16 | 2020-10-20 | 2020-11-11 | 2020-11-12 | 2020-12-04 | 2020-12-18 | 2020-12-22 |  |  | GoP | 3570798 | 3570798 |  | 3545292.3 | 3545292.3 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-02
ITB-2020-09-082 | Procurement of Perishable Goods for SFP 10th Cycle Implementation in Zamboanga Sibugay Province (ZSP) District 2 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-16 | 2020-10-16 | 2020-10-20 | ONLINE | 2020-11-12 | 2020-12-04 |  |  |  |  | GoP | 3352760 | 3352760 |  | 3280890 | 3280890 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-02
ITB-2020-09-083 | Procurement of Grocery Items for SFP 10th Cycle Implementation in Zamboanga Sibugay Province (ZSP) District 2 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-16 | 2020-10-16 | 2020-10-20 | 2020-11-11 | 2020-11-12 | 2020-12-04 | 2020-12-18 | 2020-12-22 |  |  | GoP | 11616442 | 11616442 |  | 11607186 | 11607186 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-02
ITB-2020-09-084 | Procurement of Commercial Rice for SFP 10th Cycle Implementation in Zamboanga Del Norte (ZDN) District 1 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-17 | 2020-10-17 | 2020-10-20 | 2020-11-11 | 2020-11-12 | 2020-12-04 | 2020-12-21 | 2020-12-22 |  |  | GoP | 1746250 | 1746250 |  | 1739265 | 1739265 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
ITB-2020-09-086 | Procurement of Eggs for SFP 10th Cycle Implementation in Zamboanga Del Norte (ZDN) District 1 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-17 | 2020-10-17 | 2020-10-20 | 2020-11-09 | 2020-11-12 | 2020-12-04 |  |  |  |  | GoP | 1681400 | 1681400 |  | 1633360 | 1633360 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
ITB-2020-09-087 | Procurement of Perishable Goods for SFP 10th Cycle Implementation in Zamboanga Del Norte (ZDN) District 1 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-17 | 2020-10-17 | 2020-10-20 | 2020-11-09 | 2020-11-12 | 2020-12-04 |  |  |  |  | GoP | 1579019 | 1579019 |  | 1535507 | 1535507 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
ITB-2020-09-088 | Procurement of Grocery Items for SFP 10th Cycle Implementation in Zamboanga Del Norte (ZDN) District 1 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-17 | 2020-10-17 | 2020-10-20 | ONLINE | 2020-11-12 | 2020-12-04 |  |  |  |  | GoP | 5470331 | 5470331 |  | 5437554.1 | 5437554.1 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
ITB-2020-09-090 | Procurement of Whole Dressed Chicken for SFP 10th Cycle Implementation in Zamboanga Del Norte (ZDN) District 2 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-17 | 2020-10-17 | 2020-10-20 | ONLINE | 2020-11-12 | 2020-12-04 | 2020-12-23 | 2020-12-23 |  |  | GoP | 3966400 | 3966400 |  | 3867240 | 3867240 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
ITB-2020-09-091 | Procurement of Eggs for SFP 10th Cycle Implementation in Zamboanga Del Norte (ZDN) District 2 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-17 | 2020-10-17 | 2020-10-20 | 2020-11-11 | 2020-11-12 | 2020-12-04 |  |  |  |  | GoP | 2540524 | 2540524 |  | 1814660 | 1814660 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
ITB-2020-09-092 | Procurement of Perishable Goods for SFP 10th Cycle Implementation in Zamboanga Del Norte (ZDN) District 2 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-17 | 2020-10-17 | 2020-10-20 | 2020-11-09 | 2020-11-12 | 2020-12-04 |  |  |  |  | GoP | 2385684 | 2385684 |  | 2319733 | 2319733 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
ITB-2020-09-093 | Procurement of Grocery Items for SFP 10th Cycle Implementation in Zamboanga Del Norte (ZDN) District 2 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-17 | 2020-10-17 | 2020-10-20 | ONLINE | 2020-11-12 | 2020-12-04 |  |  |  |  | GoP | 8265042 | 8265042 |  | 8215536.2 | 8215536.2 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
| Procurement of Whole Dressed Chicken for SFP 10th Cycle Implementation in Zamboanga Del Norte (ZDN) District 3 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-17 | 2020-10-17 | 2020-10-20 | ONLINE | 2020-11-12 | 2020-12-04 | 2020-12-23 | 2020-12-23 |  |  | GoP | 4863600 | 4863600 |  | 4742010 | 4742010 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
ITB-2020-09-096 | Procurement of Eggs for SFP 10th Cycle Implementation in Zamboanga Del Norte (ZDN) District 3 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-17 | 2020-10-17 | 2020-10-20 | ONLINE | 2020-11-12 | 2020-12-04 | 2020-12-23 | 2020-12-23 |  |  | GoP | 3115504 | 3115504 |  | 3115504 | 3115504 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
ITB-2020-09-097 | Procurement of Perishable Goods for SFP 10th Cycle Implementation in Zamboanga Del Norte (ZDN) District 3 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-17 | 2020-10-17 | 2020-10-20 | ONLINE | 2020-11-12 | 2020-12-04 | 2020-12-23 | 2020-12-23 |  |  | GoP | 2925573 | 2925573 |  | 2862910 | 2862910 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
ITB-2020-09-098 | Procurement of Grocery Items for SFP 10th Cycle Implementation in Zamboanga Del Norte (ZDN) District 3 | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-17 | 2020-10-17 | 2020-10-20 | ONLINE | 2020-11-12 | 2020-12-04 | 2020-12-23 | 2020-12-23 |  |  | GoP | 10135673 | 10135673 |  | 10074974.3 | 10074974.3 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
ITB-2020-09-099 | Procurement of Commercial Rice for SFP 10th Cycle Implementation in Zamboanga City and Sibuco | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-19 | 2020-10-19 | 2020-10-20 | 2020-11-11 | 2020-12-04 | 2020-12-07 | 2020-12-07 |  |  |  | GoP | 3882500 | 3882500 |  | 3416600 | 3416600 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
ITB-2020-09-100 | Procurement of Whole Dressed Chicken for SFP 10th Cycle Implementation in Zamboanga City and Sibuco | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-19 | 2020-10-19 | 2020-10-20 | 2020-11-11 | 2020-12-04 | 2020-12-04 | 2020-12-21 | 2020-12-22 |  |  | GoP | 5833800 | 5833800 |  | 5687955 | 5687955 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
ITB-2020-09-101 | Procurement of Eggs for SFP 10th Cycle Implementation in Zamboanga City and Sibuco | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-19 | 2020-10-19 | 2020-10-20 | 2020-11-11 | 2020-12-04 | 2020-12-04 | 2020-12-21 | 2020-12-22 |  |  | GoP | 3737097 | 3737097 |  | 3737097 | 3737097 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
ITB-2020-09-103 | Procurement of Grocery Items for SFP 10th Cycle Implementation in Zamboanga City and Sibuco | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-19 | 2020-10-19 | 2020-10-20 | ONLINE | 2020-12-04 | 2020-12-04 | 2020-12-23 | 2020-12-23 |  |  | GoP | 12157882 | 12157882 |  | 12089913.2 | 12089913.2 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
ITB-2020-09-104 | Procurement of Commercial Rice for SFP 10th Cycle Implementation in Isabela City | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-19 | 2020-10-19 | 2020-10-20 | 2020-11-11 | 2020-12-04 | 2020-12-07 |  |  |  |  | GoP | 1131570 | 1131570 |  | 1005048 | 1005048 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
ITB-2020-09-105 | Procurement of Whole Dressed Chicken for SFP 10th Cycle Implementation in Isabela City | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-19 | 2020-10-19 | 2020-10-20 | ONLINE | 2020-12-04 | 2020-12-04 | 2020-12-23 | 2020-12-23 |  |  | GoP | 1600000 | 1600000 |  | 1560000 | 1560000 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
ITB-2020-09-106 | Procurement of Perishable Goods for SFP 10th Cycle Implementation in Isabela City | [19 empty] | SFP | NO | Competitive Bidding | 2020-09-19 | 2020-09-24 | 2020-10-03 | 2020-10-19 | 2020-10-19 | 2020-10-20 | ONLINE | 2020-12-04 | 2020-12-04 | 2020-12-23 | 2020-12-23 |  |  | GoP | 1467210 | 1467210 |  | 1466571 | 1466571 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-11-04
ITB-2020-09-108 | Procurement of Electrical Works of DSWD Fo IX | [19 empty] | GENSERVE | YES | Competitive Bidding | 2020-10-15 | 2020-11-13 | 2020-11-21 | 2020-12-03 | 2020-12-03 | 2020-12-03 | 2020-12-11 | 2020-12-12 | 2020-12-14 | 2020-12-23 | 2020-12-28 |  |  |  | 1569763.5 |  | 1569763.5 | 1540843.84 |  | 1540843.84 | COA, TZU Chi Foundation and ZC Chamber of Commerce & PICE ZC Chapter | 2020-11-13 | 2020-11-13 | 2020-11-13 | 2020-11-13 | 2020-12-03
ITB-2020-03-109 | Procurement of Perishable Goodsfor the SFP 10th Cycle Implementation in District 1 Zamboanga del Sur (ZDS) District 1 (Negotiated Procurement 2 failed Bidding) | [19 empty] | SFP | NO | NP-53.1 Two Failed Biddings | 2020-12-03 | 2020-12-15 | 2020-12-21 | 2020-12-26 | 2020-12-26 | 2020-12-26 | n/a | 2020-12-26 | [5 empty] | GoP | 3752951 | 3752951 |  | 3174198.6 | 3174198.6 |  | n/a | n/a | n/a | n/a | n/a | n/a
ITB-2020-03-110 | Procurement of Perishable Goods for SFP 10th Cycle Implementation in District 2 Zamboanga Del Sur (ZDS) District 2 (Negotiated Procurement 2 failed Bidding) | [19 empty] | SFP | NO | NP-53.1 Two Failed Biddings | 2020-12-03 | 2020-12-15 | 2020-12-21 | 2020-12-26 | 2020-12-26 | 2020-12-26 | n/a | 2020-12-26 | [5 empty] | GoP | 2766050 | 2766050 |  | 2284940 | 2284940 |  | n/a | n/a | n/a | n/a | n/a | n/a
ITB-2020-03-111 | 2nd Public Bidding: Procurement of Commercial Rice for SFP 10th Cycle Implementation in District 2 Zamboanga Del Norte (ZDN) | [19 empty] | SFP | NO | Competitive Bidding | 2020-11-12 | 2020-11-12 | 2020-11-21 | 2020-12-03 | 2020-12-03 | 2020-12-03 | 2020-12-11 | 2020-12-11 | [5 empty] | GoP | 2638750 | 2638750 |  | . | . |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-11-13 | 2020-11-13 | 2020-11-13 | 2020-11-13 | 2020-12-03
ITB-2020-03-112 | Procurement of Commercial Rice for SFP 10th Cycle Implementation in District 3 Zamboanga Del Norte (ZDN) (Negotiated Procurement 2 failed Bidding) | [19 empty] | SFP | NO | NP-53.1 Two Failed Biddings | 2020-12-03 | 2020-12-15 | 2020-12-21 | 2020-12-26 | 2020-12-26 | 2020-12-26 | n/a | 2020-12-26 | [5 empty] | GoP | 3236250 | 3236250 |  | 3223305 | 3223305 |  | n/a | n/a | n/a | n/a | n/a | n/a
ITB-2020-03-113 | Procurement of Perishable Goods for SFP 10th Cycle Implementation in Zamboanga City & Sibuco (Negotiated Procurement 2 failed Bidding) | [19 empty] | SFP | NO | NP-53.1 Two Failed Biddings | 2020-12-03 | 2020-12-15 | 2020-12-21 | 2020-12-26 | 2020-12-26 | 2020-12-26 | n/a | 2020-12-26 | [5 empty] | GoP | 3509121 | 3509121 |  | 3506699 | 3506699 |  | n/a | n/a | n/a | n/a | n/a | n/a
ITB-2020-03-114 | 2ND PUBLIC BIDDING: PROCUREMENT OF PERISHABLE ITEMS FOR BANGUN IMPLEMENTATION IN BASILAN PROVINCE | [19 empty] | BangUN | NO | Competitive Bidding | 2020-11-27 | 2020-11-29 | 2020-12-07 | 2020-12-19 | 2020-12-19 | 2020-12-19 | ONLINE | 2020-12-26 | [5 empty] | GoP | 5679740 | 5679740 |  | 4589590 | 4589590 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-12-01 | 2020-12-01 | 2020-12-01 | 2020-12-01
ITB-2020-03-115 | PROCUREMENT OF PERISHABLE ITEMS FOR BANGUN IMPLEMENTATION IN SULU PROVINCE | [19 empty] | BangUN | NO | Competitive Bidding | 2020-11-27 | 2020-11-29 | 2020-12-07 | 2020-12-19 | 2020-12-19 | 2020-12-19 | ONLINE | 2020-12-26 | [5 empty] | GoP | 6474240 | 6474240 |  | 5335200 | 5335200 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-12-01 | 2020-12-01 | 2020-12-01 | 2020-12-01
ITB-2020-03-116 | 2ND PUBLIC BIDDING: PROCUREMENT OF PERISHABLE ITEMS FOR BANGUN IMPLEMENTATION IN TAWITAWI PROVINCE | [19 empty] | BangUN | NO | Competitive Bidding | 2020-11-27 | 2020-11-29 | 2020-12-07 | 2020-12-19 | 2020-12-19 | 2020-12-19 | ONLINE | 2020-12-26 | [5 empty] | GoP | 5568140 | 5568140 |  | 4589590 | 4589590 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-12-01 | 2020-12-01 | 2020-12-01 | 2020-12-01
ITB-2020-03-118 | Procurement of Food Items Food Items for CY 2021 BangUN Implimentation in Basilan Province. | [19 empty] | BangUN | YES | Competitive Bidding | 2020-12-27 | 2020-12-27 | 2020-12-29 | 2021-01-11 | 2021-01-11 | 2021-01-12 | [8 empty] | 15183800 | 15183800 |  | 14987401.2 | 14987401.2 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-12-21 | 2020-12-21 | 2020-12-21 | 2020-12-21
ITB-2020-03-119 | Procurement of Food Items Food Items for CY 2021 BangUN Implimentation in Tawi-Tawi Province. | [19 empty] | BangUN | YES | Competitive Bidding | 2020-12-27 | 2020-12-27 | 2020-12-29 | 2021-01-11 | 2021-01-11 | 2021-01-12 | [8 empty] | 15183800 | 15183800 |  | 13677200 | 13677200 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-12-21 | 2020-12-21 | 2020-12-21 | 2020-12-21
ITB-2020-03-120 | Procurement of Food Items Food Items for CY 2021 BangUN Implimentation in Sulu Province. | [19 empty] | BangUN | YES | Competitive Bidding | 2020-12-27 | 2020-12-27 | 2020-12-29 | 2021-01-11 | 2021-01-11 | 2021-01-12 | [8 empty] | 17849600 | 17849600 |  | 17814400 | 17814400 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-12-21 | 2020-12-21 | 2020-12-21 | 2020-12-21
ITB-2020-03-121 | Procurement of CY 2021 1st Semester Grocery Items for Home for the Elderly. | [19 empty] | HFE | YES | Competitive Bidding | 2020-12-28 | 2020-12-28 | 2020-12-29 | 2021-01-12 | 2021-01-12 | 2021-01-12 | [8 empty] | 1609425 | 1609425 |  | 1412718.56 | 1412718.56 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-12-21 | 2020-12-21 | 2020-12-21 | 2020-12-21
ITB-2020-03-122 | Procurement of CY 2021 1st Semester Frozen Goods for Home for the Elderly. | [19 empty] | HFE | YES | Competitive Bidding | 2020-12-28 | 2020-12-28 | 2020-12-29 | 2021-01-12 | 2021-01-12 | 2021-01-12 | [8 empty] | 1432750 | 1432750 |  | 1432750 | 1432750 |  | COA, TZU Chi Foundation and ZC Chamber of Commerce | 2020-12-21 | 2020-12-21 | 2020-12-21 | 2020-12-21
0
0
0
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 345410035.7
[21 empty] | Prepared by: | [10 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
[21 empty] | BAC Secretariat | [10 empty] | BAC Chairperson | [10 empty] | Head of the Procuring Entity