## app
Department of Social Welfare and Development (DSWD) Field Office IX, Updated Annual Procurement Plan for FY 2021 (Changes within 2nd Semester)
Code (PAP) | Procurement Project | PMO/ End-User | Is this an Early Procurement Activity? (Yes/No) | Mode of Procurement | Schedule for Each Procurement Activity |  |  |  | Source of Funds | Estimated Budget (PhP) |  |  | Remarks (brief description of Project) | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [8 empty] | Remarks (Explaining changes from the APP)
[5 empty] | Advertisement/Posting of IB/REI | Submission/Opening of Bids | Notice of Award | Contract Signing |  | Total | MOOE | CO |  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  | Pre-Proc Conf | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Delivery/ Accept
330100100001000 | Procurement for the Supply and Delivery of Canned Goods for Stockpiling of Food Items | DRMD | NO | Competitive Bidding | 2021-07-29 | 2021-08-17 | Sept. 20, 2021 | 2021-10-13 | GoP | 2986070 | 2986070
320101100001000 | Procurement for Formula Milk for Infant and Children 2nd Semester | RSCC | NO | Competitive Bidding | 2021-07-29 | 2021-08-17 | Sept. 20, 2021 | 2021-10-13 | GoP | 1739380 | 1739380
320101100001000 | Procurement of CY 2021 (2nd Semester) Grocery Items for RSCC | RSCC | NO | Competitive Bidding | 2021-08-05 | 2021-09-06 | 2021-10-18 | 2021-11-15 | GoP | 1344210 | 1344210
200000100001000 | Procurement of Various ICT Equipment for DSWD Field Office IX | ICTMU | NO | Competitive Bidding | 2021-08-05 | 2021-09-06 | 2021-10-18 | 2021-12-16 | GoP | 3031760 | 3031760
320101100001000 | 2nd Public Bidding: Procurement of CY 2021 (2nd Semester) Grocery Items for HE | HE | NO | Competitive Bidding | 2021-08-16 | 2021-09-06 | 2021-10-18 | 2021-11-15 | GoP | 1174655 | 1174655
320101100001000 | 2nd Public Bidding: Procurement of CY 2021 (2nd Semester) Frozen Goods for HE | HE | NO | Competitive Bidding | 2021-08-16 | 2021-09-06 | 2021-10-13 | 2021-10-31 | GoP | 1184140 | 1184140
320105100002000 | Procurement of 3rd Quarter Hygiene Kit and Janitorial Supplies for PCDP | PCDP | NO | Competitive Bidding | 2021-08-23 | 2021-09-13 | 2021-10-18 | 2021-12-22 | GoP | 900820 | 900820
320105100002000 | Procurement of 3rd Quarter Food Stuff for PCDP | PCDP | NO | Competitive Bidding | 2021-08-23 | 2021-09-13 | 2021-10-18 | 2021-11-15 | GoP | 1659340 | 1659340
320101100001000 | Procurement of Meat and Poultry Goods (2nd Semester) for RSCC | RSCC | NO | Competitive Bidding | 2021-08-26 | 2021-09-15 | 2021-10-18 | 2021-11-15 | GoP | 304590 | 304590
320101100001000 | Procurement of Frozen Goods (2nd Semester) for RSCC | RSCC | NO | Competitive Bidding | 2021-08-26 | 2021-09-15 | 2021-10-13 | 2021-10-31 | GoP | 375300 | 375300
330100100001000 | ITB 2021-10-090: Procurement of Raw Materials for Stockpiling of Food Items | DRMD | NO | Competitive Bidding | 2021-10-21 | 2021-11-10 | 2021-12-10 | DEC 24, 2021 | GoP | 9962290 | 9962290
320104200002000 | Negotiated procurement: Micro-Nutrients Powder Powder for CY 2021, BangUN Implimentation for BaSulTa | BangUN | NO | Competitive Bidding | 2021-10-05 | 2021-10-13 | 2021-10-18 | 2021-11-11 | GoP | 1400000 | 1400000
330100100001000 | Lease of Venue to Conduct Skills Enhancement for Regional Quick Response Team Members on Disaster Preparedness | DRMD | NO | Competitive Bidding | 2021-09-17 | 2021-09-20 | 2021-10-05 | 2021-10-07 | GoP | 1722700 | 1722700
320101100001000 | ITB 2021-08-037: Procurement of Fruits (2nd Semester) for RSCC | RSCC | NO | Competitive Bidding | 2021-08-26 | 2021-09-15 | 2021-10-18 | 2021-11-19 | GoP | 184300 | 184300 | [9 empty] | RSCC
320101100001000 | ITB 2021-08-038: Procurement of Vegetables (2nd Semester) for RSCC | RSCC | NO | Competitive Bidding | 2021-08-26 | 2021-09-15 | 2021-10-13 | 2021-10-31 | GoP | 255340 | 255340 | [9 empty] | RSCC
320101100001000 | ITB 2021-08-039: Procurement of Personal Effects and Janitorial Supplies (2nd Semester) for HE | HE | NO | Competitive Bidding | 2021-08-26 | 2021-09-15 | 2021-10-18 | 2021-12-29 | GoP | 1250890 | 1250890 | [9 empty] | HE
320102100001000 | ITB 2021-09-041: Procurement of Commercial Rice for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Zamboanga Del Norte (ZDN) District 1 | SFP | NO | Competitive Bidding | 2021-09-02 | 2021-09-22 | 2021-11-02 | 2021-11-18 | GoP | 1654820 | 1654820 | [9 empty] | SFP
320102100001000 | ITB 2021-09-042: Procurement of Grocery Items for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Zamboanga Del Norte (ZDN) District 1 | SFP | NO | Competitive Bidding | 2021-09-02 | 2021-09-22 | 2021-11-02 | 2021-11-18 | GoP | 1602951 | 1602951 | [9 empty] | SFP
320102100001000 | ITB 2021-09-043: Procurement of Whole Dressed Chicken for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Zamboanga Del Norte (ZDN) District 1 | SFP | NO | NP-53.1 Two Failed Biddings | 2021-09-02 | 2021-09-22 | 2021-11-02 | 2021-11-18 | GoP | 2943316.25 | 2943316.25 | [9 empty] | SFP
320102100001000 | ITB 2021-09-044: Procurement of Perishable Items for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Zamboanga Del Norte (ZDN) District 1 | SFP | NO | NP-53.1 Two Failed Biddings | 2021-09-02 | 2021-09-22 | 2021-11-02 | 2021-11-18 | GoP | 822344.24 | 822344.24 | [9 empty] | SFP
320102100001000 | ITB 2021-09-046: Procurement of Commercial Rice for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Zamboanga Del Norte (ZDN) District 2 | SFP | NO | Competitive Bidding | 2021-09-02 | 2021-09-22 | 2021-11-02 | 2021-11-18 | GoP | 3647200 | 3647200 | [9 empty] | SFP
320102100001000 | ITB 2021-09-047 :Procurement of Grocery Items for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Zamboanga Del Norte (ZDN) District 2 | SFP | NO | Competitive Bidding | 2021-09-02 | 2021-09-22 | 2021-11-02 | 2021-11-18 | GoP | 2890037 | 2890037 | [9 empty] | SFP
320102100001000 | ITB 2021-09-048: Procurement of Whole Dressed Chicken for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Zamboanga Del Norte (ZDN) District 2 | SFP | NO | Competitive Bidding | 2021-09-02 | 2021-09-22 | 2021-11-02 | 2021-11-18 | GoP | 6119074.8 | 6119074.8 | [9 empty] | SFP
320102100001000 | ITB 2021-09-049: Procurement of Perishable Items for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Zamboanga Del Norte (ZDN) District 2 | SFP | NO | Competitive Bidding | 2021-09-02 | 2021-09-22 | 2021-11-02 | 2021-11-18 | GoP | 4440033.75 | 4440033.75 | [9 empty] | SFP
320102100001000 | ITB 2021-09-051: Procurement of Commercial Rice for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Zamboanga Del Norte (ZDN) District 3 | SFP | NO | Competitive Bidding | 2021-09-02 | 2021-09-22 | 2021-11-02 | 2021-11-18 | GoP | 5512510 | 5512510 | [9 empty] | SFP
320102100001000 | ITB 2021-09-052: Procurement of Grocery Items for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Zamboanga Del Norte (ZDN) District 3 | SFP | NO | Competitive Bidding | 2021-09-02 | 2021-09-22 | 2021-11-02 | 2021-11-26 | GoP | 5195256 | 5195256 | [9 empty] | SFP
320102100001000 | ITB 2021-09-053: Procurement of Whole Dressed Chicken for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Zamboanga Del Norte (ZDN) District 3 | SFP | NO | Competitive Bidding | 2021-09-02 | 2021-09-22 | 2021-11-02 | 2021-11-18 | GoP | 9811036.2 | 9811036.2 | [9 empty] | SFP
320102100001000 | ITB 2021-09-054: Procurement of Perishable Items for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Zamboanga Del Norte (ZDN) District 3 | SFP | NO | Competitive Bidding | 2021-09-02 | 2021-09-22 | 2021-11-02 | 2021-12-10 | GoP | 2749016.25 | 2749016.25 | [9 empty] | SFP
320102100001000 | ITB 2021-09-056: Procurement of Commercial Rice for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Zamboanga Del Sur (ZDS) District 1 | SFP | NO | Competitive Bidding | 2021-09-02 | 2021-09-23 | 2021-11-02 | 2021-12-10 | GoP | 3795573 | 3795573 | [9 empty] | SFP
320102100001000 | ITB 2021-09-057: Procurement of Grocery Items for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Zamboanga Del Sur (ZDS) District 1 | SFP | NO | Competitive Bidding | 2021-09-02 | 2021-09-23 | 2021-11-02 | 2021-12-10 | GoP | 3141123.35 | 3141123.35 | [9 empty] | SFP
320102100001000 | ITB 2021-09-058: Procurement of Whole Dressed Chicken for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Zamboanga Del Sur (ZDS) District 1 | SFP | NO | Competitive Bidding | 2021-09-02 | 2021-09-23 | 2021-11-02 | 2021-12-10 | GoP | 6394248 | 6394248 | [9 empty] | SFP
320102100001000 | ITB 2021-09-059: Procurement of Perishable Items for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Zamboanga Del Sur (ZDS) District 1 | SFP | NO | Competitive Bidding | 2021-09-02 | 2021-09-23 | 2021-11-02 | 2021-12-10 | GoP | 1636442.7 | 1636442.7 | [9 empty] | SFP
320102100001000 | ITB 2021-09-061: Procurement of Commercial Rice for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Zamboanga Del Sur (ZDS) District 2 | SFP | NO | Competitive Bidding | 2021-09-02 | 2021-09-23 | 2021-11-02 | 2021-12-10 | GoP | 2700603 | 2700603 | [9 empty] | SFP
320102100001000 | ITB 2021-09-062: Procurement of Grocery Items for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Zamboanga Del Sur (ZDS) District 2 | SFP | NO | Competitive Bidding | 2021-09-02 | 2021-09-23 | 2021-11-02 | 2021-12-10 | GoP | 2235353.15 | 2235353.15 | [9 empty] | SFP
320102100001000 | ITB 2021-09-063: Procurement of Whole Dressed Chicken for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Zamboanga Del Sur (ZDS) District 2 | SFP | NO | Competitive Bidding | 2021-09-02 | 2021-09-23 | 2021-11-02 | 2021-12-10 | GoP | 4549608 | 4549608 | [9 empty] | SFP
320102100001000 | ITB 2021-09-064: Procurement of Perishable Items for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Zamboanga Del Sur (ZDS) District 2 | SFP | NO | Competitive Bidding | 2021-09-02 | 2021-09-23 | 2021-11-02 | 2021-12-10 | GoP | 1165693.5 | 1165693.5 | [9 empty] | SFP
320102100001000 | ITB 2021-09-066: Procurement of Commercial Rice for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Zamboanga Sibugay Province (ZSP) District 1 | SFP | NO | Competitive Bidding | 2021-09-02 | 2021-09-24 | 2021-11-02 | 2021-12-10 | GoP | 4039080 | 4039080 | [9 empty] | SFP
320102100001000 | ITB 2021-09-068: Procurement of Whole Dressed Chicken for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Zamboanga Sibugay Province (ZSP) District 1 | SFP | NO | Competitive Bidding | 2021-09-02 | 2021-09-24 | 2021-11-02 | 2021-12-10 | GoP | 6716650.5 | 6716650.5 | [9 empty] | SFP
320102100001000 | ITB 2021-09-069: Procurement of Perishable Items for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Zamboanga Sibugay Province (ZSP) District 1 | SFP | NO | Competitive Bidding | 2021-09-02 | 2021-09-24 | 2021-11-02 | 2021-11-18 | GoP | 2011760.36 | 2011760.36 | [9 empty] | SFP
320102100001000 | ITB 2021-09-070: Procurement of Nutri Bun for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Zamboanga Sibugay Province (ZSP) District 2 | SFP | NO | Competitive Bidding | 2021-09-02 | 2021-09-24 | 2021-11-02 | On-Going | GoP | 1379970 | 1379970 | [9 empty] | SFP
320102100001000 | ITB 2021-09-071: Procurement of Commercial Rice for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Zamboanga Sibugay Province (ZSP) District 2 | SFP | NO | Competitive Bidding | 2021-09-02 | 2021-09-24 | 2021-11-02 | DEC 09, 2021 | GoP | 6185127 | 6185127 | [9 empty] | SFP
320102100001000 | ITB 2021-09-072: Procurement of Grocery Items for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Zamboanga Sibugay Province (ZSP) District 2 | SFP | NO | Competitive Bidding | 2021-09-02 | 2021-09-24 | 2021-11-02 | DEC 09, 2021 | GoP | 4829304.35 | 4829304.35 | [9 empty] | SFP
320102100001000 | ITB 2021-09-073: Procurement of Whole Dressed Chicken for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Zamboanga Sibugay Province (ZSP) District 2 | SFP | NO | Competitive Bidding | 2021-09-02 | 2021-09-24 | 2021-11-02 | 2021-11-22 | GoP | 9143542.32 | 9143542.32 | [9 empty] | SFP
320102100001000 | ITB 2021-09-074: Procurement of Perishable Items for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Zamboanga Sibugay Province (ZSP) District 2 | SFP | NO | Competitive Bidding | 2021-09-02 | 2021-09-24 | 2021-11-02 | 2021-12-09 | GoP | 2704956 | 2704956 | [9 empty] | SFP
320102100001000 | ITB 2021-09-075: Procurement of Commercial Rice for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Isabela City | SFP | NO | Competitive Bidding | 2021-09-02 | 2021-09-24 | 2021-11-02 | 2021-11-26 | GoP | 805100 | 805100 | [9 empty] | SFP
320102100001000 | ITB 2021-09-076: Procurement of Grocery Items for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Isabela City | SFP | NO | Competitive Bidding | 2021-09-02 | 2021-09-24 | 2021-11-02 | 2021-11-18 | GoP | 665360 | 665360 | [9 empty] | SFP
320102100001000 | ITB 2021-09-077: Procurement of Whole Dressed Chicken for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Isabela City | SFP | NO | Competitive Bidding | 2021-09-02 | 2021-09-24 | 2021-11-02 | 2021-11-18 | GoP | 1710712.5 | 1710712.5 | [9 empty] | SFP
320102100001000 | ITB 2021-09-078: Procurement of Perishable Items for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Isabela City | SFP | NO | Competitive Bidding | 2021-09-02 | 2021-09-24 | 2021-11-02 | 2021-11-18 | GoP | 1276590 | 1276590 | [9 empty] | SFP
330100100001000 | ITB 2021-09-079: 2nd Public Bidding Procurement of Instant Coffee and Cereal Drinks for Stockpiling of Food Items | DRMD | NO | Competitive Bidding | 2021-09-21 | 2021-10-11 | 2021-11-22 | 2021-12-21 | GoP | 1530595.5 | 1530595.5 | [9 empty] | DRMD
310100100001000 | ITB 2021-09-080: 2nd Public Bidding Procurement of Medical Supplies for Pantawid Staff | 4Ps | NO | Competitive Bidding | 2021-09-21 | 2021-10-11 | 2021-11-18 | 2021-12-29 | GoP | 850236 | 850236 | [9 empty] | 4Ps
310100100001000 | NP-2021-11-003: Negotiated Procurement of Nutri Bun for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Zamboanga Del Norte (ZDN) District 1 | SFP | NO | NP-53.1 Two Failed Biddings | 2021-11-04 | 2021-11-11 | 2021-11-16 | DEC 10, 2021 | GoP | 390960 | 390960 | [9 empty] | SFP
310100100001000 | NP-2021-11-004: Negotiated Procurement of Nutri Bun for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Zamboanga Del Norte (ZDN) District 2 | SFP | NO | NP-53.1 Two Failed Biddings | 2021-11-04 | 2021-11-11 | 2021-11-16 | DEC 10, 2021 | GoP | 946260 | 946260 | [9 empty] | SFP
310100100001000 | NP-2021-11-005: Negotiated Procurement of Nutri Bun for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Zamboanga Del Norte (ZDN) District 3 | SFP | NO | NP-53.1 Two Failed Biddings | 2021-11-04 | 2021-11-11 | 2021-11-16 | DEC 10, 2021 | GoP | 1302390 | 1302390 | [9 empty] | SFP
310100100001000 | NP-2021-11-006: Negotiated Procurement of Nutri Bun for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Zamboanga Del Sur (ZDS) District 1 | SFP | NO | NP-53.1 Two Failed Biddings | 2021-11-04 | 2021-11-11 | 2021-11-16 | DEC 10, 2021 | GoP | 897570 | 897570 | [9 empty] | SFP
310100100001000 | NP-2021-11-007: Negotiated Procurement Nutri Bun for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Zamboanga Del Sur (ZDS) District 2 | SFP | NO | NP-53.1 Two Failed Biddings | 2021-11-04 | 2021-11-11 | 2021-11-16 | DEC 10, 2021 | GoP | 596148 | 596148 | [9 empty] | SFP
310100100001000 | NP-2021-11-008: Negotiated Procurement of Nutri Bun for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Zamboanga Sibugay (ZSP) District 1 | SFP | NO | NP-53.1 Two Failed Biddings | 2021-11-04 | 2021-11-11 | 2021-11-16 | DEC 10, 2021 | GoP | 890625 | 890625 | [9 empty] | SFP
310100100001000 | ITB 2021-10-088: 2nd Public Bidding: Procurement of Grocery Items for Supplementary Feeding Program (SFP) 11th Cycle Implementation in Zamboanga Sibugay Province (ZSP) District 1 | SFP | NO | Competitive Bidding | 2021-10-14 | 2021-11-03 | 2021-12-10 | DEC 23, 2021 | GoP | 3692714.8 | 3692714.8 | [9 empty] | SFP
320101100001000 | ITB 2021-10-089: Procurement of Personal Effects and Common Janitorial Supplies for RSCC | RSCC | NO | Competitive Bidding | 2021-10-21 | 2021-11-10 | 2021-12-10 | On-Going | GoP | 974780 | 974780 | [9 empty] | RSCC
320101100001000 | ITB 2021-10-091: Procurement of Clothing and Personal Effects for RRCY | RRCY | NO | Competitive Bidding | 2021-10-21 | 2021-11-10 | 2021-12-20 | On-Going | GoP | 427625 | 427625 | [9 empty] | RRCY
320101100001000 | ITB 2021-10-092: Procurement of Janitorial Supplies for RRCY | RRCY | NO | Competitive Bidding | 2021-10-21 | 2021-11-10 | 2021-12-10 | On-Going | GoP | 453182.5 | 453182.5 | [9 empty] | RRCY
320101100001000 | ITB 2021-10-093: Procurement of Various Meats for RRCY | RRCY | NO | Competitive Bidding | 2021-10-21 | 2021-11-10 | 2021-12-10 | On-Going | GoP | 1956790 | 1956790 | [9 empty] | RRCY
320104100001000 | ITB 2021-11-096: "Procurement of Commercial Rice for Production of Family Food Packs for CIU Clients" | CIU | NO | Competitive Bidding | 2021-11-24 | 2021-12-14 | 2021-12-29 | On-Going | GoP | 1980000 | 1980000 | [9 empty] | CIU
310100100002000 | Purchase of Office Supplies for the use of Sustainable Livelihood Program | SLP | NO | NP-53.5 Agency-to-Agency | 2021-07-01 | 2021-07-01 | 2021-07-01 | 2021-07-01 | GoP | 196390 | 196390
310100100002000 | Purchase for the Repair of Desktop Computers at SLP | SLP | NO | Shopping | 2021-07-01 | 2021-07-01 | 2021-07-01 | 2021-07-01 | GoP | 413600 | 413600
310100100002000 | Purchase of Rent of Vehicles (VAN Rental) | SLP | NO | NP-53.9 - Small Value Procurement | 2021-07-01 | 2021-07-01 | 2021-07-01 | 2021-07-01 | GoP | 240000 | 240000
310100100002000 | Purchase of E-load for Communication Allowance & Data Services | SLP | NO | Direct Contracting | July & Oct. 2021 | July & Oct. 2021 | July & Oct. 2021 | July & Oct. 2021 | GoP | 390600 | 390600
310100100002000 | Purchase of Caterings Services during Meetings of SLP | SLP | NO | NP-53.9 - Small Value Procurement | July toDec. 2021 | July toDec. 2021 | July toDec. 2021 | July toDec. 2021 | GoP | 220500 | 220500
310100100002000 | Lease of Venue for Staff Development and RPMT Meeting | SLP | NO | NP-53.8 Defense Cooperation Agreement | Aug. & Nov. 2021 | Aug. & Nov. 2021 | Aug. & Nov. 2021 | Aug. & Nov. 2021 | GoP | 116000 | 116000
310100100002000 | Lease of Venue for Hotel Accomodation during trainings | SLP | NO | NP-53.8 Defense Cooperation Agreement | 2021-10-01 | 2021-10-01 | 2021-10-01 | 2021-10-01 | GoP | 638400 | 638400
310100100002000 | Purchase of Prizes and tokens (Grocery items/packages) | SLP | NO | Shopping | 2021-07-01 | 2021-07-01 | 2021-07-01 | 2021-07-01 | GoP | 30000 | 30000
310100100002000 | Purchase of Customize Plaques of Recognition | SLP | NO | NP-53.9 - Small Value Procurement | 2021-07-01 | 2021-07-01 | 2021-07-01 | 2021-07-01 | GoP | 22500 | 22500
310100100002000 | Purchase of Advocacy kits/pouch holder/bag (cloth) | SLP | NO | Shopping | 2021-07-01 | 2021-07-01 | 2021-07-01 | 2021-07-01 | GoP | 33600 | 33600
310100100002000 | Purchase of Advocacy kits/pouch holder/ Bag | SLP | NO | Shopping | 2021-07-01 | 2021-07-01 | 2021-07-01 | 2021-07-01 | GoP | 37500 | 37500
310100100002000 | SLP Provincial Mid-Year Program Review cum IPC Checkpoint Workshop (Liloy) | SLP | NO | NP-53.8 Defense Cooperation Agreement | 2021-08-01 | 2021-08-01 | 2021-08-01 | 2021-08-01 | GoP | 130200 | 130200
310100100002000 | SLP Provincial Mid-Year Program Review cum IPC Checkpoint Workshop (Pagadian city) | SLP | NO | NP-53.8 Defense Cooperation Agreement | 2021-09-01 | 2021-09-01 | 2021-09-01 | 2021-09-01 | GoP | 108500 | 108500
310100100002000 | SLP Provincial Mid-Year Program Review cum IPC Checkpoint Workshop (Zamboanga city) | SLP | NO | NP-53.8 Defense Cooperation Agreement | 2021-09-01 | 2021-09-01 | 2021-09-01 | 2021-09-01 | GoP | 172800 | 172800
310100100002000 | Purchase of Office for the SLP Staff at Dipolog City (LONG BOND PAPER S-20 up to Oblong - Shaped: 4 seater glass table ) | SLP | NO | Shopping | 2021-09-01 | 2021-09-01 | 2021-09-01 | 2021-09-01 | GoP | 162620.01 | 162620.01
310100100002000 | Purchase of Raincoat, Facemask, ethyl ALCOHOL, Ruber shoe cover, Air purfier and vitamin C | SLP | NO | Shopping | 2021-09-01 | 2021-09-01 | 2021-09-01 | 2021-09-01 | GoP | 72720 | 72720
310100100002000 | Purchase of Office Suppies and Medical Supplies for SLP Ipil (Disposable Face Mask 3 ply, up to Office table w/ top glass) | SLP | NO | Shopping | 2021-09-01 | 2021-09-01 | 2021-09-01 | 2021-09-01 | GoP | 148960 | 148960
310100100002000 | Alcohol 3.6 liter , Face Masks, 50 pcs/box, 3 ply, Vitamin C with Zinc, Face Shield, Personal Protective Equipment and | SLP | NO | Shopping | 2021-09-01 | 2021-09-01 | 2021-09-01 | 2021-09-01 | GoP | 72710 | 72710
310100100002000 | Purchase of 3 in 1 Printer for SLP Ipil | SLP | NO | Shopping | 2021-09-01 | 2021-09-01 | 2021-09-01 | 2021-09-01 | GoP | 160000 | 160000
320101100001000 | ACRYLIC ROOM SIGNAGE, ACRYLIC TABLE NAME PLATE (11"x14") and Acrylic Suggestion Box (8"X8") for home for women | Home for Women | NO | NP-53.9 - Small Value Procurement | 2021-09-01 | 2021-09-01 | 2021-09-01 | 2021-09-01 | GoP | 37750 | 37750
320101100001000 | Purchase of Office Supplies for the use of Home for women | Home for Women | NO | Shopping | 2022-11-01 | 2022-11-01 | 2022-11-01 | 2022-11-01 | GoP | 276845 | 276845
320101100001000 | L1375 x W780 x H875 mm High Density Polyethylene Trash Bin with a capacity of 660 Liters, 263kg and 4 Wheels with brake (Wheel size: 200mm∅) | Home for Women | NO | Shopping | 2021-09-01 | 2021-09-01 | 2021-09-01 | 2021-09-01 | GoP | 29998 | 29998
320101100001000 | 72cm x 72cm 32cm Industrialized Metallic Exhaust Fan with an airflow capacity of 145m2 /min., single phase 230V, 60Hz and a revolution of 1600 RPM with a power of 600W with built-in thermal cut-off relay and it has a weight of 15kg. To be connected to the existing power line. | Home for Women | NO | Shopping | 2021-09-01 | 2021-09-01 | 2021-09-01 | 2021-09-01 | GoP | 14999 | 14999
320101100001000 | Industrialized Wall Fan with 16 inches 3 wing metal blade, 3 speed control system, oscillation control adjustable fan head and with Thermal fuse protected motor.To be connected to the existing power line. | Home for Women | NO | Shopping | 2021-09-01 | 2021-09-01 | 2021-09-01 | 2021-09-01 | GoP | 54834.48 | 54834.48
320101100001000 | 12” Ceiling mounted exhaust fan, Size: 300mm (12"), Case size: 32.3 x 16.9 x 32 (cm), Voltage: 230v, Frequency: 60 Hz, Net weight: 3 kg, Climate: Class T, Consumption: 38 watts with an Anti-vibration mounting, thermal fuse, shock resistant, self-lubricating motor, reduced noise, enhanced air volume capacity, corrosion resistant, Installation Dimension: 30cmx30cm.To be connected to the existing power line. | Home for Women | NO | Shopping | 2021-09-01 | 2021-09-01 | 2021-09-01 | 2021-09-01 | GoP | 38566.65 | 38566.65
320101100001000 | 220V 12” Fire Alarm bell with 24V DC 30mA Manual press alarm bell, Operating Contact: Max. 30V DC 500mA, fire Proof Plastic immediately output fire alarm signal. Indicator above fire alarm push-button is to conform the alarm signal transfer. There are phone jack and reset button behind the cover cap. To be connected to the existing power line. | Home for Women | NO | Shopping | 2021-09-01 | 2021-09-01 | 2021-09-01 | 2021-09-01 | GoP | 10913.56 | 10913.56
320101100001000 | Night lights made with Iron and Acrylic High temperature baking varnish or plastic absorbing lampshade, with a Power of AC110 – 240V, Eco-friendly, no UV light, no radiation, no flicker, it can protect eyesight, Energy saving and use for a long time, up to 50000 hours 24w, Light color Pure white or Warm White for your choice and Ultra-thin round housing Color refer to the end user. | Home for Women | NO | Shopping | 2021-09-01 | 2021-09-01 | 2021-09-01 | 2021-09-01 | GoP | 9124.71 | 9124.71
320101100001000 | Purchase of Seismic restraint brackets for cabinets | Home for Women | NO | Shopping | N/A | N/A | 2021-09-01 | 2021-09-01 | GoP | 28888.2 | 28888.2
320101100001000 | Purchase of 195 r-15 Tire (For Ambulance) and 185 r-14 Tire (For Revo) for HFW | Home for Women | NO | Shopping | 2021-09-01 | 2021-09-01 | 2021-09-01 | 2021-09-01 | GoP | 54450 | 54450
320101100001000 | Purchase of Vehicel Parts and Accessories for Maintenance of Vehicle at HFW | Home for Women | NO | Shopping | 2021-09-01 | 2021-09-01 | 2021-09-01 | 2021-09-01 | GoP | 175180 | 175180
320101100001000 | Purchase of Common Janitorial Supplies for HFW-2nd sem of 2021 | Home for Women | NO | Shopping | 2022-11-01 | 2022-11-01 | 2022-11-01 | 2022-11-01 | GoP | 492085 | 492085
320101100001000 | Purchase of Water Drum with cover ( 105L) ,Storage Box (150L), Utility Pail with cover (12L), Stainless Steel Basin (70cm) | Home for Women | NO | Shopping | 2022-11-01 | 2022-11-01 | 2022-11-01 | 2022-11-01 | GoP | 30000 | 30000
320101100001000 | Purchase of BROTHER L2540DW Toner | Home for Women | NO | Shopping | 2022-11-01 | 2022-11-01 | 2022-11-01 | 2022-11-01 | GoP | 17750 | 17750
320101100001000 | Purchase of AIR HUMIDIFIER | Home for Women | NO | Shopping | 2022-11-01 | 2022-11-01 | 2022-11-01 | 2022-11-01 | GoP | 39600 | 39600
320101100001000 | Purchase of AIR PURIFIER | Home for Women | NO | Shopping | 2022-11-01 | 2022-11-01 | 2022-11-01 | 2022-11-01 | GoP | 31500 | 31500
320101100001000 | Purchase of Heavy Duty Vacuum Cleaner (Specification: 3 in 1 Vacuum cleaner, 20 Liter, Adjustable telescoping wand, with extra accessories.) | Home for Women | NO | Shopping | 2022-11-01 | 2022-11-01 | 2022-11-01 | 2022-11-01 | GoP | 22500 | 22500
320101100001000 | Purchase of Spinner Mop (Specification: 360 degree spin mop head, 2 in 1 nucket wash and wring, Stainless steel wringer bucket with adjustable mop pole to 85-128 cm,with extra mop head) | Home for Women | NO | Shopping | 2022-11-01 | 2022-11-01 | 2022-11-01 | 2022-11-01 | GoP | 3425 | 3425
320101100001000 | Purchase of Smoke Detector | Home for Women | NO | Shopping | 2022-11-01 | 2022-11-01 | 2022-11-01 | 2022-11-01 | GoP | 15000 | 15000
320101100001000 | Purchase of COMMON ICT EQUIPMENTS AND SUPPLIES for HFW (COMMON ICT EQUIPMENT up to Keyboard: USB standard (wireless) | Home for Women | NO | Shopping | 2022-11-01 | 2022-11-01 | 2022-11-01 | 2022-11-01 | GoP | 317490 | 317490
320101100001000 | Purchase of Food Supplies (Groceries) for the consumption of HFW Clients | Home for Women | NO | Shopping | 2021-06-01 | 2021-06-01 | 2021-07-01 | 2021-07-01 | GoP | 893880 | 893880
320101100001000 | Purchase of Food Supplies (Frozen Goods) for the consumption of HFW Clients | Home for Women | NO | Shopping | 2021-06-01 | 2021-06-01 | 2021-07-01 | 2021-07-01 | GoP | 725540 | 725540
320101100001000 | Purchase of Food Supplies (VEGETABLES ) for the consumption of HFW Clients | Home for Women | NO | Shopping | 2021-06-01 | 2021-06-01 | 2021-07-01 | 2021-07-01 | GoP | 440445 | 440445
320101100001000 | Purchase of Beef, Chicken, Fish for the Consumption of HFW | Home for Women | NO | Shopping | 2022-11-01 | 2022-11-01 | 2022-11-01 | 2022-11-01 | GoP | 332380 | 332380
320101100001000 | Purchase of Additional Food Supplies (VEGETABLES ) for the consumption of HFW Clients-last quarter of 2021 | Home for Women | NO | Shopping | Dec. 2021 | Dec. 2021 | Dec. 2021 | Dec. 2021 | GoP | 56250 | 56250
320101100001000 | Purchase of Food Supplies (FRUITS ) for the consumption of HFW Clients | Home for Women | NO | Shopping | Dec. 2021 | Dec. 2021 | Dec. 2021 | Dec. 2021 | GoP | 194490 | 194490
320101100001000 | Purchase of KITCHEN UTENSILS for Home for Women | Home for Women | NO | Shopping | 2022-08-01 | 2022-08-01 | 2022-08-01 | 2022-08-01 | GoP | 72750 | 72750
320101100001000 | Purchase of PERSONAL EFFECT (FOR CLIENTS) at HOME FOR WOMEN | Home for Women | NO | Shopping | 2021-06-01 | 2021-06-01 | 2021-07-01 | 2021-07-01 | GoP | 74600 | 74600
320101100001000 | Purchase of Service PHYSICAL THERAPIST (P500.00 / session (3 session per week) for 2 clients for 52 weeks) | Home for Women | NO | NP-53.9 - Small Value Procurement | 2021-06-01 | 2021-06-01 | 2021-07-01 | 2021-07-01 | GoP | 156000 | 156000
320101100001000 | Purchase of Service OCCUPATIONAL THERAPIST (P500.00 / session for 9 clients for 52 weeks) | Home for Women | NO | NP-53.9 - Small Value Procurement | 2021-06-01 | 2021-06-01 | 2021-07-01 | 2021-07-01 | GoP | 234000 | 234000
320101100001000 | PURCHASE OF SERVICES FOR 4 HOUSEPARENTS x Php 579.56/days for 30 days | Home for Women | NO | NP-53.9 - Small Value Procurement | 2022-08-01 | 2022-08-01 | 2022-08-01 | 2022-08-01 | GoP | 466444.8 | 466444.8
320101100001000 | PURCHASE OF SERVICE OF TWO (2) COOK x Php 546.60 per day for 30 days | Home for Women | NO | NP-53.9 - Small Value Procurement | 2022-08-01 | 2022-08-01 | 2022-08-01 | 2022-08-01 | GoP | 203536.8 | 203536.8
320101100001000 | PURCHASE OF SERVICE OF ONE (1) LAUNDRESS X PHP 486.00 per day for 30 days | Home for Women | NO | NP-53.9 - Small Value Procurement | 2021-08-01 | 2021-08-01 | 2021-08-01 | 2021-08-01 | GoP | 90483.8 | 90483.8
320101100001000 | Purchase of Catering Services for the conduct of 18 days to end Vaw Campaign | Home for Women | NO | NP-53.9 - Small Value Procurement | 2021-11-01 | 2021-11-01 | 2021-11-01 | 2021-11-01 | GoP | 57000 | 57000
320101100001000 | Purchase of Catering Services for the conduct of Nutrition month Celebration | Home for Women | NO | NP-53.9 - Small Value Procurement | 2021-06-01 | 2021-06-01 | 2021-06-01 | 2021-06-01 | GoP | 70000 | 70000
320101100001000 | Purchase of Catering Services for the conduct of Care for the Carers | Home for Women | NO | NP-53.9 - Small Value Procurement | 2021-11-01 | 2021-11-01 | 2021-11-01 | 2021-11-01 | GoP | 186000 | 186000
320101100001000 | Purchase of Catering Services for the conduct of Mental health awareness montth celebration | Home for Women | NO | NP-53.9 - Small Value Procurement | 2021-10-01 | 2021-10-01 | 2021-10-01 | 2021-10-01 | GoP | 117800 | 117800
320101100001000 | Purchase of Catering Services for the conduct of Year-end Center Review | Home for Women | NO | NP-53.9 - Small Value Procurement | 2021-12-01 | 2021-12-01 | 2021-12-01 | 2021-12-01 | GoP | 104000 | 104000
320101100001000 | Purchase of Communication Allowance for Staff of HFW | Home for Women | NO | Direct Contracting | N/A | N/A | 2022-11-01 | 2022-11-01 | GoP | 39600 | 39600
320101100001000 | Purchase of Hand Tools for the use of Home for Women Clienys (Heavy duty Tool Box up to Claw Hammer) | Home for Women | NO | NP-53.9 - Small Value Procurement | 2021-07-01 | 2021-07-01 | 2021-07-01 | 2021-07-01 | GoP | 50460 | 50460
320101100001000 | Purchase of Lavatory Stainless Faucet, Heavy duty door knob Lever Type, Double Action Stainless Hinges, Sliding Door Lockset w/ key and Gooseneck Stainless Faucet | Home for Women | NO | Shopping | N/A | N/A | 2022-12-01 | 2022-12-01 | GoP | 27000 | 27000
320101100001000 | Cost and Labor (40,000km Check up) for Ambulance | Home for Women | NO | Direct Contracting | 2021-07-01 | 2021-07-01 | 2021-07-01 | 2021-07-01 | GoP | 50000 | 50000
320101100001000 | LABOR AND MATERIALS > Road Graveling Materials specifically G2 gravel > Deliveries, scattering and compaction | Home for Women | NO | NP-53.9 - Small Value Procurement | 2021-07-01 | 2021-07-01 | 2021-07-01 | 2021-07-01 | GoP | 375000 | 375000
320101100001000 | Purchase of ASSORTED EDUCATIONAL BOOK for clients at HFW | Home for Women | NO | Shopping | 2021-07-01 | 2021-07-01 | 2021-07-01 | 2021-07-01 | GoP | 33200 | 33200
320101100001000 | Folding Table and Chairs (4 chair, 1 table per set) Height: 0.6-0.7 Meters | Home for Women | NO | Shopping | 2021-09-01 | 2021-09-01 | 2021-09-01 | 2021-09-01 | GoP | 14925 | 14925
320101100001000 | Purchase of Diapers for Clients-HFE use | Home for Women | NO | Shopping | 2021-06-01 | 2021-07-01 | 2021-07-01 | 2021-07-01 | GoP | 45600 | 45600
320101100001000 | Purchase of Customized Acrylic Paper Weights, Gang Chair, Outdoor Tent (good for 8-10 person) | Home for Women | NO | Shopping | 2021-11-01 | 2021-11-01 | 2021-11-01 | 2021-11-01 | GoP | 108845 | 108845
320101100001000 | Purchase of Kawa, Serving Spoon, Serving Fork and Stainless Baking Table | Home for Women | NO | Shopping | 2021-12-01 | 2021-12-01 | 2021-12-01 | 2021-12-01 | GoP | 18200 | 18200
320101100001000 | Purchase of Stainless Baking Table | Home for Women | NO | Shopping | 2021-12-01 | 2021-12-01 | 2021-12-01 | 2021-12-01 | GoP | 14300 | 14300
320101100001000 | Teflon, Electric Tape, Plason, Stainless Steel Pressurized Tank (42 gallons) | Home for Women | NO | Shopping | 2021-12-01 | 2021-12-01 | 2021-12-01 | 2021-12-01 | GoP | 77500 | 77500
320101100001000 | Garden Rake, Garden Hose (150 meters), 3.5MM Squared THHN wire and 2.0MM Squared THHN wire | Home for Women | NO | Shopping | 2021-12-01 | 2021-12-01 | 2021-12-01 | 2021-12-01 | GoP | 17760 | 17760
320101100001000 | Ring Binding Machine (Legal size) & Paper cutter (big) | Home for Women | NO | Shopping | 2021-11-01 | 2021-11-01 | 2021-11-01 | 2021-11-01 | GoP | 12850 | 12850
320101100001000 | Purchase of REFRIGIRATOR 6CU. FT. and ALCOHOL STAND WITH PEDAL | Home for Women | NO | Shopping | 2021-12-01 | 2021-12-01 | 2021-12-01 | 2021-12-01 | GoP | 29880 | 29880
320101100001000 | 100 POSITION IN-WALL KEY METAL CABINET (Labeles Key shelves / 0.8mm Steel Walls / hold 100 keys in five rows / colored key tabs with white space for labeling/ two sided index chart to record keyes position / key-operated lock with two keys / sturdy 0.8mm steel construction / flange for neat in-wall installation) | Home for Women | NO | Shopping | 2021-11-01 | 2021-11-01 | 2021-11-01 | 2021-11-01 | GoP | 29000 | 29000
320101100001000 | FLOWER POT STAND (For indoor and outdoor metal rust proof iron round stand (50cm x 20cm) color: black | Home for Women | NO | Shopping | 2021-11-01 | 2021-11-01 | 2021-11-01 | 2021-11-01 | GoP | 14500 | 14500
320101100001000 | FLOWER POT STAND (For indoor and outdoor metal rust proof iron round stand (30cm x 10cm) | Home for Women | NO | Shopping | 2021-11-01 | 2021-11-01 | 2021-11-01 | 2021-11-01 | GoP | 14500 | 14500
320101100001000 | TUBULAR METAL FLOWER POT STAND (3 Tier step Stand Black (HxLxW) 3"x4'x3') / Height: 3 feet (1ft. per layer) Length: 4 feet / Width of every layer is 1 feet / 1"x1" Tubular Bar Main Frame and support; 1/4" thick flat bar for the base / Powder coated, Rust Preventive Paint, Smooth Finish, Color Black, Welded) | Home for Women | NO | Shopping | 2021-11-01 | 2021-11-01 | 2021-11-01 | 2021-11-01 | GoP | 120000 | 120000
320101100001000 | Purchase of 1500W RELAY TYPE AVR, 3000W AUTOMATIC VOLTAGE REGULATOR, MINI LAUNDRY BASKET WITH COVER, TALKING DIGITAL BP APPARATUS, HAND HELD PULSE OXIMETER | Home for Women | NO | Shopping | 2021-12-01 | 2021-12-01 | 2021-12-01 | 2021-12-01 | GoP | 340218 | 340218
320101100001000 | Customized Jacket for Care for Carers | Home for Women | NO | NP-53.9 - Small Value Procurement | 2021-12-01 | 2021-12-01 | 2021-12-01 | 2021-12-01 | GoP | 32000 | 32000
320101100001000 | Customized Planner for Year End Review | Home for Women | NO | NP-53.9 - Small Value Procurement | 2021-12-01 | 2021-12-01 | 2021-12-01 | 2021-12-01 | GoP | 72000 | 72000
320101100001000 | Customized Disaster Bag | Home for Women | NO | NP-53.9 - Small Value Procurement | 2022-11-01 | 2022-11-01 | 2022-11-01 | 2022-11-01 | GoP | 30000 | 30000
320101100001000 | Grass Cutter GX35 4 Stroke (• 35.8cc, • Rated Power, • 1.3hp (1.2kw), • Bore & Stroke, • 39*30mm, • Shaft Rotation,• Counterclockwise, Fuel Type, Unleaded 86 octane or higher, Fuel Capacity, 650ml, Oil Type, 10~40W Engine Oil 4T, Oil Capacity, 100ml, inclusion 1x Engine (GX35), 1x Handle Bar & Stick Set, 1x Metal Blade 2 Teeth, 1x Nylon/Tansi Cutter, 1x Shoulder Strap, 1x Mud Guard,1x Tools Set) | Home for Women | NO | Shopping | 2021-11-01 | 2022-11-01 | 2022-11-01 | 2022-11-01 | GoP | 14900 | 14900
320101100001000 | Purchase of 20” Chainsaw Gasoline Operated | Home for Women | NO | Shopping | 2021-12-01 | 2021-12-01 | 2021-12-01 | 2021-12-01 | GoP | 7995 | 7995
320101100001000 | STAINLESS ALCOHOL FOOT PEDAL DISPENSER (No hand contact, just step to dispense alcohol Adjustable to most alcohol pump containers 3 feet, 5 inches in height Comes with a strap so the alcohol container stays in place No battery needed, that means low to zero maintenance. Default color is metal gray) | Home for Women | NO | Shopping | 2021-11-01 | 2021-11-01 | 2021-11-01 | 2021-11-01 | GoP | 15000 | 15000
320101100001000 | Purchase of SMOKE DETECTOR FIRE ALARM, | Home for Women | NO | Shopping | 2021-11-01 | 2021-11-01 | 2021-11-01 | 2021-11-01 | GoP | 15000 | 15000
320101100001000 | PURCHASE OF SERVICES FOR BLOOD CHEMISTRY | Home for Women | NO | Shopping | 2021-11-01 | 2021-11-01 | 2021-12-01 | 2021-12-01 | GoP | 72100 | 72100
320101100001000 | Wooden Cabinet with compartment (for hanging clothes, lockable, atleast 6ft, floor mount) | Home for Women | NO | Shopping | 2021-11-01 | 2021-11-01 | 2021-12-01 | 2021-12-01 | GoP | 49995 | 49995
320101100001000 | CHAIR, monobloc, beige, with backrest, w/o armrest, good quality | Home for Women | NO | Shopping | 2021-11-01 | 2021-11-01 | 2021-12-01 | 2021-12-01 | GoP | 59000 | 59000
320101100001000 | Purchase of Grocery Items for the consumption og Home for Women | Home for Women | NO | Shopping | 2021-11-01 | 2021-11-01 | 2021-12-01 | 2021-12-01 | GoP | 302830 | 302830
320101100001000 | OFFICE RENTAL OF PANTAWID STAFF IN SINDANGAN, ZAMBOANGA DEL NORTE FROM JULY-DECEMBER 2021 | Home for Women | NO | NP-53.10 Lease of Real Property and Venue | 2021-07-02 | 2021-07-12 | 2021-07-13 | 2021-07-13 | GoP | 90000 | 90000
320101100001000 | TO BE USE IN THE 3RD FLOOR PANTAWID SECTION | Pantawid Pamilya program | NO | Shopping | 2021-07-06 | 2021-07-12 | 2021-07-13 | 2021-07-13 | GoP | 568145 | 568145
310100100001000 | PROCUREMENT OF ADVOCACY BAG TO BE USED FOR HANDLING AND KEEPING OF KILOS-UNILAD FORMS | Pantawid Pamilya program | NO | NP-53.9 - Small Value Procurement | 2021-07-26 | 2021-08-02 | 2021-08-03 | 2021-08-03 | GoP | 715000 | 715000
310100100001000 | TO BE DISTRIBUTED AS PART OF THE BATA, BALIK ESKWELA (BBE) CAMPAIGN | Pantawid Pamilya program | NO | NP-53.9 - Small Value Procurement | 2021-08-10 | 2021-08-16 | 2021-08-17 | 2021-08-01 | GoP | 209500 | 209500
310100100001000 | TO BE USE FOR SWDI ADMINISTRATION | Pantawid Pamilya program | NO | NP-53.9 - Small Value Procurement | 2021-08-26 | 2021-08-31 | 2021-09-01 | 2021-09-01 | GoP | 525000 | 525000
310100100001000 | PROCUREMNET OF OTHER RELATED TRAINING SUPPLIES MATERIALS & EQUIPMENT | Pantawid Pamilya program | NO | Shopping | 2021-09-03 | 2021-09-13 | 2021-11-02 | 2021-11-02 | GoP | 202610 | 202610
310100100001000 | OFFICE SUPPLIES FOR THE USE OF IPIL POO, IPIL,ZSP | Pantawid Pamilya program | NO | Shopping | 2021-11-10 | 2021-11-15 | 2021-11-16 | 2021-11-16 | GoP | 118995 | 118995
310100100001000 | PANTAWID PAMILYA REGISTRATION SET 11B | Pantawid Pamilya program | NO | NP-53.9 - Small Value Procurement | 2021-11-15 | 2021-11-22 | 2021-11-23 | 2021-11-23 | GoP | 194167.9 | 194167.9
310100100001000 | TO BE DISTRIBUTED POSTED ON PUBLIC SPACES ON NOVEMBER 2021 | Pantawid Pamilya program | NO | NP-53.9 - Small Value Procurement | 2021-11-15 | 2021-11-22 | 2021-11-23 | 2021-11-23 | GoP | 88875 | 88875
310100100001000 | PURCHASE OF BREAD AND PASTRY NC-II SKILLS TRAINING BY BAKING AND PASTRY FOR SINDANGAN 59 BENES CY 2021 | Pantawid Pamilya program | NO | Shopping | 2021-11-29 | 2021-12-06 | 2021-12-28 | 2021-12-28 | GoP | 142367 | 142367
310100100001000 | TO BE USED IN THE 3RD FLOOR PANTAWID SECTION | Pantawid Pamilya program | NO | Shopping | 2021-11-29 | 2021-12-06 | 2021-12-28 | 2021-12-28 | GoP | 302500 | 302500
310100100001000 | Purchase of Office Supplies, Medical Supplies TO BE USE IN THE 3RD FLOOR PANTAWID SECTION | Pantawid Pamilya program | NO | Shopping | 2021-11-29 | 2021-12-06 | 2021-12-07 | 2021-12-15 | GoP | 39600 | 39600
310100100001000 | C0NDUCT OF STAFF DEVELOPMEN FOR PANTAWID RPMO STAFF 2021, PROGRAM ASSESSMENT PROGRAM ASSESSMENT AND STRATEGIC DIRECTION SETTLING FOR 2022 ON DEC 16-17-, 2021 AT Z.C | Pantawid Pamilya program | NO | NP-53.10 Lease of Real Property and Venue | 2021-12-06 | 2021-12-13 | 2021-12-14 | 2021-12-14 | GoP | 159200 | 159200
100000100001000 | PROC. OF SERVICE PROVIDERS FOR ADMINISTRATIVE SUPPORT SERVICES FOR 5 MONTHS FOR ACCOUNTING SECTION | Accounting | NO | NP-53.9 - Small Value Procurement | 2021-07-23 | 2021-07-27 | 2021-07-27 | 2021-07-27 | GoP | 587244 | 587244
100000100001000 | PURCHASE OF FOR ADDITIONAL OFFICE SUPPLIES SECOND SEM ACCOUNTING UNIT | Accounting | NO | Shopping | 2021-11-29 | 2021-12-06 | 2021-12-28 | 2021-12-28 | GoP | 142367 | 142367
320104100001000 | FOR THE USE OF ADOPTION RESOURCE AND REFERRAL SECTION (ARRS)-PSD STAFF | ARRS | NO | Shopping | 2021-07-05 | 2021-07-12 | 2021-07-13 | 2021-07-13 | GoP | 50093 | 50093
320104100001000 | TO BE SERVE DURING THE CONSULTATION - DIALOQUE CUM WORKSHOP FOR REGIONAL CHILD WELFARE SPECIALIST (RSWSG) | ARRS | NO | NP-53.9 - Small Value Procurement | 2021-08-12 | 2021-08-16 | 2021-08-17 | 2021-08-17 | GoP | 66000 | 66000
320104100001000 | TO BE SERVE DURING THE CAPACITY BUILDING FOR LGU SOCIAL WORKERS AND CCAs ON ALTERNATIVE PARENTAL CARE PROGRAM | ARRS | NO | Lease of Real Property and Venue | 2021-08-12 | 2021-08-16 | 2021-08-17 | 2021-08-17 | GoP | 175500 | 175500
320104100001000 | CAPACITY BUILDING FOR LGU SOCIAL WORKERS AND CCAs ON ALTERNATIVE PARENTAL CARE PROGRAM ZAMBOANGA DEL SUR CLUSTER | ARRS | NO | Lease of Real Property and Venue | 2021-08-12 | 2021-08-23 | 2021-09-06 | 2021-09-06 | GoP | 315000 | 315000
320104100001000 | CAPACITY BUILDING FOR LGU SOCIAL WORKERS AND CCAs ON ALTERNATIVE PARENTAL CARE PROGRAM ZAMBOANGA DEL NORTE CLUSTER | ARRS | NO | Lease of Real Property and Venue | 2021-08-12 | 2021-08-23 | 2021-08-24 | 2021-08-24 | GoP | 337500 | 337500
320104100001000 | TO BE SERVE DURING THE ALAGA KALINGA PARA SA BARANGAY,FOSTER CARE IN THE BARANGAY AT ZAMBOANGA CITY | ARRS | NO | Lease of Real Property and Venue | 2021-09-30 | 2021-10-04 | 2021-10-05 | 2021-10-05 | GoP | 236250 | 236250
100000100001000 | CY 2021 2ND SEMESTER DIVISION PERFORMANCE REVIEW | ADMIN | NO | Lease of Real Property and Venue | 2021-12-14 | 2021-12-20 | 2021-12-21 | 2021-12-20 | GoP | 202400 | 202400
320101100001000 | Purchase of Supplies FOR THE USE OF MAINTAINING CLEANLINESS OF FOOT WEAR BEFORE ENTERING THE FACILITY AND FOR THE USE OF HANDWASHING AND DRYING OF HANDS | AVRC III | NO | Shopping | 2021-07-03 | 2021-07-12 | 2021-07-13 | 2021-07-13 | GoP | 77900 | 77900
320101100001000 | FOR THE USE OF SAFE KEEPING OF DOCUMENTS AND FOR THE USE OF THE CENTER ACTIVITY | AVRC III | NO | Shopping | 2021-07-03 | 2021-07-12 | 2021-07-13 | 2021-07-13 | GoP | 85000 | 85000
320101100001000 | FOR THE USE OF THE CLIENT IN VOCATIONAL TRAINING | AVRC III | NO | Shopping | 2021-07-03 | 2021-07-12 | 2021-07-13 | 2021-07-13 | GoP | 381572.5 | 381572.5
320101100001000 | AVRC III INFORMATION AND ADVOCACY MATERIALS | AVRC III | NO | NP-53.9 - Small Value Procurement | 2021-07-03 | 2021-07-12 | 2021-07-27 | 2021-07-27 | GoP | 250200 | 250200
320101100001000 | MONTHLY PROVISION OF HYGIENE KIT FOR AVRC-III CLIENTS | AVRC III | NO | Shopping | 2021-07-03 | 2021-07-12 | 2021-07-13 | 2021-07-13 | GoP | 290880 | 290880
320101100001000 | PPE FOR THE USE OF AVRC-III STAFF FOR CY-2021 | AVRC III | NO | Shopping | 2021-07-08 | 2021-07-19 | 2021-07-20 | 2021-07-20 | GoP | 91600 | 91600
320101100001000 | STAFF DEVELOPMENT ON JULY 29-30, 2021 | AVRC III | NO | Lease of Real Property and Venue | 2021-07-08 | 2021-07-12 | 2021-07-13 | 2021-07-13 | GoP | 74100 | 74100
320101100001000 | PURCHASE OF SERVICE OF 8 STAFFS FOR THE EFFECTIVE AND EFFICIENT PROVISION OF SERVICES TO PWDs CLIENT RESPONSIVE TO THEIR NEEDS AUG 16- DEC 22, 2021 | AVRC III | NO | NP-53.9 - Small Value Procurement | 2021-07-21 | 2021-07-26 | 2021-07-27 | 2021-07-27 | GoP | 977487 | 977487
320101100001000 | REPAIR OF POULTRY FACILITY FOR SKILLS ACQUISITIONS OF PWDs OF AVRC-III | AVRC III | NO | NP-53.9 - Small Value Procurement | 2021-07-26 | 2021-08-09 | 2021-08-11 | 2021-08-11 | GoP | 295000 | 295000
320101100001000 | PROVISION OF TAILORED COSTUMES FOR AVRC III BAND AND SONG INTERPRETERS | AVRC III | NO | Shopping - Ordinary Office Supplies and Equipment | 2021-07-28 | 2021-08-09 | 2021-10-19 | 2021-10-19 | GoP | 136000 | 136000
320101100001000 | CONDUCT OF COVID-19 SCREENING TEST PRIOR TO ACTIVATION AND PROBABLE COVID-19 INFECTED PWDs CLIENT | AVRC III | NO | NP-53.9 - Small Value Procurement | 2021-07-28 | 2021-08-09 | 2021-08-11 | 2021-08-11 | GoP | 280000 | 280000
320101100001000 | FOR MEDICAL USE OF CLIENT | AVRC III | NO | Shopping - Ordinary Office Supplies and Equipment | 2021-07-29 | 2021-08-09 | 2021-10-19 | 2021-10-19 | GoP | 430055 | 430055
320101100001000 | IMPROVEMENT AND INSTALLATION OF CCTV AT AVRC III | AVRC III | NO | NP-53.9 - Small Value Procurement | 2021-08-19 | 2021-08-31 | 1-SEPT-2021 | 1-SEPT-2021 | GoP | 300000 | 300000
320101100001000 | FOR THE USE OF GROUND AND BUILDING MAINTENANCE AT AVRC-III | AVRC III | NO | Shopping | 2021-08-26 | 2021-09-06 | 2021-10-05 | 2021-10-05 | GoP | 115505 | 115505
320101100001000 | MONTHLY PROVISION OF HYGIENE KIT FOR AVRC-III CLIENTS | AVRC III | NO | Shopping | 2021-08-27 | 2021-09-06 | 2021-09-06 | 2021-09-06 | GoP | 293280 | 293280
320101100001000 | LIVELIHOOD ASSISTANCE: PROVISION OF STARTER KIT FOR GRADUATE CLIENTS ON VOCATIONAL SKILL COURSE (BARBERING) | AVRC III | NO | Shopping | 2021-08-28 | 2021-09-06 | 2021-09-07 | 2021-09-07 | GoP | 89495 | 89495
320101100001000 | LIVELIHOOD ASSISTANCE: PROVISION OF STARTER KIT FOR GRADUATE CLIENTS ON VOCATIONAL SKILL COURSE (MASSAGE THERAPY) | AVRC III | NO | Shopping | 2021-08-28 | 2021-09-06 | 2021-10-05 | 2021-10-05 | GoP | 213763.5 | 213763.5
320101100001000 | LIVELIHOOD ASSISTANCE: PROVISION OF STARTER KIT FOR GRADUATE CLIENTS ON VOCATIONAL SKILL COURSE (POULTRY) | AVRC III | NO | Shopping | 2021-08-28 | 2021-09-06 | 2021-09-07 | 2021-09-07 | GoP | 63370 | 63370
320101100001000 | FOR THE USE OF PWD TRAINEES OF AVRC-III ALONG AGRICULTURE | AVRC III | NO | Shopping | 2021-09-01 | 2021-09-06 | 23-2021- | 23-2021- | GoP | 157735.5 | 157735.5
320101100001000 | SPIRITUAL LIFE CELEBRATION CUM VALUES FORMATION SESSION OF AVRC III STAFF AND CLIENTS | AVRC III | NO | NP-53.9 - Small Value Procurement | 2021-09-02 | 2021-09-06 | 2021-09-06 | 2021-09-06 | GoP | 141600 | 141600
320101100001000 | FOR FAMILY DAY CELEBRATION | AVRC III | NO | NP-53.9 - Small Value Procurement | 2021-09-08 | 2021-09-13 | 2021-09-14 | 2021-09-14 | GoP | 58500 | 58500
320101100001000 | UPGRADING OF COVERED PATHWALKS | AVRC III | NO | NP-53.9 - Small Value Procurement | 2021-09-20 | 2021-09-27 | 2021-11-16 | 2021-11-16 | GoP | 365870.5 | 365870.5
320101100001000 | MAINTENANCE OF AVRC-III ROAD ACCESS | AVRC III | NO | NP-53.9 - Small Value Procurement | 2021-09-20 | 2021-09-27 | 2021-09-28 | 2021-09-28 | GoP | 258750 | 258750
320101100001000 | REPAIR OF THE CEILING OF MAIN BUILDING AT AVRC III, MAMPANG , Z.C | AVRC III | NO | NP-53.9 - Small Value Procurement | 2021-09-20 | 2021-09-27 | 2021-11-16 | 2021-11-16 | GoP | 370980 | 370980
320101100001000 | FOR THE USE OF AVRC-III AMBULANCE WITH PLATE # PO-C432 | AVRC III | NO | Shopping | 2021-09-28 | 2021-10-04 | 2021-11-09 | 2021-11-09 | GoP | 68800 | 68800
320101100001000 | 2021 NATIONAL DEAF AWARENESS WEEK OBSERVANCE | AVRC III | NO | NP-53.9 - Small Value Procurement | 2021-11-04 | 2021-11-15 | 2021-11-16 | 2021-11-16 | GoP | 75000 | 75000
320101100001000 | FOR THE USE OF PAGING SYSTEM AT THE CENTER | AVRC III | NO | Shopping | 2021-11-04 | 2021-11-15 | 2021-11-16 | 2021-11-16 | GoP | 101200 | 101200
320101100001000 | REPAIR OF COMPORT ROOM IN THE MAIN BUILDING AND DORMITORIES | AVRC III | NO | NP-53.9 - Small Value Procurement | 2021-11-04 | 2021-11-15 | 2021-11-16 | 2021-11-16 | GoP | 278133 | 278133
320101100001000 | AVRC III STAFF DEVELOPMENT MEETING | AVRC III | NO | NP-53.9 - Small Value Procurement | 2021-11-18 | 2021-11-22 | 2021-11-23 | 2021-11-23 | GoP | 77140 | 77140
320101100001000 | PROVISION OF PERSONAL PROTECTIVE EQUIPMENT TO PWDS ON VOCATIONAL REHABILITATION ALONG BEAUTY CARE AND MASSAGE THERAPY | AVRC III | NO | Shopping | 2021-11-29 | 2021-12-06 | 2021-12-24 | 2021-12-23 | GoP | 97125 | 97125
320101100001000 | OTHER SUPPLIES | Home for Elderly | NO | Shopping | 2021-07-09 | 2021-07-19 | 2021-08-03 | 2021-08-03 | GoP | 208530 | 208530
320101100001000 | Purchase of Catering Services re:FOR THE CONDUCT OF 3RD & 4TH QUARTER SOCIAL ENHANCEMENT ACTIVITY OF THE HOME FOR THE ELDERLY | Home for Elderly | NO | NP-53.9 - Small Value Procurement | 2021-07-13 | 2021-07-19 | 20-Ju-l21 | 20-Ju-l21 | GoP | 54400 | 54400
320101100001000 | FOR THE HFE OPERATION | Home for Elderly | NO | Shopping | 2021-08-17 | 2021-08-23 | 2021-10-05 | 2021-10-05 | GoP | 250090 | 250090
320101100001000 | Purchase of ICT ACCESSORIES AND EQUIPMENTS | Home for Elderly | NO | Shopping | 2021-08-17 | 2021-08-23 | 2021-09-14 | 2021-09-14 | GoP | 290050 | 290050
320101100001000 | Purchase of MEAT & FROZEN MEAT | Home for Elderly | NO | Shopping | 2021-08-17 | 2021-08-23 | 14-Sept-2021 | 14-Sept-2021 | GoP | 242760 | 242760
320101100001000 | Purchase of FOOD STUFF (GROCERY ITEMS) | Home for Elderly | NO | Shopping | 2021-08-17 | 2021-08-23 | 2021-11-09 | 2021-11-09 | GoP | 92710 | 92710
320101100001000 | FOR THE OPERATION OG THE HOME FOR THE ELDERLY | Home for Elderly | NO | Shopping | 2021-09-18 | 2021-09-27 | 2021-09-28 | 2021-09-28 | GoP | 71540 | 71540
320101100001000 | TO BE INSTALLED ON THE NEWLY CONSTRCUTED AND REAPIRED BUILDING AND ROOMS OF CLIENTS | Home for Elderly | NO | NP-53.9 - Small Value Procurement | 2021-09-28 | 2021-10-04 | 2021-10-05 | 2021-10-05 | GoP | 157600 | 157600
320101100001000 | Purchase of Service Provider/Manpower FOR THE OPERATION OF THE HOME FOR THE ELDERLY OCTOBER 24-DECEMBER 31, 2021 | Home for Elderly | NO | NP-53.9 - Small Value Procurement | 2021-09-29 | 2021-10-04 | 2021-10-05 | 2021-10-05 | GoP | 657039.96 | 657039.96
320101100001000 | Purchase of Medical Supplies for the USE OF CLIENTS OF THE HOME FOR THE ELDERLY | Home for Elderly | NO | Shopping | 2021-10-22 | 2021-11-08 | 2021-12-14 | 2021-12-14 | GoP | 240255 | 240255
320101100001000 | TO BE PLACED ON THE NEWLY CONSTRUCTED AND REPAIRED BUILDING OF THE HOME OF ELDERLY | Home for Elderly | NO | Shopping | 2021-11-18 | 2021-11-22 | 2021-12-14 | 2021-12-14 | GoP | 370300 | 370300
320101100001000 | Purchase of Food Supplies for DAILY CONSUMPTION OF CLIENTS OF HE HOME FOR THE ELDERLY (VEGETABLES) | Home for Elderly | NO | Shopping | 2021-12-16 | 2021-12-20 | 2021-12-21 | 2021-12-21 | GoP | 221000 | 221000
320101100001000 | Purchase of Food Supplies for FOOD CONSUMPTION OF CLIENTS OF THE HOME FOR THE ELDERLY (FRESH MEAT) | Home for Elderly | NO | Shopping | 2021-12-16 | 2021-12-20 | 2021-12-28 | 2021-12-28 | GoP | 280500 | 280500
320101100001000 | Purchase of OFFICE SUPPLIES OFFICE SUPPLIESFOR THE HOME FOR THE ELDERLY OPERATION | Home for Elderly | NO | Shopping | 2021-12-16 | 2021-12-20 | 2021-12-21 | 2021-12-21 | GoP | 242700 | 242700
320101100001000 | FOR THE CONDUCT OF THE VALUES STRENGTHENING OF RESIDENTS IN THE HOME OF ELDERLY | Home for Elderly | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2021-07-13 | 2021-07-13 | GoP | 31500 | 31500
320101100001000 | TO BE USED DURING THE CONDUCT OF NUTRITION MONTH ACTIVITY OF THE HOME ELDERLY | Home for Elderly | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2021-07-13 | 2021-07-13 | GoP | 35300 | 35300
320101100001000 | FOR THE HOME ELDERLY OPERATION | Home for Elderly | NO | Shopping | N/A | N/A | 2021-07-13 | 2021-07-13 | GoP | 47580 | 47580
320101100001000 | FOR THE CONDUCT OF VALUE STRENGTHENING OF THE HOME OF THE ELDERLY | Home for Elderly | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2021-07-13 | 2021-07-13 | GoP | 4000 | 4000
320101100001000 | ONE UNIT TO BE USED FOR THE IMPLEMENTATION OF THE QR CODE SCANNING AND ONE UNIT FOR THE HFE IPERATION TO BE USE BY CENTER HEAD | Home for Elderly | NO | Shopping | N/A | N/A | 2021-08-24 | 2021-08-24 | GoP | 29998 | 29998
320101100001000 | PURCHASE MATERIALS TO BE USE FOR THE INSTALLATION AT THE NICHE OF THE DEPARTED CLIENTS OF HFE | Home for Elderly | NO | Shopping | N/A | N/A | 2021-08-24 | 2021-08-24 | GoP | 25200 | 25200
320101100001000 | AIRCON INSTALLATION | Home for Elderly | NO | NP-53.9 - Small Value Procurement | 2021-11-01 | 2021-11-01 | 2021-11-01 | 2021-11-01 | GoP | 101456.25 | 101456.25
320101100001000 | COVID-19 RT-PCR TEST (SWAB) | Home for Elderly | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2021-11-01 | 2021-11-01 | GoP | 3800 | 3800
320101100001000 | AIRCON CLEANING;SPLIT TYPE;KOPPEL BRAND | Home for Elderly | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2021-11-01 | 2021-11-01 | GoP | 1500 | 1500
320101100001000 | SUPPLY AND INSTALLATION OF LIGHTED PANAFLEX SIGNAGE (0.6M X 2.0M) | Home for Elderly | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2021-11-01 | 2021-11-01 | GoP | 44450 | 44450
320101100001000 | Purchase of Materials for VARIOUS REPAIRS at HFE | Home for Elderly | NO | NP-53.9 - Small Value Procurement | 2021-11-01 | 2021-11-01 | 2021-11-01 | 2021-11-01 | GoP | 108159.55 | 108159.55
320101100001000 | REPAIR OF EXTERIOR CEILING AT THE MULTIPURPOSE BUILDING OF HFE | Home for Elderly | NO | NP-53.9 - Small Value Procurement | 2021-11-01 | 2021-11-01 | 2021-11-01 | 2021-11-01 | GoP | 142055.85 | 142055.85
320101100001000 | Purchase of Office Supplies for the use at HFE | Home for Elderly | NO | Shopping | 2021-12-01 | 2021-12-01 | 2021-12-01 | 2021-12-01 | GoP | 281169 | 281169
320105100002000 | purchase of Eco Bag with DSWD logo (Customized) at least 14 " length X 16 " width | PCDP | NO | Shopping | 2021-12-01 | 2021-12-01 | 2021-12-01 | 2021-12-01 | GoP | 89000 | 89000
320105100002000 | Purchase of Adult Side Chai, Whitebaord with Roller, Water Dispenser, Philippine Flag and Wifi Repeater | PCDP | NO | Shopping | 2021-11-01 | 2021-11-01 | 2021-11-01 | 2021-11-01 | GoP | 392109 | 392109
320105100002000 | Purchase of Office Supplies for the use of PCDP | PCDP | NO | Shopping | 2021-10-01 | 2021-10-01 | 2021-10-01 | 2021-10-01 | GoP | 86251.6 | 86251.6
320105100002000 | Purchase of Cleaning Equipment for the use at PCDP (Vacum Cleaner up to Portable Welding Machine) | PCDP | NO | Shopping | 2021-10-01 | 2021-10-01 | 2021-10-01 | 2021-10-01 | GoP | 80033 | 80033
330100100001000 | Purchase of COMMON ICT EQUIPMENT for the use of PCDP (Processor, Latest Architecture up to Computer Printer 3in1 with Build Tank ink (Good QUALITY)) | PCDP | NO | Shopping | 2021-12-01 | 2021-12-01 | 2021-12-01 | 2021-12-01 | GoP | 269150 | 269150
330100100001000 | FOR THE FOOD (FISH) CONSUMPTION OF DEPORTEES/PCDP CLIENTS (3RD QUARTER OF 2021) | PCDP | NO | Shopping | 2021-08-05 | 2021-08-09 | 2021-08-17 | 2021-09-09 | GoP | 764000 | 764000
330100100001000 | FOR THE FOOD CONSUMPTION (FRESH FRUITS) DEPORTEES PCDP CLIENTS | PCDP | NO | Shopping | 2021-12-07 | 2021-12-13 | 2021-12-14 | 2021-12-14 | GoP | 307395 | 307395
330100100001000 | Labor and Materials for INSTALLATION OF COMBAT WIRES AT PCDP | PCDP | NO | NP-53.9 - Small Value Procurement | 2021-11-09 | 2021-11-15 | NOV.23,2021 | 2021-11-01 | GoP | 371983.38 | 371983.38
330100100001000 | Purchase of COMMMON JANITORIAL SUPPLIES OF PROCESSING CENTER FOR DISPLACED PERSONS | PCDP | NO | Shopping | 2021-11-18 | 2021-11-29 | DEC.01,2021 | 2021-12-14 | GoP | 72524 | 72524
330100100001000 | FOR THE USE OF REPACKING FOOD PACKS FOR THE REFS/PCDP CLIENTS | PCDP | NO | Shopping | 2021-11-18 | 2021-11-29 | DEC.21,2021 | 2021-12-14 | GoP | 539000 | 539000
330100100001000 | FOR OFFICE EQUIPMENT OF DEPORTEES/PROCESSING CENTER FOR DISPLACED PERSONS | PCDP | NO | Shopping | 2021-11-19 | 2021-11-29 | DEC.21,2021 | 2021-12-14 | GoP | 188775 | 188775
330100100001000 | FOR OFFICE EQUIPMENT OF DEPORTEES/PROCESSING CENTER FOR DISPLACED PERSONS | PCDP | NO | Shopping | 2021-11-19 | 2021-11-29 | DEC.01,2021 | 2021-12-14 | GoP | 692500 | 692500
330100100001000 | PURCHASE OF KITCHEN SUPPLIES USE FOR THE COOK OF PROCESSING CENTER FOR DISPLACED PERSONS | PCDP | NO | Shopping | 2021-12-20 | 2021-12-24 | DEC.24,2021 | 2021-12-14 | GoP | 317385 | 317385
330100100001000 | PURCHASE OF FOOD CONSUMPTION (MILK) OF DEPORTEES/PROCESSING CENTER FOR DISPLACED | PCDP | NO | Shopping | 2021-12-20 | 2021-12-24 | DEC.24,2021 | 2021-12-14 | GoP | 454500 | 454500
330100100001000 | PURCHASE OF MEDICAL EQUIPMENT OF DEPORTEES/PROCESSING CENTER FOR DISPLACED PERSONS | PCDP | NO | Shopping | 2021-12-20 | 2021-12-24 | DEC.24,2021 | 2021-12-14 | GoP | 120470 | 120470
330100100001000 | PURCHASE OF LAUNDRYSUPPLIES FOR THE USE OF DEPORTEES/PROCESSING CENTER FOR DISPLACED PERSON CLIENT | PCDP | NO | Shopping | 2021-12-20 | 2021-12-24 | DEC.24,2021 | 2021-12-14 | GoP | 136050 | 136050
200000100001000 | LABOR AND MATERIALS FOR THE Electrical Improvement at Propose MIS Office | ICTMS | NO | NP-53.9 - Small Value Procurement | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | GoP | 90783.01 | 90783.01 |  | BAC RESO NO. 074-09-2021 (CHANGE MODE OF PROCUREMENT FROM PUBLIC BIDDING TO SMALL VALUE PROCUREMENT DUE TO THE SAID PROJECTS WAS ERRONEOUSLY LUMP IN ONE TILE PROCUREMENT)
200000100001000 | LABOR AND MATERIALS FOR THE Site Development and Restructuring of MIS Office | ICTMS | NO | NP-53.9 - Small Value Procurement | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | GoP | 159162.88 | 159162.88 |  | BAC RESO NO. 074-09-2021 (CHANGE MODE OF PROCUREMENT FROM PUBLIC BIDDING TO SMALL VALUE PROCUREMENT DUE TO THE SAID PROJECTS WAS ERRONEOUSLY LUMP IN ONE TILE PROCUREMENT)
200000100001000 | LABOR AND MATERIALS FOR THE Provision of Drainage at FO IX | ICTMS | NO | NP-53.9 - Small Value Procurement | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | GoP | 17827.3 | 17827.3 |  | BAC RESO NO. 074-09-2021 (CHANGE MODE OF PROCUREMENT FROM PUBLIC BIDDING TO SMALL VALUE PROCUREMENT DUE TO THE SAID PROJECTS WAS ERRONEOUSLY LUMP IN ONE TILE PROCUREMENT)
200000100001000 | LABOR AND MATERIALS FOR THE Provision of Covered Pathwalk @ OPCEN Pagadian; | ICTMS | NO | NP-53.9 - Small Value Procurement | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | GoP | 180000 | 180000 |  | BAC RESO NO. 074-09-2021 (CHANGE MODE OF PROCUREMENT FROM PUBLIC BIDDING TO SMALL VALUE PROCUREMENT DUE TO THE SAID PROJECTS WAS ERRONEOUSLY LUMP IN ONE TILE PROCUREMENT)
200000100001000 | LABOR AND MATERIALS FOR THE Provision of Glass Partition Extension at OPCEN Pagadian; | ICTMS | NO | NP-53.9 - Small Value Procurement | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | GoP | 96570.68 | 96570.68 |  | BAC RESO NO. 074-09-2021 (CHANGE MODE OF PROCUREMENT FROM PUBLIC BIDDING TO SMALL VALUE PROCUREMENT DUE TO THE SAID PROJECTS WAS ERRONEOUSLY LUMP IN ONE TILE PROCUREMENT)
200000100001000 | LABOR AND MATERIALS FOR THE Provision of Drainage Canal at at OPCEN Pagadian; | ICTMS | NO | NP-53.9 - Small Value Procurement | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | GoP | 49994.47 | 49994.47 |  | BAC RESO NO. 074-09-2021 (CHANGE MODE OF PROCUREMENT FROM PUBLIC BIDDING TO SMALL VALUE PROCUREMENT DUE TO THE SAID PROJECTS WAS ERRONEOUSLY LUMP IN ONE TILE PROCUREMENT)
200000100001000 | LABOR AND MATERIALS FOR THE Propose Site Development at OPCEN Pagadian. | ICTMS | NO | NP-53.9 - Small Value Procurement | 2021-09-20 | 2021-09-20 | 2021-09-20 | 2021-09-20 | GoP | 48895.47 | 48895.47 |  | BAC RESO NO. 074-09-2021 (CHANGE MODE OF PROCUREMENT FROM PUBLIC BIDDING TO SMALL VALUE PROCUREMENT DUE TO THE SAID PROJECTS WAS ERRONEOUSLY LUMP IN ONE TILE PROCUREMENT)
| Prepared By: | Funds Allocated: |  |  | Recommended By: |  |  |  |  | Approved by:
| XANTHI ROMEILLA J. VALLECER | MA. CORAZON G. SUMICAD |  |  | RIDUAN P. HADJIMUDDIN |  |  |  |  | ATTY. SITTIE RAIFAH M. PAMALOY-HASSAN
| BAC Secretariat head | Chief, FMD |  |  | BAC Chairperson |  |  |  |  | OIC Regional Director

## how_to_fill_out-definitions
| GUIDE TO PREPARE APP | APP COLUMN HEADER/S
STEP 1 | In the Code column, kindly indicate the PAP Code. Please refer to the code indicated in the technical budget posted in the DBM website. For GOCCs and LGUs, indicate the procuring entity's internal numbering system. | Code (PAP)
STEP 2 | For the Procurement Project column, please align descriptions of program/projects with budget documents and ensure clarity and accuracy in describing each procurement program/project. | Procurement Project
STEP 3 | For PMO/End-User, please indicate the PMO/End-User unit who will implement/utilize the procurement program/project. Multiple end-user units are allowed only if the procurement activity was consolidated by the BAC to procure requirements of the end-user units. | PMO/End-User
STEP 4 | For Mode of Procurement and Schedule for Each Procurement Activity, all modes of procurement are available as a dropdown list and requirements for a specific schedule for Ads/Post of IB/REI, Sub/Open of Bids, Notice of Award, and/or Contract Signing are automatically identified thru the MS Excel formula. Note that for Foreign-funded procurement, please use Others - Foreign-funded procurement as the Mode of Procurement. Kindly indicate a specific period (dates, month, quarter) when each Procurement Activity will be done. Please refer to our website: http://www.gppb.gov.ph/timelines/timelines.htm for the specific periods for each activity. Note: For SVP, IB/REI is similar to RFQ. Ads/Post of IB/REI for Shopping 52.1(b) and NP-SVP (53.9) needs to be posted in PhilGEPS for ABCs above 50k. Notice of Award posting in PhilGEPS is mandatory for all Alternative Modes only for ABCs above 50k. | Mode of Procurement | Schedule for Each Procurement Activity
|  |  | Ads/Post of IB/REI | Sub/Open of Bids | Notice of Award | Contract Signing
STEP 5 | For Source of Funds, a dropdown list is available. If the Source of Funds the PE will use is not included, please indicate "Others" and specify under the Remarks column. | Source of Funds
STEP 6 | For Estimated Budget (PhP), kindly fill out either MOOE or CO columns only. Total ABC column is not editable, but will automatically compute for the total MOOE and CO components of the project. This breakdown is needed for tracking purposes. Finally, please ensure that amounts indicated are aligned with budget documents. | Estimated Budget (PhP)
STEP 7 | Before submission to the GPPB, ensure that the Head of the Procuring Entity (HoPE) approves/signs the APP.
GENERAL INFORMATION
#1 | All Cells with Fill Color Orange needs to be filled out by the Agency. This is a visual reminder of blank or improperly filled out cells.
#2 | To ensure that automated indicator which procurement activity needs to be filled out with specific periods, PE must copy entire Excel row with the mode of procurement for the specific procurement program/project and paste on the last sample row "Negotiated Procurement-53.13" in the template.
#3 | If PE wishes to edit formatting and design of borders, fonts, among others of the APP template, it is suggested to utilize the automated formulas in the template before copying contents and reformatting.
#4 | Per Section of 3.1.1 of DBM Circular No. 2015-7, the Approved Budget for the Contract (ABC) shall be “[t]he amount reflected in the MYOA”. Hence, the ABC in the Annual Procurement Plan (APP) shall be the full amount stated in the MYOA with remarks added on how much will be actually disbursed for that particular fiscal year. Moreover, the Procurement Monitoring Report (PMR) should also reflect full amount in the MYOA if the entire contract was awarded within the fiscal year. Thus, for succeeding years, actual disbursements from the MYOA need not be reflected in the APPs and PMRs, unless current contract with MYOA is terminated and a new procurement activity is undertaken.
DEFINITIONS
1. PROGRAM (BESF)– A homogeneous group of activities necessary for the performance of a major purpose for which a government agency is established, for the basic maintenance of the agency’s administrative operations or for the provisions of staff support to the agency’s administrative operations or for the provisions of staff support to the agency’s line functions.
2. PROJECT (BESF)– Special agency undertakings which are to be carried out within a definite time frame and which are intended to result in some pre-determined measure of goods and services.
3. PMO/End User - Unit as proponent of program or project
4. Mode of Procurement - Competitive Bidding and Alternative Methods including: selective bidding, direct contracting, repeat order, shopping, and negotiated procurement.
5. Schedule for Each Procurement Activity - Major procurement activities (advertising/posting; submission and receipt/Opening of bids; award of contract; contract signing).
6. Source of Funds - Whether GoP, Foreign Assisted or Special Purpose Fund
7. Estimated Budget - Agency approved estimate of project/program costs
8. Remarks - brief description of program or project

## data_validation (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
Emergency Procurement under the Bayanihan Act
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets
Others - Foreign-funded procurement