## app
|  | DEPARTMENT OF SOCIAL WELFARE AND DEVELOPMENT (DSWD FO-IX) Indicative Annual Procurement Plan for FY 2024 for Non-CSE | [11 empty] | Department of Budget and Management Procurement Monitoring Report as of month/day/2006
Code (PAP) | Procurement Project | PMO/ End-User | Is this an Early Procurement Activity? (Yes/No) | Mode of Procurement | Schedule for Each Procurement Activity |  |  |  | Source of Funds | Estimated Budget (PhP) |  |  | Remarks (brief description of Project) | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [8 empty] | Remarks (Explaining changes from the APP)
[5 empty] | Advertisement/Posting of IB/REI | Submission/Opening of Bids | Notice of Award | Contract Signing |  | Total | MOOE | CO |  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  | Pre-Proc Conf | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Delivery/ Accept
100000100001000 | Procurement of Ink refills for daily operation | GASS | NO | Shopping | N/A | N/A | 2024-02-01 | 2024-03-01 | GoP | 30561 | 30561
100000100001000 | Procurement of Electronic Load for Division Heads, Section Heads and staffs | GASS | NO | Direct Contracting | N/A | N/A | 2024-02-01 | 2024-03-01 | GoP | 798600 | 798600 |  | THE PROCUREMENT PROJECTS IS SUBJECT TO RENEWAL (PER GPPB RESO. NO. 06-2022)
100000100001000 | Purchase of Postage Stamp | RAMS | NO | NP-53.5 Agency-to-Agency | N/A | N/A | 2024-02-01 | 2024-03-01 | GoP | 2100 | 2100
100000100001000 | Procurement of Meals and Accommodations for meetings | GASS | NO | NP-53.10 Lease of Real Property and Venue | N/A | N/A | 2024-06-01 | 2024-07-01 | GoP | 1244000 | 1244000
100000100001000 | Catering Services for meetings | GASS | NO | NP-53.9 - Small Value Procurement | 2024-06-01 | 2024-06-01 | 2024-07-01 | 2024-07-01 | GoP | 1050200 | 1050200
100000100001000 | Procurement of Office furniture and Equipments | GenServ | NO | Shopping | N/A | N/A | 2024-02-01 | 2024-03-01 | GoP | 7600 | 7600
100000100001000 | Procurement of Rechargeable batteries | GenServ | NO | Shopping | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 148000 | 148000
100000100001000 | Procurement of Tires for DSWD vehicles | GenServ | YES | Competitive Bidding | 2023-11-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | GoP | 3420400 | 3420400
100000100001000 | Procurement of Automotive specialty tools | GenServ | NO | Shopping | N/A | N/A | 2024-02-01 | 2024-03-01 | GoP | 35000 | 35000
100000100001000 | Procurement of Janitorial services for FY 2024 | GenServ | YES | Competitive Bidding | 2023-11-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | GoP | 10633345.8 | 10633345.8 |  | THE PROCUREMENT PROJECTS IS SUBJECT TO RENEWAL (PER GPPB RESO. NO. 06-2022)
100000100001000 | Procurement of Security guard services for FY 2024 | GenServ | YES | Competitive Bidding | 2023-11-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | GoP | 20612736 | 20612736 |  | THE PROCUREMENT PROJECTS IS SUBJECT TO RENEWAL (PER GPPB RESO. NO. 06-2022)
100000100001000 | Procurement of Diesel, Gasoline Fuel and Engine Oil for daily operation | GenServ | NO | NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 9975600 | 9975600
100000100001000 | Purchase of Braking systems and components (Fluids) | GenServ | NO | NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | N/A | N/A | 2024-02-01 | 2024-03-01 | GoP | 49600 | 49600
100000100001000 | Procurement of Office supplies | GenServ | NO | Shopping | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 135080 | 135080
100000100001000 | Procurement of Photocopier toner | GenServ | NO | Shopping | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 250000 | 250000
100000100001000 | Procurement of Sprayers and Vacuum cleaners | GenServ | NO | Shopping | N/A | N/A | 2024-02-01 | 2024-03-01 | GoP | 50000 | 50000
100000100001000 | Procurement of Umbrellas, Waterproof jacket or raincoat and boots | GenServ | NO | Shopping | N/A | N/A | 2024-02-01 | 2024-03-01 | GoP | 27600 | 27600
100000100001000 | Procurement of Electrical cable and accessories | GenServ | NO | Shopping | 2024-04-01 | 2024-04-01 | 2024-05-01 | 2024-05-01 | GoP | 57800 | 57800
100000100001000 | Purchase of Oil and Fuel Filters | GenServ | NO | Shopping | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 513000 | 513000
100000100001000 | Procurement of Braking systems and components | GenServ | NO | Shopping | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 587500 | 587500
100000100001000 | Procurement of services for Vehicle air conditioner | GenServ | NO | NP-53.9 - Small Value Procurement | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 665000 | 665000
100000100001000 | Procurement of Vehicle maintenance and repair services | GenServ | NO | NP-53.9 - Small Value Procurement | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 732000 | 732000
100000100001000 | Procurement of Elevator maintenance services | GenServ | NO | Direct Contracting | N/A | N/A | 2024-02-01 | 2024-03-01 | GoP | 210000 | 210000
100000100001000 | Procurement of Air conditioning installation or maintenance or repair services | GenServ | NO | NP-53.9 - Small Value Procurement | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 378000 | 378000
100000100001000 | Procurement of Air conditioning installation or maintenance or repair services | GenServ | NO | NP-53.9 - Small Value Procurement | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 3315000 | 3315000
100000100001000 | Procurement of maintenance and or repair services for Portable generator | GenServ | NO | NP-53.9 - Small Value Procurement | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 70000 | 70000
100000100001000 | Procurement of Vehicle maintenance and repair services | GenServ | NO | Direct Contracting | N/A | N/A | 2024-02-01 | 2024-03-01 | GoP | 1760000 | 1760000
100000100001000 | Procurement of Lease and rental of property or building | GenServ | NO | NP-53.10 Lease of Real Property and Venue | N/A | N/A | 2024-02-01 | 2024-03-01 | GoP | 3720000 | 3720000 |  | THE PROCUREMENT PROJECTS IS SUBJECT TO RENEWAL (PER GPPB RESO. NO. 06-2022)
100000100001000 | Procurement of Cleaning and janitorial supplies | GenServ | NO | Shopping | N/A | N/A | 2024-02-01 | 2024-03-01 | GoP | 28800 | 28800
100000100001000 | Procurement of Fire extinguishers | GenServ | NO | Shopping | N/A | N/A | 2024-02-01 | 2024-03-01 | GoP | 73700 | 73700
100000100001000 | Procurement of Meals and Accommodations during court hearings | Property | NO | NP-53.10 Lease of Real Property and Venue | N/A | N/A | 2024-02-01 | 2024-03-01 | GoP | 570780 | 570780
100000100001000 | Purchase of Airline ticket or boarding pass ATB printers | Property | NO | NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | N/A | N/A | 2024-02-01 | 2024-03-01 | GoP | 360000 | 360000
100000100001000 | Procurement of services for Land surveying | Property | NO | NP-53.9 - Small Value Procurement | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 140000 | 140000
100000100001000 | Procurement of services for Installation of floor tile | Property | NO | NP-53.9 - Small Value Procurement | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 235800 | 235800
100000100001000 | Procurement of Office supplies | Accounting | NO | Shopping | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 1347900 | 1347900
100000100001000 | Procurement of Drug addiction prevention or control services | HRMDD | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2024-02-01 | 2024-03-01 | GoP | 20000 | 20000
100000100001000 | Purchase of Purified Water for daily consumption of staffs | Property | NO | Shopping | N/A | N/A | 2024-02-01 | 2024-03-01 | GoP | 33600 | 33600
100000100001000 | Procurement of Lease and rental of property or building | HRMDD | NO | NP-53.10 Lease of Real Property and Venue | N/A | N/A | 2024-02-01 | 2024-03-01 | GoP | 2770000 | 2770000 |  | THE PROCUREMENT PROJECTS IS SUBJECT TO RENEWAL (PER GPPB RESO. NO. 06-2022)
310100100002000 | Procurement of Ink refills | SLP | NO | Shopping | 2024-04-01 | 2024-04-01 | 2024-05-01 | 2024-05-01 | GoP | 84975 | 84975
310100100002000 | Procurements of Meals and Snacks during cluster meetings | SLP | NO | NP-53.9 - Small Value Procurement | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | GoP | 238000 | 238000
320101100001000 | Procurement of Meat and poultry products | BDSK | YES | Competitive Bidding | 2023-11-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | GoP | 1222750 | 1222750
320101100001000 | Procurement of Fresh Fish | BDSK | YES | Competitive Bidding | 2023-11-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | GoP | 1730300 | 1730300
320101100001000 | Procurement of Fresh Vegetables and Fruits | BDSK | YES | Competitive Bidding | 2023-11-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | GoP | 1306350 | 1306350
320101100001000 | Procurement of Grocery Items | BDSK | YES | Competitive Bidding | 2023-11-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | GoP | 1829535 | 1829535
320101100001000 | Procurement of Meat and poultry products | BDSK | NO | Competitive Bidding | 2024-06-01 | 2024-06-01 | 2024-07-01 | 2024-07-01 | GoP | 1129800 | 1129800
320101100001000 | Procurement of Fresh Fish | BDSK | NO | Competitive Bidding | 2024-06-01 | 2024-06-01 | 2024-07-01 | 2024-07-01 | GoP | 1665290 | 1665290
320101100001000 | Procurement of Fresh Fruits | BDSK | NO | Competitive Bidding | 2024-06-01 | 2024-06-01 | 2024-07-01 | 2024-07-01 | GoP | 369600 | 369600
320101100001000 | Procurement of Fresh Vegetables | BDSK | NO | Competitive Bidding | 2024-06-01 | 2024-06-01 | 2024-07-01 | 2024-07-01 | GoP | 484360 | 484360
320101100001000 | Procurement of Grocery Items | BDSK | NO | Competitive Bidding | 2024-06-01 | 2024-06-01 | 2024-07-01 | 2024-07-01 | GoP | 1881285 | 1881285
320101100001000 | Procurement of Meals and Accommodation for Regional General Assembly | BDSK | NO | NP-53.10 Lease of Real Property and Venue | N/A | N/A | 2024-03-01 | 2024-03-01 | GoP | 30000 | 30000
320101100001000 | Procurement of Cleaning and janitorial supplies | BDSK | NO | Shopping | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 490070 | 490070
320101100001000 | Procurement of Office Equipment and Supplies | BDSK | NO | Shopping | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | GoP | 506283 | 506283
320101100001000 | Procurement of Electronic Load for Section Head and staffs | BDSK | NO | Direct Contracting | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 97200 | 97200
320101100001000 | Procurement of Air conditioning maintenance and repair services | BDSK | NO | NP-53.9 - Small Value Procurement | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 29600 | 29600
320101100001000 | Procurement of Bedding and Linnens | BDSK | NO | Shopping | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | GoP | 58200 | 58200
320101100001000 | Procurement of Apparels for clients | BDSK | NO | Shopping | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | GoP | 601450 | 601450
320101100001000 | Procurement of Catering Services for activities in center | BDSK | NO | NP-53.9 - Small Value Procurement | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 1137700 | 1137700
320101100001000 | Procurement of Meals with Accommodation for meetings | BDSK | NO | NP-53.10 Lease of Real Property and Venue | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 457400 | 457400
320101100001000 | Procurement of Cooking gas refill | BDSK | NO | Shopping | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 370000 | 370000
320101100001000 | Procurement for Diesel of Vehicle | BDSK | NO | NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 382500 | 382500
320101100001000 | Procurement of Medicines and Medical Supplies | BDSK | NO | Shopping | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 428495 | 428495
320101100001000 | Procurement of Heavyduty Fan for daily operation | BDSK | NO | Shopping | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | GoP | 350600 | 350600
320101100001000 | Procurement of Laboratory services | AVRC-III | NO | NP-53.9 - Small Value Procurement | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | GoP | 61000 | 61000
320101100001000 | Procurement of Drugs and Pharmaceutical Products | AVRC-III | NO | Shopping | 2024-04-01 | 2024-04-01 | 2024-05-01 | 2024-05-01 | GoP | 342642 | 342642
320101100001000 | Procurement of Diesel, Gasoline Fuel and Engine Oil for daily operation | AVRC-III | NO | NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | N/A | N/A | 2024-05-01 | 2024-05-01 | GoP | 656750 | 656750
320101100001000 | Procurement of Cleaning and Janitorial supplies | AVRC-III | NO | Shopping | 2024-04-01 | 2024-04-01 | 2024-05-01 | 2024-05-01 | GoP | 581615 | 581615
320101100001000 | Telecommunication Services | AVRC-III | NO | Direct Contracting | N/A | N/A | 2024-05-01 | 2024-05-01 | GoP | 176400 | 176400 |  | THE PROCUREMENT PROJECTS IS SUBJECT TO RENEWAL (PER GPPB RESO. NO. 06-2022)
320101100001000 | Office Equipment and Accessories and Supplies | AVRC-III | NO | Shopping | 2024-04-01 | 2024-04-01 | 2024-05-01 | 2024-05-01 | GoP | 486500 | 486500
320101100001000 | Procurement of Umbrellas, coats and jackets | AVRC-III | NO | Shopping | 2024-04-01 | 2024-04-01 | 2024-05-01 | 2024-05-01 | GoP | 300000 | 300000
320101100001000 | Catering Services for meetings/programs | AVRC-III | NO | NP-53.9 - Small Value Procurement | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 2054500 | 2054500
320101100001000 | Procurement of Printing Services for materials | AVRC-III | NO | NP-53.9 - Small Value Procurement | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 110000 | 110000
320101100001000 | Procurement of personal care products | AVRC-III | NO | Shopping | 2024-04-01 | 2024-04-01 | 2024-05-01 | 2024-05-01 | GoP | 639550 | 639550
320101100001000 | Provision of Grocery Items for clients | AVRC-III | NO | Shopping | 2024-04-01 | 2024-04-01 | 2024-05-01 | 2024-05-01 | GoP | 1096880 | 1096880
320101100001000 | Procurement of Bedclothes and table and kitchen linen and towels | AVRC-III | NO | Shopping | 2024-04-01 | 2024-04-01 | 2024-05-01 | 2024-05-01 | GoP | 226200 | 226200
320101100001000 | Procurement of Assistive devices for clients | AVRC-III | NO | Shopping | 2024-04-01 | 2024-04-01 | 2024-05-01 | 2024-05-01 | GoP | 107000 | 107000
320101100001000 | Procurement of Lettuce seeds or seedlings | AVRC-III | NO | Shopping | 2024-04-01 | 2024-04-01 | 2024-05-01 | 2024-05-01 | GoP | 166000 | 166000
320101100001000 | Procurement of Training tools and kits for clients | AVRC-III | NO | Shopping | 2024-07-01 | 2024-07-01 | 2024-08-01 | 2024-08-01 | GoP | 372100 | 372100
320101100001000 | Procurement of garden handtools | AVRC-III | NO | Shopping | N/A | N/A | 2024-08-01 | 2024-08-01 | GoP | 226550 | 226550
320101100001000 | Procurement of Tools and materials for poultry | AVRC-III | NO | Shopping | 2024-07-01 | 2024-07-01 | 2024-08-01 | 2024-08-01 | GoP | 82044 | 82044
320101100001000 | Procurement of Cookware and kitchen tools | AVRC-III | NO | Shopping | 2024-07-01 | 2024-07-01 | 2024-08-01 | 2024-08-01 | GoP | 77400 | 77400
320101100001000 | Purchase of Painting accessories | AVRC-III | NO | Shopping | N/A | N/A | 2024-08-01 | 2024-08-01 | GoP | 14625 | 14625
320101100001000 | Procurement of School kit for students | AVRC-III | NO | Shopping | 2024-04-01 | 2024-04-01 | 2024-05-01 | 2024-05-01 | GoP | 136050 | 136050
320101100001000 | Procurement of Rehabilitation services for clients | AVRC-III | NO | NP-53.9 - Small Value Procurement | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 162000 | 162000
320101100001000 | Procurement of Meals and Accomodation for program | AVRC-III | NO | NP-53.10 Lease of Real Property and Venue | 2024-07-01 | 2024-07-01 | 2024-08-01 | 2024-08-01 | GoP | 489000 | 489000
320101100001000 | Upgrading of Agricultute classroom and Worshop and Installation of glass division at Archive Records room | AVRC-III | NO | NP-53.9 - Small Value Procurement | 2024-04-01 | 2024-04-01 | 2024-05-01 | 2024-05-01 | GoP | 385000 | 385000
320101100001000 | Procurement of Air conditioning installation or maintenance or repair services | AVRC-III | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2024-06-01 | 2024-06-01 | GoP | 17600 | 17600
320101100001000 | Repair and Maintenace for sewing machine | AVRC-III | NO | NP-53.9 - Small Value Procurement | N/A | N/A | 2024-06-01 | 2024-06-01 | GoP | 10000 | 10000
320101100001000 | Vehicle maintenance and repair services | AVRC-III | NO | NP-53.9 - Small Value Procurement | 2024-04-01 | 2024-04-01 | 2024-05-01 | 2024-05-01 | GoP | 200000 | 200000
320101100001000 | Procurement of Seafoods | HFE | YES | Competitive Bidding | 2023-11-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | GoP | 1323000 | 1323000
320101100001000 | Procurement of Veggies/Fruits | HFE | YES | Competitive Bidding | 2023-11-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | GoP | 1177200 | 1177200
320101100001000 | Procurement of Frozen Goods/Meat | HFE | YES | Competitive Bidding | 2023-11-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | GoP | 1603000 | 1603000
320101100001000 | Procurement of Grocery Items | HFE | YES | Competitive Bidding | 2023-11-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | GoP | 1505280 | 1505280
320101100001000 | Procurement of Medicines and Medical Supplies | HFE | YES | Competitive Bidding | 2023-11-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | GoP | 1501065 | 1501065
320101100001000 | Procurement of Personal care products | HFE | NO | Competitive Bidding | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 2158400 | 2158400
320101100001000 | Procurement of Catering Services for activities in center | HFE | NO | NP-53.9 - Small Value Procurement | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 1692000 | 1692000
320101100001000 | Procurement of Printing Services for materials | HFE | NO | NP-53.9 - Small Value Procurement | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 355950 | 355950
320101100001000 | Procurement of Cookware and kitchen tools | HFE | NO | Shopping | 2024-04-01 | 2024-04-01 | 2024-05-01 | 2024-05-01 | GoP | 230300 | 230300
320101100001000 | Procurement of Cleaning and Janitorial supplies | HFE | NO | Shopping | 2024-04-01 | 2024-04-01 | 2024-05-01 | 2024-05-01 | GoP | 473400 | 473400
320101100001000 | Procurement of Telecommunication Services | HFE | NO | Direct Contracting | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 122400 | 122400
320101100001000 | Procurement of vehicle maintenance and repair services | HFE | NO | NP-53.9 - Small Value Procurement | 2024-04-01 | 2024-04-01 | 2024-05-01 | 2024-05-01 | GoP | 40000 | 40000
320101100001000 | Procurement of Air conditioning installation or maintenance or repair service | HFE | NO | NP-53.9 - Small Value Procurement | 2024-04-01 | 2024-04-01 | 2024-05-01 | 2024-05-01 | GoP | 30000 | 30000
320101100001000 | Procurement of Septic tanks | HFE | NO | NP-53.9 - Small Value Procurement | 2024-04-01 | 2024-04-01 | 2024-05-01 | 2024-05-01 | GoP | 50000 | 50000
320101100001000 | Procurement of Fire extinguisher inspection maintenance and repair service | HFE | NO | NP-53.9 - Small Value Procurement | 2024-04-01 | 2024-04-01 | 2024-05-01 | 2024-05-01 | GoP | 50000 | 50000
320101100001000 | Procurement of Assistive devices for clients | HFE | NO | NP-53.9 - Small Value Procurement | 2024-04-01 | 2024-04-01 | 2024-05-01 | 2024-05-01 | GoP | 240000 | 240000
320101100001000 | Health assistance vocational training services | HFE | NO | Shopping | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 82500 | 82500
320101100001000 | Procurement of Office furniture | HFE | NO | Shopping | 2024-04-01 | 2024-04-01 | 2024-05-01 | 2024-05-01 | GoP | 299500 | 299500
320101100001000 | Procurement of Office supplies | HFE | NO | Shopping | 2024-04-01 | 2024-04-01 | 2024-05-01 | 2024-05-01 | GoP | 619785 | 619785
320101100001000 | Procurement of Frozen Goods/Meat | HFW | YES | Competitive Bidding | 2023-11-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | GoP | 4389595 | 4389595
320101100001000 | Procurement of Fruits and Veggies | HFW | YES | Competitive Bidding | 2023-11-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | GoP | 1179020 | 1179020
320101100001000 | Procurement of Grocery Items | HFW | YES | Competitive Bidding | 2023-11-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | GoP | 3155170 | 3155170
320101100001000 | Procurement of Commercial Rice; 80% whole grains, 25 kls | HFW | YES | Competitive Bidding | 2023-11-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | GoP | 300000 | 300000
320101100001000 | Procurement of Apparels, Personal Effects & Toiletries | HFW | YES | Competitive Bidding | 2023-11-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | GoP | 1973950 | 1973950
320101100001000 | Procurement of Medicines and Medical Supplies | HFW | YES | Competitive Bidding | 2023-11-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | GoP | 1027365 | 1027365
320101100001000 | Procurement of Dental services | HFW | NO | NP-53.9 - Small Value Procurement | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | GoP | 90000 | 90000
320101100001000 | Procurement of Catering Services | HFW | NO | NP-53.9 - Small Value Procurement | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 655900 | 655900
320101100001000 | Procurement of Laboratory services | HFW | NO | NP-53.9 - Small Value Procurement | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | GoP | 56000 | 56000
320101100001000 | Procurement of Printing Services for materials | HFW | NO | NP-53.9 - Small Value Procurement | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | GoP | 294000 | 294000
320101100001000 | Procurement of Janitorial supplies | HFW | YES | Competitive Bidding | 2023-11-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | GoP | 1543450 | 1543450
320101100001000 | Procurement of Cooking gas refill and Gasoline | HFW | NO | NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | GoP | 400000 | 400000
320101100001000 | Procurement of Electronic Load for staffs | HFW | NO | Direct Contracting | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | GoP | 154800 | 154800
320101100001000 | Procurement of Aircon Maintenance and services | HFW | NO | NP-53.9 - Small Value Procurement | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | GoP | 140500 | 140500
320101100001000 | Procurement of Pest Control Services | HFW | NO | NP-53.9 - Small Value Procurement | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | GoP | 302513 | 302513
320101100001000 | Procurement of Septic Tanks services | HFW | NO | NP-53.9 - Small Value Procurement | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | GoP | 118800 | 118800
320101100001000 | Procurement of vehicle maintenance and repair services | HFW | NO | NP-53.9 - Small Value Procurement | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | GoP | 200000 | 200000
320101100001000 | Procurement of Vehicle Battery | HFW | NO | Shopping | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | GoP | 20000 | 20000
320101100001000 | Procurement of Catering services during meetings | RRCY | NO | NP-53.9 - Small Value Procurement | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 4003400 | 4003400
320101100001000 | Procurement of Training tools and starter kits for clients | RRCY | NO | Shopping | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 1995550 | 1995550
320101100001000 | Procurement of Training cost and materials | RRCY | NO | NP-53.9 - Small Value Procurement | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 810225 | 810225
320101100001000 | Procurement of Meals with Accommodation for meetings | RRCY | NO | NP-53.10 Lease of Real Property and Venue | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 1315000 | 1315000
320101100001000 | Procurement of Training materials | RRCY | NO | Shopping | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 30000 | 30000
320101100001000 | Procurement of Meat and poultry products | RRCY | YES | Competitive Bidding | 2023-11-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | GoP | 2234720 | 2234720
320101100001000 | Procurement of Meat and poultry products | RRCY | NO | Competitive Bidding | 2024-07-01 | 2024-07-01 | 2024-08-01 | 2024-08-01 | GoP | 2234720 | 2234720
320101100001000 | Procurement of Fruits and Veggies | RRCY | YES | Competitive Bidding | 2023-11-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | GoP | 888730 | 888730
320101100001000 | Procurement of Fruits and Veggies | RRCY | NO | Competitive Bidding | 2024-07-01 | 2024-07-01 | 2024-08-01 | 2024-08-01 | GoP | 888730 | 888730
320101100001000 | Procurement of Frozen Goods/Meat | RRCY | YES | Competitive Bidding | 2023-11-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | GoP | 699550 | 699550
320101100001000 | Procurement of Frozen Goods/Meat | RRCY | NO | Competitive Bidding | 2024-07-01 | 2024-07-01 | 2024-08-01 | 2024-08-01 | GoP | 699550 | 699550
320101100001000 | Procurement of Grocery Items | RRCY | YES | Competitive Bidding | 2023-11-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | GoP | 1662234 | 1662234
320101100001000 | Procurement of Grocery Items | RRCY | NO | Competitive Bidding | 2024-07-01 | 2024-07-01 | 2024-08-01 | 2024-08-01 | GoP | 1712459 | 1712459
320101100001000 | Procurement of Cooking Gas refill | RRCY | NO | Shopping | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 610000 | 610000
320101100001000 | Procurement of Gasoline and Fuel | RRCY | NO | Direct Contracting | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 520000 | 520000
320101100001000 | Procurement of Cleaning and Janitorial supplies | RRCY | NO | Shopping | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 332670 | 332670
320101100001000 | Procurement of Cleaning and Janitorial supplies | RRCY | NO | Shopping | 2024-07-01 | 2024-07-01 | 2024-08-01 | 2024-08-01 | GoP | 332670 | 332670
320101100001000 | Procurement of Clothing and Personal effects | RRCY | NO | Shopping | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 677340 | 677340
320101100001000 | Procurement of Bedding and Linnens | RRCY | NO | Shopping | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 482600 | 482600
320101100001000 | Procurement of Office Supplies and Equipment | RRCY | NO | Shopping | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 712491 | 712491
320101100001000 | Procurement of Telecommunication Services | RRCY | NO | Direct Contracting | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 126000 | 126000
320101100001000 | Procurement of Air conditioning installation or maintenance or repair service | RRCY | NO | NP-53.9 - Small Value Procurement | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 44000 | 44000
320101100001000 | Procurement of Meat and poultry products | RSCC | YES | Competitive Bidding | 2023-11-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | GoP | 1355100 | 1355100
320101100001000 | Procurement of Fruits and Veggies | RSCC | YES | Competitive Bidding | 2023-11-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | GoP | 625632 | 625632
320101100001000 | Procurement of Grocery Items | RSCC | YES | Competitive Bidding | 2023-11-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | GoP | 2147690 | 2147690
320101100001000 | Procurement of Medicines and Medical Supplies | RSCC | YES | Competitive Bidding | 2023-11-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | GoP | 131552 | 131552
320101100001000 | Procurement of Personal effects | RSCC | YES | Competitive Bidding | 2023-11-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | GoP | 1020800 | 1020800
320101100001000 | Procurement of Cleaning and Janitorial supplies | RSCC | YES | Competitive Bidding | 2023-11-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | GoP | 558200 | 558200
320101100001000 | Procurement of Powdered Milk | RSCC | NO | Shopping | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | GoP | 1913600 | 1913600
320101100001000 | Procurement of Cooking gas refill and Gasoline Fuel | RSCC | NO | NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 333400 | 333400
320101100001000 | Procurement of Telecommunication Services | RSCC | NO | Direct Contracting | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | GoP | 144000 | 144000
320101100001000 | Procurement of Occupational therapy services | RSCC | NO | NP-53.9 - Small Value Procurement | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 308000 | 308000
320101100001000 | Procurement of Vehicle batteries | RSCC | NO | Shopping | 2024-04-01 | 2024-04-01 | 2024-05-01 | 2024-05-01 | GoP | 19600 | 19600
320101100001000 | Procurement of Air conditioning installation or maintenance or repair service | RSCC | NO | NP-53.9 - Small Value Procurement | 2024-04-01 | 2024-04-01 | 2024-05-01 | 2024-05-01 | GoP | 19500 | 19500
320101100001000 | Procurement of Apparels for clients | RSCC | NO | Shopping | 2024-04-01 | 2024-04-01 | 2024-05-01 | 2024-05-01 | GoP | 309150 | 309150
320101100001000 | Procurement of School kits and educational toys for children | RSCC | NO | Shopping | 2024-07-01 | 2024-07-01 | 2024-08-01 | 2024-08-01 | GoP | 117650 | 117650
320101100001000 | Procurement of services for Septic tanks suction | RSCC | NO | NP-53.9 - Small Value Procurement | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | GoP | 150000 | 150000
320101100001000 | Procurement of Pest control | RSCC | NO | NP-53.9 - Small Value Procurement | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 45000 | 45000
320101100001000 | Procurement of Domestic kitchen supplies | RSCC | NO | Shopping | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | GoP | 47000 | 47000
320101100001000 | Catering Services for meetings | RSCC | NO | NP-53.9 - Small Value Procurement | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 875500 | 875500
320101100001000 | Procurement of Meals and Accommodation | RSCC | NO | NP-53.10 Lease of Real Property and Venue | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 211200 | 211200
320101100001000 | Procurement of Training and Advocacy materials | RSCC | NO | NP-53.9 - Small Value Procurement | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 212000 | 212000
320101100001000 | Procurement of prizes and awards | RSCC | NO | Shopping | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 211500 | 211500
320101100001000 | Procurement of Printing and Photographic and Audio and Visual Equipment and Supplies | RSCC | NO | Shopping | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | GoP | 47000 | 47000
320101100001000 | Procurement of Powdered Milk | RSCC | NO | Shopping | 2024-04-01 | 2024-04-01 | 2024-05-01 | 2024-05-01 | GoP | 1112280 | 1112280
320101100001000 | Catering Services for meetings | ORD | NO | NP-53.9 - Small Value Procurement | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | GoP | 344000 | 344000
320101100001000 | Procurement of Meals and Accommodation | ORD | NO | NP-53.10 Lease of Real Property and Venue | 2024-09-01 | 2024-09-01 | 2024-10-01 | 2024-10-01 | GoP | 126000 | 126000
320101100001000 | Procurement of Office Supplies and Equipment | ORD | NO | Shopping | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | GoP | 41758 | 41758
320101100001000 | Telecommunication Services | ORD | NO | Direct Contracting | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | GoP | 46800 | 46800
320101100001000 | Procurement of Meals and Accommodation | ARDO | NO | NP-53.10 Lease of Real Property and Venue | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | GoP | 50000 | 50000
320101100001000 | Telecommunication Services | ARDO | NO | Direct Contracting | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | GoP | 16800 | 16800
320101100001000 | Procurement of Office Supplies and Equipment | ARDO | NO | Shopping | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | GoP | 46250 | 46250
320101100001000 | Procurement of Meals and Accommodation | PSD Chief | NO | NP-53.10 Lease of Real Property and Venue | 2024-06-01 | 2024-06-01 | 2024-07-01 | 2024-07-01 | GoP | 440000 | 440000
320101100001000 | Procurement of Advocacy Shirt | PSD Chief | NO | NP-53.9 - Small Value Procurement | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | GoP | 5500 | 5500
320101100001000 | Procurement of Office Supplies and Equipment | PSD Chief | NO | Shopping | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | GoP | 264550 | 264550
320101100001000 | Telecommunication Services | PSD Chief | NO | Direct Contracting | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 21600 | 21600
320101100001000 | Procurement of Meals and Accommodation | SocPen | NO | NP-53.10 Lease of Real Property and Venue | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 854280 | 854280
320101100001000 | Procurement of Training and Advocacy materials | SocPen | NO | NP-53.9 - Small Value Procurement | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 1762500 | 1762500
320101100001000 | Procurement of Advocacy materials | SocPen | NO | Shopping | 2024-10-01 | 2024-10-01 | 2024-11-01 | 2024-11-01 | GoP | 110000 | 110000
320101100001000 | Procurement of Office Equipment and Supplies | SocPen | NO | Shopping | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | GoP | 1887500 | 1887500
320101100001000 | Telecommunication Services | SocPen | NO | Direct Contracting | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 418200 | 418200
320101100001000 | Procurement of Meals and Accommodation | RRPTP | NO | NP-53.10 Lease of Real Property and Venue | 2024-06-01 | 2024-06-01 | 2024-07-01 | 2024-07-01 | GoP | 201200 | 201200
320101100001000 | Procurement of Training and Advocacy materials | RRPTP | NO | NP-53.9 - Small Value Procurement | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | GoP | 200650 | 200650
320101100001000 | Procurement of Training supplies and materials | RRPTP | NO | Shopping | 2024-06-01 | 2024-06-01 | 2024-07-01 | 2024-07-01 | GoP | 16600 | 16600
320101100001000 | Catering Services for meetings | RRPTP | NO | NP-53.9 - Small Value Procurement | 2024-06-01 | 2024-06-01 | 2024-07-01 | 2024-07-01 | GoP | 120000 | 120000
320101100001000 | Telecommunication Services | RRPTP | NO | Direct Contracting | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | GoP | 21600 | 21600
320101100001000 | Procurement of Office supplies and Equipment | RRPTP | NO | Shopping | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | GoP | 97217 | 97217
350100100001000 | Procurement of Meals and Accommodation | TARA-FOCAL | NO | NP-53.10 Lease of Real Property and Venue | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | GoP | 455500 | 455500
350100100001000 | Procurement of Office Equipment and Supplies | TARA-FOCAL | NO | Shopping | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | GoP | 87200 | 87200
350100100001000 | Telecommunication Services | TARA-FOCAL | NO | Direct Contracting | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | GoP | 21600 | 21600
350100100001000 | Procurement of Office Equipment and Supplies | LEGAL UNIT | NO | Shopping | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | GoP | 11880 | 11880
350100100001000 | Telecommunication Services | LEGAL UNIT | NO | Direct Contracting | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | GoP | 25200 | 25200
350100100001000 | Procurement of Meals and Accommodation | SWADT ISABELA | NO | NP-53.10 Lease of Real Property and Venue | 2024-07-01 | 2024-07-01 | 2024-08-01 | 2024-08-01 | GoP | 30000 | 30000
350100100001000 | Procurement of Office Equipment and Supplies | SWADT ISABELA | NO | Shopping | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | GoP | 109506 | 109506
350100100001000 | Procurement of Office Equipment and Supplies | SWADT IPIL | NO | Shopping | 2024-09-01 | 2024-09-01 | 2024-10-01 | 2024-10-01 | GoP | 193223.23 | 193223.23
350100100001000 | Catering Services of meetings | SWADT DIPOLOG | NO | NP-53.9 - Small Value Procurement | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 44000 | 44000
350100100001000 | Procurement of Meals and Accommodation | SWADT DIPOLOG | NO | NP-53.10 Lease of Real Property and Venue | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 55000 | 55000
350100100001000 | Procurement of services for repair and maintenance | SWADT DIPOLOG | NO | NP-53.9 - Small Value Procurement | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 327594 | 327594
350100100001000 | Procurement of Office Equipment and Supplies | SWADT DIPOLOG | NO | Shopping | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 196352.7 | 196352.7
310100100001000 | Procurement of services printing of forms | PANTAWID | NO | NP-53.9 - Small Value Procurement | 2024-03-01 | 2024-03-01 | 2024-04-01 | 2024-04-01 | GoP | 954105 | 954105
310100100001000 | Procurement of Office supplies | PANTAWID | NO | Shopping | 2024-04-01 | 2024-04-01 | 2024-05-01 | 2024-05-01 | GoP | 2869862 | 2869862
310100100001000 | Procurement of Meals and Accommodation | PANTAWID | NO | NP-53.10 Lease of Real Property and Venue | 2024-04-01 | 2024-04-01 | 2024-05-01 | 2024-05-01 | GoP | 3476700 | 3476700
310100100001000 | Procurement of Air conditioning services | PANTAWID | NO | NP-53.9 - Small Value Procurement | 2024-04-01 | 2024-04-01 | 2024-05-01 | 2024-05-01 | GoP | 115998 | 115998
310100100001000 | Procurement of ICT Equipments | PANTAWID | NO | Shopping | 2024-04-01 | 2024-04-01 | 2024-05-01 | 2024-05-01 | GoP | 217000 | 217000
310100100001000 | Procurement of forms printing services | PANTAWID | NO | NP-53.9 - Small Value Procurement | 2024-04-01 | 2024-04-01 | 2024-05-01 | 2024-05-01 | GoP | 261875 | 261875
310100100001000 | Procurement of Telecommunication Services | PANTAWID | NO | Direct Contracting | 2024-02-01 | 2024-02-01 | 2024-03-01 | 2024-03-01 | GoP | 3414000 | 3414000 |  | THE PROCUREMENT PROJECTS IS SUBJECT TO RENEWAL (PER GPPB RESO. NO. 06-2022)
[8 empty] | GRAND TOTAL: |  |  | 176560888.7
Prepared By: |  |  |  | Recommended By: | [5 empty] | Approved By:
BRITANICO RAMOS |  |  |  | MARIA CORAZON G. SUMICAD | [5 empty] | RIDUAN P. HADJIMUDDIN, CESO IV
BAC Secretariat, Head |  |  |  | BAC Chairperson | [5 empty] | Regionl Director
Funds Allocated:
MARIA CORAZON G. SUMICAD
FMD Chief

## how_to_fill_out-definitions
| GUIDE TO PREPARE APP | APP COLUMN HEADER/S
STEP 1 | In the Code column, kindly indicate the PAP Code. Please refer to the code indicated in the technical budget posted in the DBM website. For GOCCs and LGUs, indicate the procuring entity's internal numbering system. | Code (PAP)
STEP 2 | For the Procurement Project column, please align descriptions of program/projects with budget documents and ensure clarity and accuracy in describing each procurement program/project. | Procurement Project
STEP 3 | For PMO/End-User, please indicate the PMO/End-User unit who will implement/utilize the procurement program/project. Multiple end-user units are allowed only if the procurement activity was consolidated by the BAC to procure requirements of the end-user units. | PMO/End-User
STEP 4 | For Mode of Procurement and Schedule for Each Procurement Activity, all modes of procurement are available as a dropdown list and requirements for a specific schedule for Ads/Post of IB/REI, Sub/Open of Bids, Notice of Award, and/or Contract Signing are automatically identified thru the MS Excel formula. Note that for Foreign-funded procurement, please use Others - Foreign-funded procurement as the Mode of Procurement. Kindly indicate a specific period (dates, month, quarter) when each Procurement Activity will be done. Please refer to our website: http://www.gppb.gov.ph/timelines/timelines.htm for the specific periods for each activity. Note: For SVP, IB/REI is similar to RFQ. Ads/Post of IB/REI for Shopping 52.1(b) and NP-SVP (53.9) needs to be posted in PhilGEPS for ABCs above 50k. Notice of Award posting in PhilGEPS is mandatory for all Alternative Modes only for ABCs above 50k. | Mode of Procurement | Schedule for Each Procurement Activity
|  |  | Ads/Post of IB/REI | Sub/Open of Bids | Notice of Award | Contract Signing
STEP 5 | For Source of Funds, a dropdown list is available. If the Source of Funds the PE will use is not included, please indicate "Others" and specify under the Remarks column. | Source of Funds
STEP 6 | For Estimated Budget (PhP), kindly fill out either MOOE or CO columns only. Total ABC column is not editable, but will automatically compute for the total MOOE and CO components of the project. This breakdown is needed for tracking purposes. Finally, please ensure that amounts indicated are aligned with budget documents. | Estimated Budget (PhP)
STEP 7 | Before submission to the GPPB, ensure that the Head of the Procuring Entity (HoPE) approves/signs the APP.
GENERAL INFORMATION
#1 | All Cells with Fill Color Orange needs to be filled out by the Agency. This is a visual reminder of blank or improperly filled out cells.
#2 | To ensure that automated indicator which procurement activity needs to be filled out with specific periods, PE must copy entire Excel row with the mode of procurement for the specific procurement program/project and paste on the last sample row "Negotiated Procurement-53.13" in the template.
#3 | If PE wishes to edit formatting and design of borders, fonts, among others of the APP template, it is suggested to utilize the automated formulas in the template before copying contents and reformatting.
#4 | Per Section of 3.1.1 of DBM Circular No. 2015-7, the Approved Budget for the Contract (ABC) shall be “[t]he amount reflected in the MYOA”. Hence, the ABC in the Annual Procurement Plan (APP) shall be the full amount stated in the MYOA with remarks added on how much will be actually disbursed for that particular fiscal year. Moreover, the Procurement Monitoring Report (PMR) should also reflect full amount in the MYOA if the entire contract was awarded within the fiscal year. Thus, for succeeding years, actual disbursements from the MYOA need not be reflected in the APPs and PMRs, unless current contract with MYOA is terminated and a new procurement activity is undertaken.
DEFINITIONS
1. PROGRAM (BESF)– A homogeneous group of activities necessary for the performance of a major purpose for which a government agency is established, for the basic maintenance of the agency’s administrative operations or for the provisions of staff support to the agency’s administrative operations or for the provisions of staff support to the agency’s line functions.
2. PROJECT (BESF)– Special agency undertakings which are to be carried out within a definite time frame and which are intended to result in some pre-determined measure of goods and services.
3. PMO/End User - Unit as proponent of program or project
4. Mode of Procurement - Competitive Bidding and Alternative Methods including: selective bidding, direct contracting, repeat order, shopping, and negotiated procurement.
5. Schedule for Each Procurement Activity - Major procurement activities (advertising/posting; submission and receipt/Opening of bids; award of contract; contract signing).
6. Source of Funds - Whether GoP, Foreign Assisted or Special Purpose Fund
7. Estimated Budget - Agency approved estimate of project/program costs
8. Remarks - brief description of program or project

## data_validation (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
Emergency Procurement under the Bayanihan Act
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets
Others - Foreign-funded procurement