## PMR
Department of Social Welfare and Development (DSWD) FIELD OFFICE -IX | [11 empty] | Procurement Monitoring Report as of July 1, 2023 to January 11, 2024
[5 empty] | Actual Procurement Activities | [20 empty] | ABC (PhP) |  |  | Contract Cost (PhP) |  |  |  |  | Date of Receipt of Invitation
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Ave. No. of Days to Commence Procurement (Pre-Proc to Posting of IB) (i.3) | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Average No. of Days to open bid proposals (Posting of IB to Opening of Bids) (i.4) | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Accumulated Days in Evaluation of Bids (Opening of Bids to Post Qua) | Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) (i.5) | Average Number of Days to Conclude Procurement (IB to BAC Reso) (i.6) | Notice of Award | Contract Signing | Notice to Proceed | Average Number of Days to Issue Notice to Proceed (NOA to NTP) (i.7) | Average Days from (Posting of IB to NTP) (i.8) | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | % Variance | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/ Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP) | Column1 | Column2
COMPLETED PROCUREMENT ACTIVITIES | [31 empty] | -
320101100001000 | Procurement of CY 2023 GROCERY ITEMS for the Consumption of DSWD FO IX- RRCY Clients for 2nd Semester of CY 2023 (ITB-2023-06-043) | Regional Rehabilitation Center for Youth (RRCY) | No | Competitive Bidding | 2023-06-13 | 2023-07-04 | 21 | 2023-07-13 | 2023-07-25 | 2023-07-25 | 21 | 2023-07-27 | 2023-08-01 | 2023-08-07 | 7 | 13 | 34 | 2023-08-14 | 2023-08-29 | 2023-08-31 | 17 | 58 |  |  | Government of the Philippines (current year's budget) | 1690730 | 1690730 |  | 1595410 | 1595410 |  | 0.056378 | (1.)Commission of Audit (COA), (2.)Zamboanga Chamber of Commerce and Industry Foundation, Inc. and (3.) Tzu Chi Foundation | 2023-07-06 | 2023-07-06 | 2023-07-06 | 2023-07-06 | 2023-07-27 |  |  | FALSE | FALSE
320101100001000 | Supply and Delivery of CY 2023 Fruits and Vegetables for the Consumption of DSWD FO IX RRCY Clients for 2nd Semester of CY-2023 (ITB-2023-06-044) | Regional Rehabilitation Center for Youth (RRCY) | No | Competitive Bidding | 2023-06-13 | 2023-07-04 |  | 2023-07-13 | 2023-07-25 | 2023-07-25 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |  | Government of the Philippines (current year's budget) | 1312241 | 1312241 |  | 0 |  |  |  | (1.)Commission of Audit (COA), (2.)Zamboanga Chamber of Commerce and Industry Foundation, Inc. and (3.) Tzu Chi Foundation | 2023-07-06 | 2023-07-06 | 2023-07-06 | 2023-07-06 |  | 2023-12-11 | Failed under Section 35.1 (a)
200000100001000 | Procurement of ICT Equipement Needed for Online Meeting and Other ICT Needs of the Region. | ICTMS | No | Competitive Bidding | 2023-05-25 | 2023-06-06 | 12 | 2023-07-11 | 2023-06-29 | 2023-06-29 | 23 | 2023-06-29 | 2023-07-10 | 2023-07-25 | 11 | 26 | 49 | 2023-07-29 | 2023-08-11 | 2023-08-16 | 18 | 71 | 2023-12-11 | 2023-12-11 | Government of the Philippines (current year's budget) | 4900000 |  | 4900000 | 4625000 |  | 4625000 | 0.056122 | (1.)Commission of Audit (COA), (2.)Zamboanga Chamber of Commerce and Industry Foundation, Inc. and (3.) Tzu Chi Foundation | 2023-06-09 | 2023-06-09 | 2023-06-09 | 2023-06-09 | 2023-06-29 |  |  | FALSE | FALSE
320101100001000 | Supply and Delivery of Frozen Goods for the consumption of Home for the Elderly Clients for July 2023 to January 2024 | Home for the Elderly (HFE) | No | Competitive Bidding | 2023-06-22 | 2023-07-02 | 10 | 2023-07-11 | 2023-07-26 | 2023-07-26 | 24 | 2023-07-27 | 2023-08-06 | 2023-08-08 | 11 | 13 | 37 | 2023-08-14 | 2023-08-29 | 2023-08-29 | 15 | 58 | 2023-10-24 | 2023-10-24 | Government of the Philippines (current year's budget) | 816050 | 816050 |  | 772000 | 772000 |  | 0.05398 | (1.)Commission of Audit (COA), (2.)Zamboanga Chamber of Commerce and Industry Foundation, Inc. and (3.) Tzu Chi Foundation | 2023-07-04 | 2023-07-04 | 2023-07-04 | 2023-07-04 | 2023-07-27 |  |  | FALSE | FALSE
320101100001000 | Supply and Delivery of GROCERY ITEMS for the consumption of Home for the Elderly Clients for July 2023 to January 2024 | Home for the Elderly (HFE) | No | Competitive Bidding | 2023-06-22 | 2023-07-02 |  | 2023-07-11 | 2023-07-26 | 2023-07-26 |  | 2023-07-27 | 2023-08-06 | 2023-08-08 |  |  |  | 2023-08-14 | 2023-08-29 | 2023-08-29 |  |  | 2023-12-05 | 2023-12-05 | Government of the Philippines (current year's budget) | 1662880 | 1662880 |  | 1400966 | 1400966 |  |  | (1.)Commission of Audit (COA), (2.)Zamboanga Chamber of Commerce and Industry Foundation, Inc. and (3.) Tzu Chi Foundation | 2023-07-04 | 2023-07-04 | 2023-07-04 | 2023-07-04 | 2023-07-27 |  |  | FALSE | FALSE
320101100001000 | Supply and Delivery of FRUITS AND VEGETABLES for the consumption of Home for the Elderly Clients for July 2023 to January 2024 | Home for the Elderly (HFE) | No | Competitive Bidding | 2023-06-22 | 2023-07-02 | 10 | 2023-07-11 | 2023-07-26 | 2023-07-26 | 24 | 2023-07-27 | 2023-08-06 | 2023-08-08 | 11 | 13 | 37 | 2023-08-14 | 2023-08-29 | 2023-08-29 | 15 | 58 | 2023-12-08 | 2023-12-08 | Government of the Philippines (current year's budget) | 635398 | 635398 |  | 627225 | 627225 |  | 0.012863 | (1.)Commission of Audit (COA), (2.)Zamboanga Chamber of Commerce and Industry Foundation, Inc. and (3.) Tzu Chi Foundation | 2023-07-04 | 2023-07-04 | 2023-07-04 | 2023-07-04 | 2023-07-27 |  |  | FALSE | FALSE
320101100001000 | Supply and Delivery of FISH and SHRIMPS for the consumption of Home for the Elderly Clients for July 2023 to January 2024 | Home for the Elderly (HFE) | No | Competitive Bidding | 2023-06-22 | 2023-07-02 | 10 | 2023-07-11 | 2023-07-26 | 2023-07-26 | 24 | 2023-07-27 | 2023-08-06 | 2023-08-08 | 11 | 13 | 37 | 2023-08-14 | 2023-08-29 | 2023-08-29 | 15 | 58 | 2023-10-17 | 2023-10-17 | Government of the Philippines (current year's budget) | 977600 | 977600 |  | 925000 | 925000 |  | 0.053805 | (1.)Commission of Audit (COA), (2.)Zamboanga Chamber of Commerce and Industry Foundation, Inc. and (3.) Tzu Chi Foundation | 2023-07-04 | 2023-07-04 | 2023-07-04 | 2023-07-04 | 2023-07-27 |  |  | FALSE | FALSE
320102100001000 | 2nd Public Bidding Supply and Delivery of Food Items for DSWD FO IX, SFP 13th Cycle Implementation in Isabela City (ITB-2023-07-050) | Supplementary Feeding Program (SFP) | No | Competitive Bidding | 2023-05-15 | 2023-07-04 |  | 2023-07-13 | 2023-07-25 | 2023-07-25 |  | 2023-07-27 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Government of the Philippines (current year's budget) | 6300000 | 6300000 |  | 0 |  |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | [6 empty] | Failed under Section 35.1 (a)
320102100001000 | 2nd Public Bidding Supply and Delivery of Commercial Rice for DSWD FO IX, SFP 13th Cycle Implementation in ZDN District I (ITB-2023-07-051) | Supplementary Feeding Program (SFP) | No | Competitive Bidding | 2023-05-15 | 2023-07-04 |  | 2023-07-13 | 2023-07-25 | 2023-07-25 |  | 2023-07-27 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Government of the Philippines (current year's budget) | 1972800 | 1972800 |  | 0 |  |  |  | (1.)Commission of Audit (COA), (2.)Zamboanga Chamber of Commerce and Industry Foundation, Inc. and (3.) Tzu Chi Foundation | [6 empty] | Failed under Section 35.1 (a)
320102100001000 | 2nd Public Bidding Supply and Delivery of Food Items for DSWD FO IX, SFP 13th Cycle Implementation in ZDN District I (ITB-2023-07-052) | Supplementary Feeding Program (SFP) | No | Competitive Bidding | 2023-05-15 | 2023-07-04 |  | 2023-07-13 | 2023-07-25 | 2023-07-25 |  | 2023-07-27 | 2023-08-01 | 2023-08-07 |  |  |  | 2023-08-14 | 2023-08-25 | 2023-08-29 |  |  | 2023-09-25 | 2023-09-25 | Government of the Philippines (current year's budget) | 7719120 | 7719120 |  | 6945247 | 6945247 |  |  | (1.)Commission of Audit (COA), (2.)Zamboanga Chamber of Commerce and Industry Foundation, Inc. and (3.) Tzu Chi Foundation | 2023-07-06 | 2023-07-06 | 2023-07-06 | 2023-07-06
320102100001000 | 2nd Public Bidding Supply and Delivery of Commercial Rice for DSWD FO IX, SFP 13th Cycle Implementation in ZDN District II (ITB-2023-07-053) | Supplementary Feeding Program (SFP) | No | Competitive Bidding | 2023-05-15 | 2023-07-04 | 50 | 2023-07-13 | 2023-07-25 | 2023-07-25 | 21 | 2023-07-27 | 2023-08-01 | 2023-08-07 | 7 | 13 | 34 | 2023-08-14 | 2023-08-25 | 2023-08-29 | 15 | 56 |  |  | Government of the Philippines (current year's budget) | 3260400 | 3260400 |  | 0 |  |  | - | (1.)Commission of Audit (COA), (2.)Zamboanga Chamber of Commerce and Industry Foundation, Inc. and (3.) Tzu Chi Foundation | 2023-07-06 | 2023-07-06 | 2023-07-06 | 2023-07-06 |  |  | Failed under Section 35.1 (a) | FALSE | FALSE
320102100001000 | 2nd Public Bidding Supply and Delivery of Food Items for DSWD FO IX, SFP 13th Cycle Implementation in ZDN District II (ITB-2023-06-054) | Supplementary Feeding Program (SFP) | No | Competitive Bidding | 2023-05-15 | 2023-07-04 | 50 | 2023-07-13 | 2023-07-25 | 2023-07-25 | 21 | 2023-07-27 | 2023-08-01 | 2023-08-07 | 7 | 13 | 34 | 2023-08-14 | 2023-08-25 | 2023-08-29 | 15 | 56 | 2023-09-26 | 2023-09-26 | Government of the Philippines (current year's budget) | 12761760 | 12761760 |  | 11482357 | 11482357 |  | 0.10025 | (1.)Commission of Audit (COA), (2.)Zamboanga Chamber of Commerce and Industry Foundation, Inc. and (3.) Tzu Chi Foundation | 2023-07-06 | 2023-07-06 | 2023-07-06 | 2023-07-06 |  |  |  | FALSE | FALSE
320102100001000 | Supply and Delivery of Commercial Rice for DSWD FO IX, SFP 13th Cycle Implementation in ZSP District I (ITB-2023-07-055) | Supplementary Feeding Program (SFP) | No | Competitive Bidding | 2023-05-15 | 2023-07-04 | 50 | 2023-07-13 | 2023-07-25 | 2023-07-25 | 21 | 2023-07-27 | 2023-08-01 | 2023-08-07 | 7 | 13 | 34 | 2023-08-14 | 2023-08-25 | 2023-08-29 | 15 | 56 | 2023-09-26 | 2023-09-26 | Government of the Philippines (current year's budget) | 3808350 | 3808350 |  | 3807672.96 | 3807672.96 |  | 0.00017778 | (1.)Commission of Audit (COA), (2.)Zamboanga Chamber of Commerce and Industry Foundation, Inc. and (3.) Tzu Chi Foundation | 2023-07-06 | 2023-07-06 | 2023-07-06 | 2023-07-06 |  |  |  | FALSE | FALSE
320102100001000 | 2nd Public Bidding Supply and Delivery of Food Items for DSWD FO IX, SFP 13th Cycle Implementation in ZDN District III (ITB-2023-07-056) | Supplementary Feeding Program (SFP) | No | Competitive Bidding | 2023-05-15 | 2023-07-04 | 50 | 2023-07-13 | 2023-07-25 | 2023-07-25 | 21 | 2023-07-27 | 2023-08-01 | 2023-08-07 | 7 | 13 | 34 | 2023-08-14 | 2023-08-25 | 2023-08-29 | 15 | 56 | 2023-09-29 | 2023-09-29 | Government of the Philippines (current year's budget) | 26408040 | 26408040 |  | 23760538 | 23760538 |  | 0.10025 | (1.)Commission of Audit (COA), (2.)Zamboanga Chamber of Commerce and Industry Foundation, Inc. and (3.) Tzu Chi Foundation | 2023-07-06 | 2023-07-06 | 2023-07-06 | 2023-07-06 |  |  |  | FALSE | FALSE
320102100001000 | 2nd Public Bidding Supply and Delivery of Commercial Rice for DSWD FO IX, SFP 13th Cycle Implementation in ZDN District III (ITB-2023-07-057) | Supplementary Feeding Program (SFP) | No | Competitive Bidding | 2023-05-15 | 2023-07-04 |  | 2023-07-13 | 2023-07-25 | 2023-07-25 |  | 2023-07-27 | 2023-08-01 | 2023-08-07 |  |  |  | 2023-08-14 | 2023-08-25 | 2023-08-29 |  |  | 2023-09-28 | 2023-09-28 | Government of the Philippines (current year's budget) | 6747600 | 6747600 |  | 6747600 | 6747600 |  |  | (1.)Commission of Audit (COA), (2.)Zamboanga Chamber of Commerce and Industry Foundation, Inc. and (3.) Tzu Chi Foundation | 2023-07-06 | 2023-07-06 | 2023-07-06 | 2023-07-06
320101100001000 | Construction of Skills Training Building Phase III at AVRC III, Mampang ZC (ITB-2023-07-058) | AVRC | No | Competitive Bidding | 2023-07-20 | 2023-07-25 |  | 2023-08-04 | 2023-08-16 | 2023-08-16 |  | 2023-08-22 | 2023-08-26 | 2023-10-01 |  |  |  | 2023-10-03 | 2023-11-03 | 2023-11-03 |  |  |  |  | Government of the Philippines (current year's budget) | 10000000 |  | 10000000 | 9428867.77 |  | 9428867.77 |  | 1. Commission of Audit (COA) (2.) PICE, (3.) National Contractors Asso. Of the Phil. Inc. (4.) Tzu Chi Foundation | 2023-07-28 | 2023-07-28 | 2023-07-28 | 2023-07-28 | 2023-08-23 |  | Ongoing Construction
320101100001000 | ITB-2023-07-059: Construction of Parking Area at Home for Women at Mampang, Zamboanga City | Home for Women (HFW) | No | Competitive Bidding | 2023-07-20 | 2023-07-25 |  | 2023-08-04 | 2023-08-16 | 2023-08-16 |  | 2023-08-22 | 2023-08-26 | 2023-09-29 |  |  |  | 2023-10-03 | 2023-10-25 | 2023-10-26 |  |  |  |  | Government of the Philippines (current year's budget) | 1763721.77 |  | 1763721.77 | 1693172.9 |  | 1693172.9 |  | 1. Commission of Audit (COA) (2.) PICE, (3.) National Contractors Asso. Of the Phil. Inc. (4.) Tzu Chi Foundation | 2023-07-28 | 2023-07-28 | 2023-07-28 | 2023-07-28 | 2023-08-23 |  | Ongoing Construction
320101100001000 | ITB-2023-07-060: Construction of Food and Non Food Storage with Clinic and Provision of Drainage Canal at BDSK, Anastacio polanco ZDN | BDSK | No | Competitive Bidding | 2023-07-20 | 2023-07-25 |  | 2023-08-04 | 2023-08-16 | 2023-08-16 |  | 2023-08-22 | 2023-08-26 | 2023-09-20 |  |  |  | 2023-10-03 | 2023-10-20 | 2023-10-26 |  |  |  |  | Government of the Philippines (current year's budget) | 5442184.74 |  | 5442184.74 | 4753068.91 |  | 4753068.91 |  | 1. Commission of Audit (COA) (2.) PICE, (3.) National Contractors Asso. Of the Phil. Inc. (4.) Tzu Chi Foundation | 2023-07-28 | 2023-07-28 | 2023-07-28 | 2023-07-28 | 2023-08-23 |  | Ongoing Construction
320101100001000 | ITB-2023-07-061: Construction of SPED Center Building and House Parent Quarter with Male and Female Comfort Room at RSCC, Mampang ZC | RSCC | No | Competitive Bidding | 2023-07-20 | 2023-07-25 |  | 2023-08-04 | 2023-08-16 | 2023-08-16 |  | 2023-08-22 | 2023-08-26 | 2023-09-29 |  |  |  | 2023-10-03 | 2023-10-25 | 2023-10-26 |  |  |  |  | Government of the Philippines (current year's budget) | 4000000 |  | 4000000 | 3840000 |  | 3840000 |  | 1. Commission of Audit (COA) (2.) PICE, (3.) National Contractors Asso. Of the Phil. Inc. (4.) Tzu Chi Foundation | 2023-07-28 | 2023-07-28 | 2023-07-28 | 2023-07-28 | 2023-08-23 |  | Ongoing Construction
320101100001000 | ITB-2023-07-062: Procurement of Powerhouse with Provision of Generator Set at Home for the Elderly, Mampang ZC | Home for the Elderly (HFE) | No | Competitive Bidding | 2023-07-20 | 2023-07-25 |  | 2023-08-04 | 2023-08-16 | 2023-08-16 |  | 2023-08-22 | 2023-08-26 | 2023-09-16 |  |  |  | 2023-09-29 | [6 empty] | Government of the Philippines (current year's budget) | 2500000 |  | 2500000 | 2249661.09 |  | 2249661.09 |  | 1. Commission of Audit (COA) (2.) PICE, (3.) National Contractors Asso. Of the Phil. Inc. (4.) Tzu Chi Foundation | 2023-07-28 | 2023-07-28 | 2023-07-28 | 2023-07-28 | 2023-08-23 |  | Ongoing Construction
| ITB-2023-07-063: labor and Materials for the Proposed Construction of Multi-Purpose Covered Court at DSWD Compound, Mampang Zamboanga City | CRCF | No | Competitive Bidding | 2023-07-20 | 2023-07-25 |  | 2023-08-04 | 2023-08-16 | 2023-08-16 |  | 2023-08-22 | 2023-08-26 | 2023-09-18 |  |  |  | 2023-10-03 | 2023-10-19 | 2023-10-19 |  |  |  |  | Government of the Philippines (current year's budget) | 4235332.03 |  | 4235332.03 | 3739493.63 |  | 3739493.63 |  | 1. Commission of Audit (COA) (2.) PICE, (3.) National Contractors Asso. Of the Phil. Inc. (4.) Tzu Chi Foundation | 2023-07-28 | 2023-07-28 | 2023-07-28 | 2023-07-28 | 2023-08-23 |  | Ongoing Construction
320101100001000 | ITB-2023-07-064: labor and Materials for the Construction of Infirmary/Clinic at RRCY, Anastacio Polanco, Zamboanga del Norte | Regional Rehabilitation Center for Youth (RRCY) | No | Competitive Bidding | 2023-07-20 | 2023-07-25 |  | 2023-08-04 | 2023-08-16 | 2023-08-16 |  | 2023-08-22 | 2023-08-26 | 2023-09-16 |  |  |  | 2023-09-29 | 2023-10-17 | 2023-10-18 |  |  |  |  | Government of the Philippines (current year's budget) | 1549003.81 |  | 1549003.81 | 1343282.02 |  | 1343282.02 |  | 1. Commission of Audit (COA) (2.) PICE, (3.) National Contractors Asso. Of the Phil. Inc. (4.) Tzu Chi Foundation | 2023-07-28 | 2023-07-28 | 2023-07-28 | 2023-07-28 | 2023-08-23 |  | Ongoing Construction
320101100001000 | ITB-2023-07-065: Labor and Materials for the Upgrading of Skills Training Center at BDSK, Anastacio Polanco, Zamboanga del Norte | BDSK | No | Competitive Bidding | 2023-07-20 | 2023-07-25 |  | 2023-08-04 | 2023-08-16 | 2023-08-16 |  | 2023-08-22 | 2023-08-26 | 2023-09-16 |  |  |  | 2023-09-29 | 2023-10-17 | 2023-10-18 |  |  |  |  | Government of the Philippines (current year's budget) | 1990615.98 |  | 1990615.98 | 1707621.39 |  | 1707621.39 |  | 1. Commission of Audit (COA) (2.) PICE, (3.) National Contractors Asso. Of the Phil. Inc. (4.) Tzu Chi Foundation | 2023-07-28 | 2023-07-28 | 2023-07-28 | 2023-07-28 | 2023-08-23 |  | Ongoing Construction
320101100001000 | ITB-2023-08-066: Procurement of Services and Materials (works) for the Construction of Perimeter Fence with Steel Gate and Guard House @ HFW, of DSWD Field Office IX (ABC: PHP 5,008,117.61) | Home for Women (HFW) | No | Competitive Bidding | 2023-08-09 | 2023-08-14 |  | 2023-08-23 | 2023-09-04 | 2023-09-04 |  | 2023-09-07 | 2023-09-12 | 2023-09-25 |  |  |  | 2023-10-23 | 2023-11-08 | 2023-11-10 |  |  |  |  | Government of the Philippines (current year's budget) | 5008117.61 |  | 5008117.61 | 4201902.78 |  | 4201902.78 |  | 1. Commission of Audit (COA) (2.) PICE, (3.) National Contractors Asso. Of the Phil. Inc. (4.) Tzu Chi Foundation | 2023-08-17 | 2023-08-17 | 2023-08-17 | 2023-08-17 | 2023-09-11 |  | Ongoing Construction
320101100001000 | ITB-2023-08-067: Procurement of Services and Materials (works) for the Construction of Perimeter Fence with Guard House @PCDP, of DSWD Field Office IX (ABC: PHP 2,776,346.27) | PCDP | No | Competitive Bidding | 2023-08-09 | 2023-08-14 |  | 2023-08-23 | 2023-09-04 | 2023-09-04 |  | 2023-09-07 | 2023-09-12 | 2023-10-02 |  |  |  | 2023-10-23 | 2023-11-06 | 2023-11-06 |  |  |  |  | Government of the Philippines (current year's budget) | 2776346.27 |  | 2776346.27 | 2262389.93 |  | 2262389.93 |  | 1. Commission of Audit (COA) (2.) PICE, (3.) National Contractors Asso. Of the Phil. Inc. (4.) Tzu Chi Foundation | 2023-08-17 | 2023-08-17 | 2023-08-17 | 2023-08-17 | 2023-09-11 |  | Ongoing Construction
320101100001000 | ITB-2023-08-068: Procurement of Services and Materials (works) for the Construction of Drainage Canal @ RRCY, of DSWD Field Office IX (ABC: PHP 1,280,848.73) | RRCY | No | Competitive Bidding | 2023-08-09 | 2023-08-14 |  | 2023-08-23 | 2023-09-04 | 2023-09-04 |  | 2023-09-07 | 2023-09-12 | 2023-09-29 |  |  |  | 2023-10-20 | 2023-11-08 | 2023-11-10 |  |  |  |  | Government of the Philippines (current year's budget) | 1280848.73 |  | 1280848.73 | 1046189.51 |  | 1046189.51 |  | 1. Commission of Audit (COA) (2.) PICE, (3.) National Contractors Asso. Of the Phil. Inc. (4.) Tzu Chi Foundation | 2023-08-17 | 2023-08-17 | 2023-08-17 | 2023-08-17 | 2023-09-11 |  | Ongoing Construction
320101100001000 | ITB-2023-08-069: Procurement of Services and Materials (works) for the Construction of Warehouse @RRCY of DSWD Field Office IX ABC: PHP 7,352,097.23) | RRCY | No | Competitive Bidding | 2023-08-09 | 2023-08-14 |  | 2023-08-23 | 2023-09-04 | 2023-09-04 |  | 2023-09-07 | 2023-09-12 | 2023-10-23 |  |  |  | 2023-11-06 | 2023-11-20 | 2023-11-21 |  |  |  |  | Government of the Philippines (current year's budget) | 7352097.23 |  | 7352097.23 | 6065923.24 |  | 6065923.24 |  | 1. Commission of Audit (COA) (2.) PICE, (3.) National Contractors Asso. Of the Phil. Inc. (4.) Tzu Chi Foundation | 2023-08-17 | 2023-08-17 | 2023-08-17 | 2023-08-17 | 2023-09-11 |  | Ongoing Construction
320103100001000 | ITB-2023-08-070-Procurement of ICT Equipments for the use of DSWD FOIX Social Pension Staff | Social Pension | No | Competitive Bidding | 2023-08-30 | 2023-09-02 |  | 2023-09-15 | 2023-09-26 | 2023-09-26 |  | 2023-09-26 | 2023-10-13 | 2023-10-27 |  |  |  | 2023-11-06 | 2023-12-04 | 2023-12-11 |  |  |  |  | Government of the Philippines (current year's budget) | 2634968 |  | 2634968 | 2555000 | 2555000 |  |  | (1.)Commission of Audit (COA), (2.)Zamboanga Chamber of Commerce and Industry Foundation, Inc. and (3.) Tzu Chi Foundation | 2023-09-07 | 2023-09-07 | 2023-09-07 | 2023-09-07 | 2023-10-11
310100100001000 | ITB-2023-08-071: Procurement of Laptop Computers for the use of DSWD FOIX City/Municipal Link Staff (ITB-2023-08-071) | 4Ps | No | Competitive Bidding | 2023-09-15 | 2023-09-19 |  | 2023-09-29 | 2023-10-11 | 2023-10-11 |  | 2023-10-11 | 2023-10-21 | 2023-11-13 |  |  |  | 2023-11-20 | 2023-12-11 | 2023-12-11 |  |  |  |  | Government of the Philippines (current year's budget) | 36511293 |  | 36511293 | 24897600 | 24897600 |  |  | (1.)Commission of Audit (COA), (2.)Zamboanga Chamber of Commerce and Industry Foundation, Inc. and (3.) Tzu Chi Foundation | 2023-09-22 | 2023-09-22 | 2023-09-22 | 2023-09-22 | 2023-10-17
320102100001000 | Procurement of Food Items for DSWD FOIX SFP 13th Cycle Zamboanga CIty (ITB-2023-09-072) | Supplementary Feeding Program (SFP) | No | Competitive Bidding | 2023-09-15 | 2023-09-19 |  | 2023-09-29 | 2023-10-11 | 2023-10-11 |  | 2023-10-11 | 2023-10-18 | 2023-10-13 |  |  |  | 2023-11-06 | 2023-11-30 | 2023-12-01 |  |  |  |  | Government of the Philippines (current year's budget) | 33623693 | 33623693 |  | 29166623.4 | 29166623.4 |  |  | (1.)Commission of Audit (COA), (2.)Zamboanga Chamber of Commerce and Industry Foundation, Inc. and (3.) Tzu Chi Foundation | 2023-09-22 | 2023-09-22 | 2023-09-22 | 2023-09-22 | 2023-10-13
320105100002000 | Construction of Two-Storey Male Dormitory Building at PCDP, Zamboanga City ITB-2023-09-073 | PCDP | No | Competitive Bidding | 2023-09-15 | 2023-09-19 |  | 2023-10-02 | 2023-10-16 | 2023-10-16 |  | 2023-10-24 | 2023-11-03 | 2023-11-12 |  |  |  | 2023-11-20 | 2023-12-12 | 2023-12-13 |  |  |  |  | Government of the Philippines (current year's budget) | 20535789.25 |  | 20535789.25 | 16349692.21 |  | 16349692.21 |  | 1. Commission of Audit (COA) (2.) PICE, (3.) National Contractors Asso. Of the Phil. Inc. (4.) Tzu Chi Foundation | 2023-09-22 | 2023-09-22 | 2023-09-22 | 2023-09-22 | 2023-10-28 |  | Ongoing Construction
320105100002000 | Construction of Covered Pathwalk at PCDP, Zamboanga City ITB-2023-09-074 | PCDP | No | Competitive Bidding | 2023-09-15 | 2023-09-19 | 4 | 2023-10-02 | 2023-10-16 | 2023-10-16 | 27 | 2023-10-24 | 2023-10-27 | 2023-11-12 | 11 | 27 | 54 | 2023-11-20 | 2023-12-15 | 2023-12-15 | 25 | 87 |  |  | Government of the Philippines (current year's budget) | 3638852.13 |  | 3638852.13 | 2792882.71 |  | 2792882.71 | 0.23248 | 1. Commission of Audit (COA) (2.) PICE, (3.) National Contractors Asso. Of the Phil. Inc./Los Contratistas, Zamboanga Chapter (4.) Tzu Chi Foundation | 2023-09-22 | 2023-09-22 | 2023-09-22 | 2023-09-22 | 2023-10-24 |  | Ongoing Construction | FALSE | FALSE
320101100001000 | Land Development and Installation of Covered Pathwalk from Admin Building to Garage at HFW, Zamboanga City ITB-2023-09-075 | Home for Women (HFW) | No | Competitive Bidding | 2023-09-15 | 2023-09-19 | 4 | 2023-10-02 | 2023-10-16 | 2023-10-16 | 27 | 2023-10-24 | 2023-11-03 | 2023-11-12 | 18 | 27 | 54 | 2023-11-20 | 2023-12-13 | 2023-12-13 | 23 | 85 |  |  | Government of the Philippines (current year's budget) | 7449952.96 |  | 7449952.96 | 5849859.58 |  | 5849859.58 | 0.21478 | 1. Commission of Audit (COA) (2.) PICE, (3.) National Contractors Asso. Of the Phil. Inc./Los Contratistas, Zamboanga Chapter (4.) Tzu Chi Foundation | 2023-09-22 | 2023-09-22 | 2023-09-22 | 2023-09-22 | 2023-10-28 |  | Ongoing Construction | FALSE | FALSE
320101100001000 | Upgrading of Admin Building with Sprinkler System at BDSK, Polanco, ZDN ITB-2023-09-076. | BDSK | No | Competitive Bidding | 2023-09-15 | 2023-09-19 | 4 | 2023-10-02 | 2023-10-16 | 2023-10-16 | 27 | 2023-10-24 | 2023-10-27 | 2023-11-12 | 11 | 27 | 54 | 2023-11-24 | 2023-12-21 | [5 empty] | Government of the Philippines (current year's budget) | 2685877.57 |  | 2685877.57 | 2383893.17 |  | 2383893.17 | 0.11243 | 1. Commission of Audit (COA) (2.) PICE, (3.) National Contractors Asso. Of the Phil. Inc./Los Contratistas, Zamboanga Chapter (4.) Tzu Chi Foundation | 2023-09-22 | 2023-09-22 | 2023-09-22 | 2023-09-22 | 2023-10-24 |  | Ongoing Construction
| ITB-2023-10-080: Labor and Materials for the Construction of Concrete Driveways and Covered Pathwalk with Lightings and Landscaping at RSCC, Mampang Zamboanga City. | CRCF | No | Competitive Bidding | 2023-10-20 | 2023-10-31 |  | 2023-11-07 | 2023-11-23 | 2023-11-23 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | Government of the Philippines (current year's budget) | 2800000 |  | 2800000 | 0 |  |  |  | 1. Commission of Audit (COA) (2.) PICE, (3.) National Contractors Asso. Of the Phil. Inc. (4.) Tzu Chi Foundation | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-10-31 | N/A |  | Failed under Section 41 (b)
320102100001000 | SFP-2023-08-816-NP: PROC. OF FOOD STUFF FOR SFP 13th CYCLE IMPLEMENTATION IN ISABELA CITY | Supplementary Feeding Program (SFP) | No | NP-53.1 Two Failed Biddings | 2023-05-15 | 2023-08-11 |  | 2023-08-15 | 2023-08-18 | 2023-08-18 |  | 2023-08-18 | N/A | 2023-08-24 |  |  |  | 2023-08-28 | 2023-09-20 | 2023-09-21 |  |  |  |  | Government of the Philippines (current year's budget) | 6300000 | 6300000 |  | 6246337.32 | 6246337.32 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2023-08-11 | 2023-08-11 | 2023-08-11 | 2023-08-11
320102100001000 | SFP-2023-08-824-NP: PROC. OF COMMERCIAL RICE FOR SFP 13th CYCLE IMPLEMENTATION IN ZAMBOANGA DEL NORTE DISTRICT 1 | Supplementary Feeding Program (SFP) | No | NP-53.1 Two Failed Biddings | 2023-05-15 | 2023-08-11 | 88 | 2023-08-15 | 2023-08-18 | 2023-08-18 | 7 | 2023-08-18 | N/A | 2023-08-24 |  | 6 | 13 | 2023-08-28 | 2023-09-21 | 2023-09-21 | 24 | 41 |  |  | Government of the Philippines (current year's budget) | 1972800 | 1972800 |  | 1956360 | 1956360 |  | 0.0083333 | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2023-08-11 | 2023-08-11 | 2023-08-11 | 2023-08-11 |  |  |  | FALSE | FALSE
320102100001000 | SFP-2023-08-826-NP: PROC. OF COMMERCIAL RICE FOR SFP 13th CYCLE IMPLEMENTATION IN ZAMBOANGA DEL NORTE DISTRICT 2 | Supplementary Feeding Program (SFP) | No | NP-53.1 Two Failed Biddings | 2023-05-15 | 2023-08-11 | 88 | 2023-08-15 | 2023-08-18 | 2023-08-18 | 7 | 2023-08-18 | N/A | 2023-08-24 |  | 6 | 13 | 2023-08-28 | 2023-09-21 | 2023-09-21 | 24 | 41 |  |  | Government of the Philippines (current year's budget) | 3260400 | 3260400 |  | 3233230 | 3233230 |  | 0.0083333 | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2023-08-11 | 2023-08-11 | 2023-08-11 | 2023-08-11 |  |  |  | FALSE | FALSE
[25 empty] | Total Allotted Budget of Procurement Activities | 250284863.1 | 121229862 | 129055001.1 |  |  |  | 19.91%
[25 empty] | Total Contract Price of Procurement Activities Conducted |  |  |  | 200452067.5 | 126119166.7 | 74332900.84
[25 empty] | Total Savings (Total Allotted Budget - Total Contract Price) | 49832795.56 | [14 empty] | 2023-06-30
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Ave. No. of Days to Commence Procurement (Pre-Proc to Posting of IB) (i.3) | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Average No. of Days to open bid proposals (Posting of IB to Opening of Bids) (i.4) | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Accumulated Days in Evaluation of Bids (Opening of Bids to Post Qua) | Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) (i.5) | Average Number of Days to Conclude Procurement (IB to BAC Reso) (i.6) | Notice of Award | Contract Signing | Notice to Proceed | Average Number of Days to Issue Notice to Proceed (NOA to NTP) (i.7) | Average Days from (Posting of IB to NTP) (i.8) | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | % Variance | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP) | Column42
ONGOING PROCUREMENT ACTIVITIES | [31 empty] | -
320101100001000 | EPAITB-2024-01-001: Procurement of CY 2024 Food Stuff (Grocery Items) for the Clients of RSCC - DSWD FOIX - Centers and Institutions (EPA) under (Framework Agreement) | Reception Study Center for Center (RSCC) | Yes | Competitive Bidding | 2023-11-06 | 2023-11-14 | 8 | 2023-11-21 | 2023-12-04 | 2023-12-04 | 20 | 2023-12-05 | 2023-12-11 | 2023-12-20 | 7 | 16 | 36 | 2024-01-11 | [6 empty] | Government of the Philippines (current year's budget) | 2072594 | 2072594 |  | 1972985 | 1972985 |  | 0.04806 | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-12-05 |  | On-Going Contract Review | 0
320101100001000 | EPAITB-2024-01-002: Procurement of CY 2024 Food Stuff (Frozen Goods) for the Clients of RSCC - DSWD FOIX - Centers and Institutions (EPA) | Reception Study Center for Center (RSCC) | Yes | Competitive Bidding | 2023-11-06 | 2023-11-14 | 8 | 2023-11-21 | 2023-12-04 | 2023-12-04 | 20 | 2023-12-05 | 2023-12-11 | 2023-12-20 | 7 | 16 | 36 | 2024-01-11 | [6 empty] | Government of the Philippines (current year's budget) | 1385490 | 1385490 |  | 1385490 | 1385490 |  | 0% | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-12-05 |  | On-Going Contract Review | 0
320101100001000 | EPAITB-2024-01-003: Procurement of CY 2024 Food Stuff (Fruits & Vegetables) for the Clients of RSCC - DSWD FOIX - Centers and Institutions (EPA) | Reception Study Center for Center (RSCC) | Yes | Competitive Bidding | 2023-11-06 | 2023-11-14 |  | 2023-11-21 | 2023-12-04 | 2023-12-04 |  | 2023-12-05 | 2023-12-11 | 2023-12-20 |  |  |  | 2024-01-11 | [6 empty] | Government of the Philippines (current year's budget) | 0 |  |  | 0 |  |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-11-15 | n/a |  | Cancelled
320101100001000 | EPAITB-2024-01-004: Procurement of CY 2024 Common Janitorial Supplies for RSCC - DSWD FOIX - Centers and Institutions (EPA) | Reception Study Center for Center (RSCC) | Yes | Competitive Bidding | 2023-11-06 | 2023-11-14 |  | 2023-11-21 | 2023-12-04 | 2023-12-04 |  | 2023-12-05 | 2023-12-11 | 2023-12-20 |  |  |  | 2024-01-11 | [6 empty] | Government of the Philippines (current year's budget) | 0 |  |  | 0 |  |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-11-15 | n/a |  | Cancelled
320101100001000 | EPAITB-2024-01-005: Procurement of CY 2024 Drugs, Medicines & Medical Supplies for the Clients of RSCC - DSWD FOIX - Centers and Institutions (EPA) | Reception Study Center for Center (RSCC) | Yes | Competitive Bidding | 2023-11-06 | 2023-11-14 |  | 2023-11-21 | 2023-12-04 | 2023-12-04 |  | 2023-12-05 | 2023-12-11 | 2023-12-20 |  |  |  | 2024-01-11 | [6 empty] | Government of the Philippines (current year's budget) | 590522 | 590522 |  | 545674.6 | 545674.6 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-12-05 |  | On-Going Contract Review
320101100001000 | EPAITB-2024-01-006: Procurement of CY 2024 Personal Care Products for the use of RSCC Clients of DSWD FOIX - Centers and Institutions (EPA) | Reception Study Center for Center (RSCC) | Yes | Competitive Bidding | 2023-11-06 | 2023-11-14 |  | 2023-11-21 | 2023-12-04 | 2023-12-04 |  | 2023-12-05 | 2023-12-11 | 2023-12-20 |  |  |  | 2024-01-11 | [6 empty] | Government of the Philippines (current year's budget) | 976800 | 976800 |  | 852625 | 852625 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-12-05 |  | On-Going Contract Review
320101100001000 | EPAITB-2024-01-007: Procurement of CY 2024 Food Stuff (Frozen Goods) for the Home for Women Clients of DSWD FOIX - Centers and Institutions (EPA) | Home for Women (HFW) | Yes | Competitive Bidding | 2023-11-06 | 2023-11-14 |  | 2023-11-21 | 2023-12-04 | 2023-12-04 |  | 2023-12-05 | 2023-12-11 | 2023-12-20 |  |  |  | 2024-01-11 | [6 empty] | Government of the Philippines (current year's budget) | 0 |  |  | 0 |  |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-11-15 | n/a |  | Cancelled
320101100001000 | EPAITB-2024-01-008: Procurement of CY 2024 Food Stuff (Fruits & Vegetables) for the Clients of Home for Women - DSWD FOIX - Centers and Institutions (EPA) | Home for Women (HFW) | Yes | Competitive Bidding | 2023-11-06 | 2023-11-14 |  | 2023-11-21 | 2023-12-04 | 2023-12-04 |  | 2023-12-05 | 2023-12-11 | 2023-12-20 |  |  |  | 2024-01-11 | [6 empty] | Government of the Philippines (current year's budget) | 1268940 | 1268940 |  | 1268940 | 1268940 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-12-05 |  | On-Going Contract Review
320101100001000 | EPAITB-2024-01-009: Procurement of CY 2024 Food Stuff (Grocery Items) for the Clients of Home for Women - DSWD FOIX - Centers and Institutions (EPA) | Home for Women (HFW) | Yes | Competitive Bidding | 2023-11-06 | 2023-11-14 |  | 2023-11-21 | 2023-12-04 | 2023-12-04 |  | 2023-12-05 | 2023-12-11 | 2023-12-20 |  |  |  | 2024-01-11 | [6 empty] | Government of the Philippines (current year's budget) | 3249700 | 3249700 |  | 2824850 | 2824850 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-12-05 |  | On-Going Contract Review
320101100001000 | EPAITB-2024-01-010: Procurement of CY 2024 Common Janitorial Supplies for the use of Home for Women - DSWD FOIX - Centers and Institutions (EPA) | Home for Women (HFW) | Yes | Competitive Bidding | 2023-11-06 | 2023-11-14 |  | 2023-11-21 | 2023-12-04 | 2023-12-04 |  | 2023-12-05 | 2023-12-11 | 2023-12-20 |  |  |  | 2024-01-11 | [6 empty] | Government of the Philippines (current year's budget) | 911830 | 911830 |  | 848472 | 848472 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-12-05 |  | On-Going Contract Review
320101100001000 | EPAITB-2024-01-011: Procurement of CY 2024 Personal Care Products, Toiletries, & Apparels for the use of Home for Women Clients of DSWD FOIX - Centers and Institutions (EPA) | Home for Women (HFW) | Yes | Competitive Bidding | 2023-11-06 | 2023-11-14 |  | 2023-11-21 | 2023-12-04 | 2023-12-04 |  | 2023-12-05 | 2023-12-11 | 2023-12-20 |  |  |  | 2024-01-11 | [6 empty] | Government of the Philippines (current year's budget) | 1088520 | 1088520 |  | 1048985 | 1048985 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-12-05 |  | On-Going Contract Review
320101100001000 | EPAITB-2024-01-012: Procurement of CY 2024 Drugs & Medicines for the clients of Home for Women - DSWD FOIX - Centers and Institutions (EPA) | Home for Women (HFW) | Yes | Competitive Bidding | 2023-11-06 | 2023-11-14 |  | 2023-11-21 | 2023-12-04 | 2023-12-04 |  | 2023-12-05 | 2023-12-11 | 2023-12-20 |  |  |  | 2024-01-11 | [6 empty] | Government of the Philippines (current year's budget) | 502288.75 | 502288.75 |  | 487457.05 | 487457.05 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-12-05 |  | On-Going Contract Review
320101100001000 | EPAITB-2024-01-013: Procurement of CY 2023 Brand New Vehicle Tires for DSWD FOIX & Centers and Institutions (EPA) | Gen. Services Section | Yes | Competitive Bidding | 2023-11-08 | 2023-11-14 |  | 2023-11-21 | 2023-12-04 | 2023-12-04 |  | 2023-12-05 | 2023-12-11 | 2023-12-20 |  |  |  | 2024-01-11 | [6 empty] | Government of the Philippines (current year's budget) | 1746800 | 1746800 |  | 1650000 | 1650000 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-12-05 |  | On-Going Contract Review
320101100001000 | EPAITB-2024-01-014: Procurement of CY 2024 Food Stuff (Grocery Items) for the Clients of Home for the Elderly - DSWD FOIX - Centers and Institutions (EPA) | Home for the Elderly (HFE) | Yes | Competitive Bidding | 2023-11-06 | 2023-11-14 |  | 2023-11-22 | 2023-12-05 | 2023-12-05 |  | 2023-12-05 | 2023-12-11 | 2023-12-20 |  |  |  | 2024-01-11 | [6 empty] | Government of the Philippines (current year's budget) | 1385100 | 1385100 |  | 1281260 | 1281260 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-12-05
320101100001000 | EPAITB-2024-01-015: Procurement of CY 2024 Food Stuff (Frozen Goods) for the Clients of Home for the Elderly - DSWD FOIX - Centers and Institutions (EPA) | Home for the Elderly (HFE) | Yes | Competitive Bidding | 2023-11-06 | 2023-11-14 |  | 2023-11-22 | 2023-12-05 | 2023-12-05 |  | 2023-12-05 | 2023-12-11 | 2023-12-20 |  |  |  | 2024-01-11 | [6 empty] | Government of the Philippines (current year's budget) | 1162650 | 1162650 |  | 1089750 | 1089750 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-12-05
320101100001000 | EPAITB-2024-01-016: Procurement of CY 2024 Food Stuff (Fruits & Vegetables) for the Clients of Home for the Elderly - DSWD FOIX - Centers and Institutions (EPA) | Home for the Elderly (HFE) | Yes | Competitive Bidding | 2023-11-06 | 2023-11-14 |  | 2023-11-22 | 2023-12-05 | 2023-12-05 |  | 2023-12-05 | 2023-12-11 | 2023-12-20 |  |  |  | 2024-01-11 | [6 empty] | Government of the Philippines (current year's budget) | 764500 | 764500 |  | 730000 | 730000 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-12-05
320101100001000 | EPAITB-2024-01-017: Procurement of CY 2024 Personal Care Products, Toiletries, & Apparels for the use of Home for the Elderly Clients of DSWD FOIX - Centers and Institutions (EPA) | Home for the Elderly (HFE) | Yes | Competitive Bidding | 2023-11-06 | 2023-11-14 |  | 2023-11-22 | 2023-12-05 | 2023-12-05 |  | 2023-12-05 | 2023-12-11 | 2023-12-20 |  |  |  | 2024-01-11 | [6 empty] | Government of the Philippines (current year's budget) | 820400 | 820400 |  | 751910 | 751910 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-12-05
320101100001000 | EPAITB-2024-01-018: Public Bidding for the Procurement of CY 2024 Food Stuff (Sea Foods) for the Clients of Home for the Elderly - DSWD FOIX - Centers and Institutions (EPA) | Home for the Elderly (HFE) | Yes | Competitive Bidding | 2023-11-06 | 2023-11-14 |  | 2023-11-22 | 2023-12-05 | 2023-12-05 |  | 2023-12-05 | 2023-12-11 | 2023-12-20 |  |  |  | 2024-01-11 | [6 empty] | Government of the Philippines (current year's budget) | 907000 | 907000 |  | 857000 | 857000 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-12-05
320101100001000 | EPAITB-2024-01-019: Procurement of CY 2024 Drugs & Medicines for the clients of Home for the Elderly - DSWD FOIX - Centers and Institutions (EPA) | Home for the Elderly (HFE) | Yes | Competitive Bidding | 2023-11-06 | 2023-11-14 |  | 2023-11-22 | 2023-12-05 | 2023-12-05 |  | 2023-12-05 | 2023-12-11 | 2023-12-20 |  |  |  | 2024-01-11 | [6 empty] | Government of the Philippines (current year's budget) | 796490 | 796490 |  | 770954 | 770954 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-12-05
320101100001000 | EPAITB-2024-01-020: Procurement of CY 2024 Food Stuff (Grocery Items) for the Clients of RRCY - DSWD FOIX - Centers and Institutions (EPA) | Regional Rehabilitation Center for Youth (RRCY) | Yes | Competitive Bidding | 2023-11-06 | 2023-11-14 |  | 2023-11-22 | 2023-12-05 | 2023-12-05 |  | 2023-12-05 | 2023-12-11 | 2023-12-20 |  |  |  | N/A | N/A | N/A |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 0 |  |  | 0 |  |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-11-15 | n/a |  | Cancelled
320101100001000 | EPAITB-2024-01-021: Procurement of CY 2024 Food Stuff (Frozen Goods) for the Clients of RRCY - DSWD FOIX - Centers and Institutions (EPA) | Regional Rehabilitation Center for Youth (RRCY) | Yes | Competitive Bidding | 2023-11-06 | 2023-11-14 |  | 2023-11-22 | 2023-12-05 | 2023-12-05 |  | 2023-12-05 | 2023-12-11 | 2023-12-20 |  |  |  | N/A | N/A | N/A |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 0 |  |  | 0 |  |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-11-15 | n/a |  | Cancelled
320101100001000 | EPAITB-2024-01-022: Procurement of CY 2024 Food Stuff (Fruits & Vegetables) for the Clients of RRCY - DSWD FOIX - Centers and Institutions (EPA) | Regional Rehabilitation Center for Youth (RRCY) | Yes | Competitive Bidding | 2023-11-08 | 2023-11-14 |  | 2023-11-22 | 2023-12-05 | 2023-12-05 |  | 2023-12-05 | 2023-12-11 | 2023-12-20 |  |  |  | N/A | N/A | N/A |  |  | N/A | N/A | Government of the Philippines (current year's budget) | 0 |  |  | 0 |  |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-11-15 | n/a |  | Cancelled
320101100001000 | EPAITB-2024-01-023: Procurement of CY 2024 Food Stuff (Frozen Goods) for the Clients of BDSK - DSWD FOIX - Centers and Institutions (EPA) | Balay Dampanan sa Kabtaan (BDSK) | Yes | Competitive Bidding | 2023-11-06 | 2023-11-14 |  | 2023-11-22 | 2023-12-05 | 2023-12-05 |  | 2023-12-05 | 2023-12-11 | 2023-12-20 |  |  |  | 2024-01-11 | [6 empty] | Government of the Philippines (current year's budget) | 1070400 | 1070400 |  | 986650 | 986650 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-12-05
320101100001000 | EPAITB-2024-01-024: Procurement of CY 2024 Food Stuff (Grocery Items) for the Clients of BDSK - DSWD FOIX - Centers and Institutions (EPA) | Balay Dampanan sa Kabtaan (BDSK) | Yes | Competitive Bidding | 2023-11-06 | 2023-11-14 |  | 2023-11-22 | 2023-12-05 | 2023-12-05 |  | 2023-12-05 | 2023-12-11 | 2023-12-20 |  |  |  | 2024-01-11 | [6 empty] | Government of the Philippines (current year's budget) | 1449250 | 1449250 |  | 1359440 | 1359440 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-11-15 | 2023-12-05
320101100001000 | EPAITB-2024-01-025: Procurement of CY 2024 Food Stuff (Grocery Items) for the Clients of RRCY - DSWD FOIX - Centers and Institutions (EPA) | Regional Rehabilitation Center for Youth (RRCY) | Yes | Competitive Bidding | 2023-11-08 | 2023-11-23 |  | 2023-12-03 | 2023-12-15 | 2023-12-15 |  | 2023-12-15 | 2023-12-22 | 2023-12-29 |  |  |  | 2024-01-11 | [6 empty] | Government of the Philippines (current year's budget) | 2038932 | 2038932 |  | 1823168 | 1823168 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2023-11-29 | 2023-11-29 | 2023-11-29 | 2023-11-29 | 2023-12-16
320101100001000 | EPAITB-2024-01-026: Procurement of CY 2024 Food Stuff (Fruits & Vegetables) for the Clients of RSCC - DSWD FOIX - Centers and Institutions (EPA) | Reception Study Center for Center (RSCC) | Yes | Competitive Bidding | 2023-11-06 | 2023-11-23 |  | 2023-12-03 | 2023-12-15 | 2023-12-15 |  | 2023-12-15 | 2023-12-22 | 2023-12-29 |  |  |  | 2024-01-11 | [6 empty] | Government of the Philippines (current year's budget) | 661842 | 661842 |  | 594100 | 594100 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2023-11-29 | 2023-11-29 | 2023-11-29 | 2023-11-29 | 2023-12-16 |  | Former EPAITB-2024-01-003
320101100001000 | Procurement of CY 2024 Food Stuff (Common Janitorial Supplies) for the Clients of RSCC DSWD FOIX Center and Institution (EPA) – EPAITB-2024-01-027 (FA) | Reception Study Center for Center (RSCC) | Yes | Competitive Bidding | 2023-11-06 | 2023-11-23 |  | 2023-12-03 | 2023-12-15 | 2023-12-15 |  | 2023-12-15 | 2023-12-22 | 2023-12-29 |  |  |  | 2024-01-11 | [6 empty] | Government of the Philippines (current year's budget) | 558200 | 558200 |  | 417200 | 417200 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2023-11-29 | 2023-11-29 | 2023-11-29 | 2023-11-29 | 2023-12-16 |  | Former EPAITB-2024-01-004
320101100001000 | Procurement of CY 2024 Food Stuff (Frozen Goods) for the Clients of RRCY - DSWD FOIX - Centers and Institutions (EPA) | Regional Rehabilitation Center for Youth (RRCY) | Yes | Competitive Bidding | 2023-11-08 | 2023-11-23 |  | 2023-12-03 | 2023-12-15 | 2023-12-15 |  | 2023-12-15 | 2023-12-22 | 2023-12-29 |  |  |  | 2024-01-11 | [6 empty] | Government of the Philippines (current year's budget) | 1297460 | 1297460 |  | 1127860 | 1127860 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2023-11-29 | 2023-11-29 | 2023-11-29 | 2023-11-29 | 2023-12-16 |  | Ongoing Procurement Process
320101100001000 | Procurement of CY 2024 Food Stuff (Fruits & Vegetables) for the Clients of RRCY - DSWD FOIX - Centers and Institutions (EPA) | Regional Rehabilitation Center for Youth (RRCY) | Yes | Competitive Bidding | 2023-11-08 | 2023-11-23 |  | 2023-12-03 | 2023-12-15 | 2023-12-15 |  | 2023-12-15 | 2023-12-22 | 2023-12-29 |  |  |  | 2024-01-11 | [6 empty] | Government of the Philippines (current year's budget) | 1459660 | 1459660 |  | 1223590 | 1223590 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2023-11-29 | 2023-11-29 | 2023-11-29 | 2023-11-29 | 2023-12-16 |  | Ongoing Procurement Process
320101100001000 | Procurement of CY 2024 Food Stuff (Meat Goods) for the Clients of RRCY - DSWD FOIX - Centers and Institutions (EPA) | Regional Rehabilitation Center for Youth (RRCY) | Yes | Competitive Bidding | 2023-11-08 | 2023-11-23 |  | 2023-12-03 | 2023-12-15 | 2023-12-15 |  | 2023-12-15 | 2023-12-22 | 2023-12-29 |  |  |  | 2024-01-11 | [6 empty] | Government of the Philippines (current year's budget) | 3571180 | 3571180 |  | 3184920 | 3184920 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2023-11-29 | 2023-11-29 | 2023-11-29 | 2023-11-29 | 2023-12-16 |  | Ongoing Procurement Process
320101100001000 | EPAITB-2024-01-031(FA):Procurement of CY 2024 Frozen Goods for the Consumption of Home for Women Clients of DSWD FOIX - Centers and Institutions (EPA | Home for Women (HFW) | Yes | Competitive Bidding | 2023-11-06 | 2023-11-30 |  | 2023-12-09 | 2023-12-21 | 2023-12-21 |  | 2023-12-21 | 2023-12-27 | 2024-01-02 |  |  |  | 2024-01-11 | [6 empty] | Government of the Philippines (current year's budget) | 3891635 | 3891635 |  | 3741340 | 3741340 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2023-12-04 | 2023-12-04 | 2023-12-04 | 2023-12-04 |  |  | Former EPAITB-2024-01-007
100000100001000 | Procurement of CY 2024 Security and Janitirial Services of DSWD FO IX | Gen. Services Section | Yes |  | n/a | n/a |  | n/a | n/a | n/a |  | n/a | n/a | 2023-12-21 |  |  |  | 2023-12-21 | 2023-12-28 | 2023-01-01 |  |  | n/a | n/a | Government of the Philippines (current year's budget) | 31239599.32 | 31239599.32 |  | 31239599.32 | 31239599.32 |  |  | n/a | n/a | n/a | n/a | n/a | n/a |  | Contract was renewed
100000100001000 | Procurement of Communication Allowance for Pamilya Pilipino Program Staff , Financial Management Division Staff, Admin Staff and Protective Division Staff to include the Center and Institution Staff | 4Ps, PSD, Admin Division and Financial Division | Yes | Direct Contracting | n/a | n/a |  | n/a | n/a | n/a |  | n/a | n/a | 2023-12-21 |  |  |  | 2023-12-21 | [7 empty] | 4532400 | 4532400 |  | 4532400 | 4532400 |  |  | n/a | n/a | n/a | n/a | n/a | n/a
100000100001000 | ITB-2023-10-079: Labor and Materials for the Construction for the Concreting of Roadway from Main gate to AVRC III and improvement of Guard House with Main Steel Gate and Logo at Home for Women, Mampang Zamboanga City | CRCF | No | Competitive Bidding | 2023-10-20 | 2023-10-31 |  | 2023-11-07 | 2023-11-23 | 2023-11-23 |  | 2023-11-24 | 2023-11-30 | 2023-12-18 |  |  |  | 2023-12-22 | [6 empty] | Government of the Philippines (current year's budget) | 7000000 |  | 7000000 | 5166152.83 |  | 5166152.83 |  | 1. Commission of Audit (COA) (2.) PICE, (3.) National Contractors Asso. Of the Phil. Inc. (4.) Tzu Chi Foundation | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-11-28
320101100001000 | ITB-2023-10-081: Upgrading of Storage Area to Warehouse with Racking System and Improvement of Playground at RSCC, Mampang | Reception Study Center for Center (RSCC) | No | Competitive Bidding | 2023-10-20 | 2023-11-07 |  | 2023-11-07 | 2023-11-23 | 2023-11-23 |  | 2023-11-24 | 2023-11-30 | 2023-12-18 |  |  |  | 2023-12-22 | [6 empty] | Government of the Philippines (current year's budget) | 3799999.99 |  | 3799999.99 | 2964671.06 |  | 2964671.06 |  | 1. Commission of Audit (COA) (2.) PICE, (3.) National Contractors Asso. Of the Phil. Inc./Los Contratistas, Zamboanga Chapter (4.) Tzu Chi Foundation | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-11-28
320101100001000 | ITB-2023-10-082: Construction of Kitchen at RSCC Mampang | Reception Study Center for Center (RSCC) | No | Competitive Bidding | 2023-09-13 | 2023-11-07 |  | 2023-11-07 | 2023-11-23 | 2023-11-23 |  | 2023-11-24 | 2023-11-30 | 2023-12-18 |  |  |  | 2023-12-22 | [6 empty] | Government of the Philippines (current year's budget) | 2900000 |  | 2900000 | 2165037 |  | 2165037 |  | 1. Commission of Audit (COA) (2.) PICE, (3.) National Contractors Asso. Of the Phil. Inc./Los Contratistas, Zamboanga Chapter (4.) Tzu Chi Foundation | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-10-31 | 2023-11-28
320105100002000 | ITB 2023-11-083 Procurement of Grocery Items for Food Consumption of Deportees, DSWD FOIX PCDP | PCDP | No | Competitive Bidding | 2023-09-13 | 2023-11-07 |  | 2023-11-15 | 2023-11-28 | 2023-11-28 |  | 2023-11-28 | 2023-12-01 | 2023-12-18 |  |  |  | 2023-12-27 | [6 empty] | Government of the Philippines (current year's budget) | 2827100 | 2827100 |  | 2639100 |  | 2639100 |  | 1. Commission of Audit (COA) (2.) PICE, (3.) National Contractors Asso. Of the Phil. Inc./Los Contratistas, Zamboanga Chapter (4.) Tzu Chi Foundation | 2023-11-08 | 2023-11-08 | 2023-11-08 | 2023-11-08 | 2023-11-28
320105100002000 | ITB 2023-11-084: Procurement of Food Items for Family Food Packs Use of DSWD FOIX, PCDP, Zamboanga City | PCDP | No | Competitive Bidding | 2023-09-13 | 2023-11-07 |  | 2023-11-15 | 2023-11-28 | 2023-11-28 |  | 2023-11-28 | 2023-12-03 | 2023-12-18 |  |  |  | 2023-12-27 | [6 empty] | Government of the Philippines (current year's budget) | 2003600 | 2003600 |  | 1708300 |  | 1708300 |  | 1. Commission of Audit (COA) (2.) PICE, (3.) National Contractors Asso. Of the Phil. Inc. (4.) Tzu Chi Foundation | 2023-11-08 | 2023-11-08 | 2023-11-08 | 2023-11-08 | 2023-11-28
320105100002000 | ITB 2023-11-085 Procurement of Hygiene Kits for the use of Deportees in DSWD FOIX, PCDP, Zamboanga City | PCDP | No | Competitive Bidding | 2023-09-13 | 2023-11-07 |  | 2023-11-15 | 2023-11-28 | 2023-11-28 |  | 2023-11-28 | 2023-12-02 | 2023-12-18 |  |  |  | 2023-12-27 | [6 empty] | Government of the Philippines (current year's budget) | 5315000 | 5315000 |  | 4161400 |  | 4161400 |  | 1. Commission of Audit (COA) (2.) PICE, (3.) National Contractors Asso. Of the Phil. Inc./Los Contratistas, Zamboanga Chapter (4.) Tzu Chi Foundation | 2023-11-08 | 2023-11-08 | 2023-11-08 | 2023-11-08 | 2023-11-28
320105100002000 | ITB 2023-11-086: Procurement of Vegetables and Fruits for the Consumption of Deportees of DSWD FOIX PCDP, Zamboanga City | PCDP | No | Competitive Bidding | 2023-09-13 | 2023-11-07 |  | 2023-11-15 | 2023-11-28 | 2023-11-28 |  | 2023-11-28 | 2023-12-01 | 2023-12-18 |  |  |  | 2023-12-27 | [6 empty] | Government of the Philippines (current year's budget) | 639420 | 639420 |  | 638200 |  | 638200 |  | 1. Commission of Audit (COA) (2.) PICE, (3.) National Contractors Asso. Of the Phil. Inc. (4.) Tzu Chi Foundation | 2023-11-08 | 2023-11-08 | 2023-11-08 | 2023-11-08 | 2023-11-28
320105100002000 | ITB 2023-11-087: Procurement of Frozen Goods for food Consumption of Deportees, DSWD FOIX PCDP, Zamboanga City | PCDP | No | Competitive Bidding | 2023-09-13 | 2023-11-07 |  | 2023-11-15 | 2023-11-28 | 2023-11-28 |  | 2023-11-28 | 2023-12-01 | 2023-12-18 |  |  |  | 2023-12-27 | [6 empty] | Government of the Philippines (current year's budget) | 1593900 | 1593900 |  | 1583500 |  | 1583500 |  | 1. Commission of Audit (COA) (2.) PICE, (3.) National Contractors Asso. Of the Phil. Inc. (4.) Tzu Chi Foundation | 2023-11-08 | 2023-11-08 | 2023-11-08 | 2023-11-08 | 2023-11-28
310100100001000 | ITB-2023-11-088: Procurement of ICT Equipments for the use of Pantawid Pamilya Pilipin Program (DSLR, Printer, Projectro, Documents Scanner, Desktop Set and Laptop) | 4Ps | No | Competitive Bidding | 2023-11-08 | 2023-11-22 | 14 | 2023-12-11 | 2023-12-12 | 2023-12-12 | 20 | 2023-12-13 | 2023-12-16 | 2023-12-18 | 4 | 6 | 26 | 2023-12-28 | [6 empty] | Government of the Philippines (current year's budget) | 21217969 | 21217969 |  | 18052300 | 18052300 |  | 14.92% | 1. Commission of Audit (COA) (2.) PICE, (3.) National Contractors Asso. Of the Phil. Inc./Los Contratistas, Zamboanga Chapter (4.) Tzu Chi Foundation | 2023-11-24 | 2023-11-24 | 2023-11-24 | 2023-11-24 | 2023-12-13 |  | Ongoing Procurement Process | -145
320101100001000 | ITB-2023-11-089: Construction of Concrete Driveways, Covered Path walks with Lighting, and Landscaping at DSWD FOIX RSCC, Zamboanga City ITB 2023-11-089 | Reception Study Center for Center (RSCC) | No | Competitive Bidding | 2023-10-20 | 2023-11-27 |  | 2023-12-11 | 2023-12-27 | 2023-12-27 |  | 2024-01-03 | 2023-01-11 | [11 empty] | Government of the Philippines (current year's budget) | 2800000 |  | 2800000 | 0 |  |  |  | 1. Commission of Audit (COA) (2.) PICE, (3.) National Contractors Asso. Of the Phil. Inc./Los Contratistas, Zamboanga Chapter (4.) Tzu Chi Foundation | 2023-11-28 | 2023-11-28 | 2023-11-28 | 2023-11-28 | 2023-01-09 |  | Ongoing Procurement Process
320105100002000 | ITB 2023-11-090 Construction/ Upgrading of Admin, and Dormitory Building at DSWD FOIX PCDP at Mampang, Zamboanga City | PCDP | No | Competitive Bidding | 2023-10-31 | 2023-11-27 |  | 2023-12-11 | 2023-12-27 | 2023-12-27 |  | 2024-01-03 | 2023-01-11 | [11 empty] | Government of the Philippines (current year's budget) | 2743655.85 |  | 2743655.85 | 0 |  |  |  | 1. Commission of Audit (COA) (2.) PICE, (3.) National Contractors Asso. Of the Phil. Inc./Los Contratistas, Zamboanga Chapter (4.) Tzu Chi Foundation | 2023-11-28 | 2023-11-28 | 2023-11-28 | 2023-11-28 | 2023-01-09 |  | Ongoing Procurement Process
320101100001000 | ITB 2023-11-091 : Upgrading of Admin and Dormitory Building at DSWD FOIX RSCC, Mampang, Zamboanga City | Reception Study Center for Center (RSCC) | No | Competitive Bidding | 2023-10-31 | 2023-11-27 | 27 | 2023-12-11 | 2023-12-28 | 2023-12-28 | 31 | 2024-01-03 | 2023-01-11 |  | -351 | [9 empty] | Government of the Philippines (current year's budget) | 4000000 |  | 4000000 | 0 |  |  | - | 1. Commission of Audit (COA) (2.) PICE, (3.) National Contractors Asso. Of the Phil. Inc./Los Contratistas, Zamboanga Chapter (4.) Tzu Chi Foundation | 2023-11-28 | 2023-11-28 | 2023-11-28 | 2023-11-28 | 2023-01-09 |  | Ongoing Procurement Process | -150
320101100001000 | ITB 2023-12-092: Upgrading of Admin Building and Dormitory at DSWD FOIX, Home for Women | Home for Women (HFW) | No | Competitive Bidding | 2023-12-05 | 2023-11-27 |  | 2023-12-16 | 2023-12-28 | 2023-12-28 |  | 2024-01-04 | 2023-01-11 | [11 empty] | Government of the Philippines (current year's budget) | 6828253.7 |  | 6828253.7 | 0 |  |  |  | 1. Commission of Audit (COA) (2.) PICE, (3.) National Contractors Asso. Of the Phil. Inc./Los Contratistas, Zamboanga Chapter (4.) Tzu Chi Foundation | 2023-12-15 | 2023-12-15 | 2023-12-15 | 2023-12-15 | 2023-01-09 |  | Ongoing Procurement Process
320101100001000 | ITB 2023-12-093 Construction of 2 Storey Dormitory at DSWD FOIX, RRCY, Polanco, ZDN | Regional Rehabilitation Center for Youth (RRCY) | No | Competitive Bidding | 2023-11-03 | 2023-11-27 |  | 2023-12-16 | 2023-12-28 | 2023-12-28 |  | 2024-01-04 | [12 empty] | Government of the Philippines (current year's budget) | 21960813 |  | 21960813 | 0 |  |  |  | 1. Commission of Audit (COA) (2.) PICE, (3.) National Contractors Asso. Of the Phil. Inc. (4.) Tzu Chi Foundation | 2023-12-15 | 2023-12-15 | 2023-12-15 | 2023-12-15 | 2023-01-09 |  | Ongoing Procurement Process
320101100001000 | ITB 2023-12-094: Construction of Skills Training Center for Bread and Pastries and Water Refilling Station at DSWD FOIX RRCY, Polanco, ZDN | Regional Rehabilitation Center for Youth (RRCY) | No | Competitive Bidding | 2023-11-07 | 2023-11-27 | 20 | 2023-12-16 | 2023-12-28 | 2023-12-28 | 31 | 2024-01-04 | [12 empty] | Government of the Philippines (current year's budget) | 5669161.58 |  | 5669161.58 | 0 |  |  | - | 1. Commission of Audit (COA) (2.) PICE, (3.) National Contractors Asso. Of the Phil. Inc. (4.) Tzu Chi Foundation | 2023-12-15 | 2023-12-15 | 2023-12-15 | 2023-12-15 | 2023-01-09 |  | Ongoing Procurement Process | -150
100000100001000 | ITB 2023-12-095: Construction of Administrative Building at DSWD Compound, Mampang, Zamboanga City | CRCF/General Services Section | No | Competitive Bidding | 2023-12-06 | 2023-11-27 | -9 | 2023-12-16 | 2023-12-28 | 2023-12-28 | 31 | 2024-01-04 | 2023-01-11 |  | -351 | [9 empty] | Government of the Philippines (current year's budget) | 15000000 |  | 15000000 | 0 |  |  | - | 1. Commission of Audit (COA) (2.) PICE, (3.) National Contractors Asso. Of the Phil. Inc./Los Contratistas, Zamboanga Chapter (4.) Tzu Chi Foundation | 2023-12-15 | 2023-12-15 | 2023-12-15 | 2023-12-15 | 2023-01-09 |  | Ongoing Procurement Process | -150
[7 empty] | 11.3333 | [17 empty] | Total Allotted Budget of On-going Procurement Activities | 177699056.2 | 104997172.1 | 72701884.12 | 107675280.9 | 86648919.97 | 21026360.89 | 6.575%
|  | Prepared by: | [9 empty] | Recommended for Approval by: | [14 empty] | APPROVED:
|  | ALWALID SAPPAYANI | [9 empty] | MA. SOCORRO S. MACASO, RSW, MSW | [16 empty] | RIDUAN P. HADJIMUDDIN, CESO IV
|  | BAC Secretariat | [9 empty] | BAC Chairperson | [16 empty] | Head of the Procuring Entity

## Tool 1-Processing (hidden)
Summary of Information for Processing of IRPP
Indicator 1: % of Processed Procurement Activities vs Planned in terms of amount |  | #ERROR!
Formula | Value | Remarks
Total Amount of APP as updated | #ERROR!
Divide by: Total Amount of ABC of procurement activities started | #REF! | ABC of awarded + ABC of on-going procurement projects (less ABC of Failure of Bids)
Indicator 2: Average % of Variance Between Contract Amount vs Approved Budget for the Contract |  | #REF!
Particular | Value | Remarks
Total Amount of ABC of procurement activities started | #REF!
Total Contact Cost | 308127348.4
Total Variance for Each Awarded Procurement Project | #REF! | Column shall be hidden
Divide by Number of Awarded Procurement Projects | 73
Indicator 3. Timeliness on the Conduct of Procurement
|  | Indicator 3.1 Average No. of Days to commence procurement (Pre-Proc to Posting of IB) |  | Indicator 3.2: Average No. of Days to open bid proposals (Posting of IB/ to Opening of Bids) |  | Indicator 3.3: Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) |  | Indicator 3.4: Average Number of Days to Conclude Procurement (Posting of IB to Recommend Award) |  | Indicator 3.5: Average Number of Days to Issue Notice to Proceed (from Issuance of NOA to Issuance of NTP) |  | Indicator 3.6: Accumulated Number of Days for the Procurement Process (Posting of IB to NTP)
Mode of Procurement | Total No. of Activities under subject modality | Total No. of Days from PreProc to IB | Average Days from Pre-Proc to Posting of IB | Total No. of Days from IB to Opening | Average Days from Posting of IB to Opening of Bids | Total No. of Days Opening to Recommend Award) | Average Days from Opening of Bids to Recommend Award | Total No. of Days from Posting of IB to Recommend Award | Average Days from Posting of IB to Recommend Award | Total No. of Days from Issuance of NOA to Issue NTP | Average Days from NOA to NTP | Total No. of Days from Posting of IB to Issue NTP | Average Days from Posting of IB to NTP
Competitive Bidding | 66 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Limited Source Bidding | 0 | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE!
Direct Contracting | 0 | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | 0
Repeat Order | 0 | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | 0
Shopping 52.1(a) - Unforeseen Contingency | 0 | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | 0
Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 0 | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | 0
NP-53.1 Two Failed Biddings | 3 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0
NP-53.2 Emergency Cases | 0 | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | 0
NP-53.3 Take-Over of Contracts | 0 | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | 0
NP-53.4 Adjacent or Contiguous | 0 | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | 0
NP-53.5 Agency-to-Agency | 0 | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | 0
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services | 0 | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | 0
NP-53.7 Highly Technical Consultants | 0 | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | 0
NP-53.8 Defense Cooperation Agreement | 0 | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE!
NP-53.9 - Small Value Procurement | 0 | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE!
NP-53.10 Lease of Real Property and Venue | 0 | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE!
NP-53.11 NGO Participation | 0 | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE!
NP-53.12 Community Participation | 0 | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | 0
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions | 0 | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | 0
NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | 0 | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | 0
Emergency Procurement under Bayanihan Act | 0 | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | 0
Foreign Guidelines - Competitive Bidding | 0 | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | 0
Foreign Guidelines - Alternative Method | 0 | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | #VALUE! |  | 0
Total | 69 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
*formula for days interval for each procurement activity for each indicator are embedded in the PMR.
Indicator 4. Percentage of Amount and Volume by Tender and Award of Procurement Activities per Mode of Procurement
Mode of Procurement | Total No. of Activities | Total Number of Awarded | Total ABC | Total Contract Cost | %Vol of Awarded | %ABC of Awarded | Total Number of Failed | ABC of Failed
Competitive Bidding | 82 | 68 | 309291794.8 | 260919421.7 | 82.93% | 84.36% | 0 | 0
Limited Source Bidding | 0 | 0 | 0 | 0 |  |  | 0 | 0
Direct Contracting | 1 | 1 | 4532400 | 4532400 | 100% | 100% | 0 | 0
Repeat Order | 0 | 0 | 0 | 0 |  |  | 0 | 0
Shopping 52.1(a) - Unforeseen Contingency | 0 | 0 | 0 | 0 |  |  | 0 | 0
Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.1 Two Failed Biddings | 3 | 3 | 11533200 | 11435927.32 | 100% | 99.16% | 0 | 0
NP-53.2 Emergency Cases | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.3 Take-Over of Contracts | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.4 Adjacent or Contiguous | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.5 Agency-to-Agency | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.7 Highly Technical Consultants | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.8 Defense Cooperation Agreement | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.9 - Small Value Procurement | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.10 Lease of Real Property and Venue | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.11 NGO Participation | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.12 Community Participation | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | 0 | 0 | 0 | 0 |  |  | 0 | 0
Emergency Procurement under Bayanihan Act | 0 | 0 | 0 | 0 |  |  | 0 | 0
Foreign Guidelines - Competitive Bidding | 0 | 0 | 0 | 0 |  |  | 0 | 0
Foreign Guidelines - Alternative Method | 0 | 0 | 0 | 0 |  |  | 0 | 0
Total | 86 | 72 | 325357394.8 | 325357394.8 | 94.31% | 94.51% | 0 | 0
Total for Alternative Mode of Procurement | 4 | 4 | 16065600 | 15968327.32 | 100% | 99.58% | 0 | 0
Indicator 5: Accumulated No. of Days for On-going Procurement Activities
Timeline | No. of Procurement Activities | %
Exceeds 180 days | 0 | 0%
Within 91 to 180 days | 0 | 0%
Within 45 to 90 days | 0 | 0%
Within 0 to 44 days | 0 | 0%
Total | 0 | 0%
*Validation shall be provided for the PMR so that the PMO can easily select and determined the total count
Indicator 6. Distribution of On-going, Awarded, and Failed procurement Activities
Status | No. of Procurement Activities | % by No. of Procurement of Activities | ABC Amount of Activities | % by ABC | Contract Cost | Contract/ABC | Variance
Awarded | 0 | 0% | 0 | 0% | 0 | 0% | #DIV/0!
Completed | 0 | 0% | 0 | 0% | 0 | 0% | #DIV/0!
Failed | 0 | 0% | 0 | 0% | 0 | 0% | #DIV/0!
Ongoing | 11 | 100% | 86548153.13 | 100% | 23588670 | 100% | 0.72745
Total | 11 | 100% | 86548153.13 | 100% | 23588670 | 100% | 0.72745
*Validation shall be provided for the PMR so that the PMO can easily select and determined the total count
Indicator 7a: % of Number of Procurement activities conducted under early procurement |  |  | 44.93%
Indicator 7b: % of ABC of Procurement activities conducted under early procurement |  |  | 12.46%
Particular | No. of Procurement Activities | ABC Amount of Activities
Under EPA | 31 | 35628183.75
Regular Procurement | 38 | 250284863.1
Total | 69 | 285913046.8
Indicator 8a: Percentage of Number of Awarded Contracts under EPA |  |  | #VALUE!
Indicator 8b: Percentage of Contract Cost of EPA against the total ABC under EPA |  |  | #VALUE!
Formula | No. of Procurement Activities | Amount of ABC Procurement Activities | Contract Cost of Procurement Activities | Percentage Variance
Total Contracts Awarded under EPA* | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Total Contracts Completed under EPA* | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Total Failed Bid under EPA* | 0 | 0 | 0 | 0%
Total Ongoing Activities under EPA* | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Total Procurement Activities under EPA | 31 | #VALUE! | #VALUE!
To compute for the total, a separate sheet may be created of the PMO may simply filter the cells to capture the total number.
Indicator 9: Stages where failure of bidding are encountered
Particular | No. of Procurement Activities | Amount of ABC | Vol. % | Amount %
Invitation To Bid | 0 | 0 | 0% | 0%
Pre-bidding Conference | 0 | 0 | 0% | 0%
Opening of Bids | 0 | 0 | 0% | 0%
Bid Evaluation | 0 | 0 | 0% | 0%
Post-Qualification | 0 | 0 | 0% | 0%
BAC Resolution | 0 | 0 | 0% | 0%
Award | 0 | 0 | 0% | 0%
Cancelled | 0 | 0 | 0% | 0%
TOTAL | 0 | 0

## Validation Menu (hidden)
REMARKS | STATUS | STAGE OF PROCUREMENT | Source of Funds
Awarded with issued Notice of Award | Awarded | Invitation To Bid | Government of the Philippines (current year's budget)
Completed | Completed | Pre-bidding Conference | Government of the Philippines (continuing budget)
Ongoing Procurement Process | Failed | Opening of Bids | Government of the Philippines (current year's and continuing budget)
Failed under Section 32.2.1 (a) | Ongoing | Bid Evaluation | Grant by an International Financing Institution
Failed under Section 35.1 (a) |  | Post-Qualification | Loan from an International Financing Institution
Failed under Section 35.1 (b) |  | BAC Resolution
Failed under Section 35.1 (c) |  | Award
Failed under Section 41 (b) |  | Cancelled
Failed under Section 41 (c)
Contract was extended
Contract was renewed
Cancelled
Others, please encode directly on the cell