## app
|  | Department of Social Welfare and Development - Field Office IX | [11 empty] | Department of Budget and Management Procurement Monitoring Report as of month/day/2006
Annual Procurement Plan for FY 2025 - Continuing Appropriation
Code (PAP) | Procurement Project | PMO/ End-User | Is this an Early Procurement Activity? (Yes/No) | Mode of Procurement | Schedule for Each Procurement Activity |  |  |  | Source of Funds | Estimated Budget (PhP) |  |  | Remarks (brief description of Project) | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [8 empty] | Remarks (Explaining changes from the APP)
[5 empty] | Advertisement/Posting of IB/REI | Submission/Opening of Bids | Notice of Award | Contract Signing |  | Total | MOOE | CO |  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  | Pre-Proc Conf | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Delivery/ Accept
320102100001000 | Rent of Office Building | SFP | NO | NP-53.10 Lease of Real Property and Venue | N/A | N/A | 2025-05-01 | 2025-05-01 | GoP | 400000 | 400000
320102100001000 | Internet Subscription, fiber, not lower than 20mbps speed/bandwidth | SFP | NO | Direct Contracting | N/A | N/A | FEB. 2025 | FEB. 2025 | GoP | 23100 | 23100
320102100001000 | Van Rental | SFP | NO | Shopping | 2025-05-01 | N/A | 2025-05-01 | 2025-05-01 | GoP | 300000 | 300000
320102100001000 | Various trainings/ meeting to be conducted with accomodations | SFP | NO | NP-53.10 Lease of Real Property and Venue | N/A | N/A | 2025-07-01 | 2025-07-01 | GoP | 1992250 | 1992250
320102100001000 | Purchase of office equipments and furnitures | SFP | NO | Shopping | 2025-05-01 | N/A | 2025-05-01 | 2025-05-01 | GoP | 855600 | 855600
320102100001000 | Nutri Scale - Digital Hanging Type Sclae | SFP | NO | Competitive Bidding | APR. 2025 | APR. 2025 | 2025-05-01 | 2025-05-01 | GoP | 8280000 | 8280000
320102100001000 | "Advocacy Shirt for Financial Management Division Staff | SFP | NO | NP-53.9 - Small Value Procurement | 2025-05-01 | N/A | 2025-05-01 | 2025-05-01 | GoP | 80000 | 80000
200000100001000 | PLDT (inclusive of 1 GBPS Primary for Regional office and 100/50 MPS for 15 Sub-regional sites. (extension of internet services for following ISPs for 3 months Jan-Mar 2025) | ICTMS | NO | Competitive Bidding | 2025-02-01 | FEB. 2025 | MAR. 2025 | MAR. 2025 | GoP | 1602150 | 1602150
200000100001000 | CONVERGE (Secondary internet of regional office with 1 GBPS Bandwith) (extension of internet services for following ISPs for 3 months Jan-Mar 2025) | ICTMS | NO | Competitive Bidding | FEB. 2025 | FEB. 2025 | MAR. 2025 | MAR. 2025 | GoP | 670411.86 | 670411.86
200000100001000 | Purchase of office supplies, furnitures, IT supplies and accessories | ICTMS | NO | Shopping | FEB. 2025 | N/A | MAR. 2025 | MAR. 2025 | GoP | 407300 | 407300
200000100001000 | Installation of various equipments and furnitures | ICTMS | NO | NP-53.9 - Small Value Procurement | FEB. 2025 | N/A | MAR. 2025 | MAR. 2025 | GoP | 836990 | 836990
200000100001000 | Tokens and other gift for pax and RP | ICTMS | NO | NP-53.9 - Small Value Procurement | FEB. 2025 | N/A | MAR. 2025 | MAR. 2025 | GoP | 81000 | 81000
200000100001000 | Various trainings/ meeting to be conducted with accomodations | ICTMS | NO | NP-53.10 Lease of Real Property and Venue | N/A | N/A | MAR. 2025 | MAR. 2025 | GoP | 321300 | 321300
200000100001000 | Catering services for various trainings | ICTMS | NO | NP-53.9 - Small Value Procurement | MAR. 2025 | N/A | MAR. 2025 | MAR. 2025 | GoP | 490000 | 490000
200000100001000 | Purcahse of workshop tokens | ICTMS | NO | Shopping | FEB. 2025 | N/A | FEB. 2025 | FEB. 2025 | GoP | 60000 | 60000
310100200001000 | Purchase of office equipments and office furnitures | KALAHI-KKB | NO | NP-53.9 - Small Value Procurement | FEB. 2025 | N/A | FEB. 2025 | FEB. 2025 | GoP | 379704.06 | 379704.06
310100200001000 | Security Services | KALAHI-KKB | NO | NP-53.9 - Small Value Procurement | 2025-07-01 | N/A | 2025-07-01 | 2025-07-01 | GoP | 738047.31 | 738047.31
. | . | . | YES | Competitive Bidding | . | . | . | . |  | 17517853.23 | 17517853.23
| Prepared by: |  |  | Recommending Approval: |  |  |  |  | Approved by:
| AL-WALID S. SAPPAYANI |  |  | MA. SOCORRO S. MACASO |  |  |  |  | RIDUAN P. HADJIMUDDIN, CESO III
| BAC Secretariat |  |  | BAC Chairman |  |  |  |  | Head of Office/ Agency
Fund allocated:
RODNA GRACE EGUIA-SUGABO
OIC-FMD Chief

## how_to_fill_out-definitions
| GUIDE TO PREPARE APP | APP COLUMN HEADER/S
STEP 1 | In the Code column, kindly indicate the PAP Code. Please refer to the code indicated in the technical budget posted in the DBM website. For GOCCs and LGUs, indicate the procuring entity's internal numbering system. | Code (PAP)
STEP 2 | For the Procurement Project column, please align descriptions of program/projects with budget documents and ensure clarity and accuracy in describing each procurement program/project. | Procurement Project
STEP 3 | For PMO/End-User, please indicate the PMO/End-User unit who will implement/utilize the procurement program/project. Multiple end-user units are allowed only if the procurement activity was consolidated by the BAC to procure requirements of the end-user units. | PMO/End-User
STEP 4 | For Mode of Procurement and Schedule for Each Procurement Activity, all modes of procurement are available as a dropdown list and requirements for a specific schedule for Ads/Post of IB/REI, Sub/Open of Bids, Notice of Award, and/or Contract Signing are automatically identified thru the MS Excel formula. Note that for Foreign-funded procurement, please use Others - Foreign-funded procurement as the Mode of Procurement. Kindly indicate a specific period (dates, month, quarter) when each Procurement Activity will be done. Please refer to our website: http://www.gppb.gov.ph/timelines/timelines.htm for the specific periods for each activity. Note: For SVP, IB/REI is similar to RFQ. Ads/Post of IB/REI for Shopping 52.1(b) and NP-SVP (53.9) needs to be posted in PhilGEPS for ABCs above 50k. Notice of Award posting in PhilGEPS is mandatory for all Alternative Modes only for ABCs above 50k. | Mode of Procurement | Schedule for Each Procurement Activity
|  |  | Ads/Post of IB/REI | Sub/Open of Bids | Notice of Award | Contract Signing
STEP 5 | For Source of Funds, a dropdown list is available. If the Source of Funds the PE will use is not included, please indicate "Others" and specify under the Remarks column. | Source of Funds
STEP 6 | For Estimated Budget (PhP), kindly fill out either MOOE or CO columns only. Total ABC column is not editable, but will automatically compute for the total MOOE and CO components of the project. This breakdown is needed for tracking purposes. Finally, please ensure that amounts indicated are aligned with budget documents. | Estimated Budget (PhP)
STEP 7 | Before submission to the GPPB, ensure that the Head of the Procuring Entity (HoPE) approves/signs the APP.
GENERAL INFORMATION
#1 | All Cells with Fill Color Orange needs to be filled out by the Agency. This is a visual reminder of blank or improperly filled out cells.
#2 | To ensure that automated indicator which procurement activity needs to be filled out with specific periods, PE must copy entire Excel row with the mode of procurement for the specific procurement program/project and paste on the last sample row "Negotiated Procurement-53.13" in the template.
#3 | If PE wishes to edit formatting and design of borders, fonts, among others of the APP template, it is suggested to utilize the automated formulas in the template before copying contents and reformatting.
#4 | Per Section of 3.1.1 of DBM Circular No. 2015-7, the Approved Budget for the Contract (ABC) shall be “[t]he amount reflected in the MYOA”. Hence, the ABC in the Annual Procurement Plan (APP) shall be the full amount stated in the MYOA with remarks added on how much will be actually disbursed for that particular fiscal year. Moreover, the Procurement Monitoring Report (PMR) should also reflect full amount in the MYOA if the entire contract was awarded within the fiscal year. Thus, for succeeding years, actual disbursements from the MYOA need not be reflected in the APPs and PMRs, unless current contract with MYOA is terminated and a new procurement activity is undertaken.
DEFINITIONS
1. PROGRAM (BESF)– A homogeneous group of activities necessary for the performance of a major purpose for which a government agency is established, for the basic maintenance of the agency’s administrative operations or for the provisions of staff support to the agency’s administrative operations or for the provisions of staff support to the agency’s line functions.
2. PROJECT (BESF)– Special agency undertakings which are to be carried out within a definite time frame and which are intended to result in some pre-determined measure of goods and services.
3. PMO/End User - Unit as proponent of program or project
4. Mode of Procurement - Competitive Bidding and Alternative Methods including: selective bidding, direct contracting, repeat order, shopping, and negotiated procurement.
5. Schedule for Each Procurement Activity - Major procurement activities (advertising/posting; submission and receipt/Opening of bids; award of contract; contract signing).
6. Source of Funds - Whether GoP, Foreign Assisted or Special Purpose Fund
7. Estimated Budget - Agency approved estimate of project/program costs
8. Remarks - brief description of program or project

## data_validation (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
Emergency Procurement under the Bayanihan Act
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets
Others - Foreign-funded procurement