## PMR
Department of Social Welfare and Development (DSWD) FIELD OFFICE -IX | [11 empty] | Procurement Monitoring Report as of January 1, 2025 to June 30, 2025
[5 empty] | . | [20 empty] | ABC (PhP) |  |  | Contract Cost (PhP) |  |  |  |  | Date of Receipt of Invitation
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Ave. No. of Days to Commence Procurement (Pre-Proc to Posting of IB) (i.3) | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Average No. of Days to open bid proposals (Posting of IB to Opening of Bids) (i.4) | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Accumulated Days in Evaluation of Bids (Opening of Bids to Post Qua) | Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) (i.5) | Average Number of Days to Conclude Procurement (IB to BAC Reso) (i.6) | Notice of Award | Contract Signing | Notice to Proceed | Average Number of Days to Issue Notice to Proceed (NOA to NTP) (i.7) | Average Days from (Posting of IB to NTP) (i.8) | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | % Variance | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/ Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP) | Column1 | Column2
COMPLETED PROCUREMENT ACTIVITIES | [31 empty] | -
100000100001000 | ITB-2024-09-036 2ND PUBLIC BIDDING PROCUREMENT OF OFFICE UNIFORM CLOTH FOR DSWD FOIX STAFF | HRMDD | No | Competitive Bidding | 2024-09-03 | 2024-10-02 | 29 | 2024-10-09 | 2024-10-22 | 2024-10-22 | 20 | 2024-10-23 | 2024-11-08 | 2024-11-25 | 17 | 34 | 54 | 2024-12-06 | 2024-04-12 | 2024-12-20 |  |  | 2025-02-14 | 2025-02-14 | Government of the Philippines (current year's budget) | 3237200 | 3237200 |  | 2865460 | 2865460 |  | 0.11483 | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2024-10-09 | 2024-10-22 | 2024-10-22 | 2024-10-23 | 2024-11-08 | 2025-02-14 |  | FALSE | FALSE
320102100001000 | ITB-2024-10-038 2ND PUBLIC BIDDING - PROCUREMENET OF FOOD ITEMS FOR DSWD FOIX SFP 14TH CYCLE IMPLEMENTATION IN ISABELA CITY, BASILAN | SFP | No | Competitive Bidding | 2024-06-21 | 2024-10-03 |  | 2024-10-09 | 2024-10-22 | 2024-10-22 |  | 2024-10-23 | 2024-11-08 | 2024-11-11 |  |  |  | 2024-11-19 | 2024-03-12 | 2024-04-12 |  |  | 2025-02-14 | 2025-02-14 | Government of the Philippines (current year's budget) | 4277351 | 4277351 |  | 3806842.39 | 3806842.39 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2024-10-09 | 2024-10-22 | 2024-10-22 | 2024-10-23 | 2024-11-08 | 2025-02-14
320105100002000 | ITB-2024-11-040 PROCUREMENT OF APPARELS AND CLOTHING FOR DSWD FOIX PCDP | PCDP | No | Competitive Bidding | 2024-10-17 | 2024-11-07 |  | 2024-11-13 | 2024-11-26 | 2024-11-26 |  | 2024-11-28 | 2024-12-03 | 2024-12-02 |  |  |  | 2024-10-06 | 2024-12-26 | 2025-01-10 |  |  | 2025-01-08 | 2025-01-08 | Government of the Philippines (current year's budget) | 7115000 | 7115000 |  | 5283500 | 5283500 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2024-11-13 | 2024-11-26 | 2024-11-26 | 2024-11-28 | 2024-12-03 | 2025-01-08
320105100002000 | ITB-2024-11-041 PROCUREMENT OF FAMILY FOOD PACK FOR DSWD FOIX PCDP, ZAMBOANGA CITY | PCDP | No | Competitive Bidding | 2024-10-17 | 2024-11-06 |  | 2024-11-14 | 2024-11-26 | 2024-11-26 |  | 2024-11-28 | 2024-12-03 | 2024-12-03 |  |  |  | 2024-12-06 | 2024-12-24 | 2025-01-10 |  |  | 2025-01-20 | 2025-01-20 | Government of the Philippines (current year's budget) | 2844880 | 2844880 |  | 2455060 | 2455060 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2024-11-14 | 2024-11-26 | 2024-11-26 | 2024-11-28 | 2024-12-03 | 2025-01-20
320102100001000 | NP2FB-2024-003 PROCUREMENT OF READY-TO-EAT HIGH PROTEIN BISCUIT | SFP | No | Competitive Bidding |  | 2024-10-30 |  | 2024-11-04 | 2024-11-08 | 2024-11-08 |  | 2024-11-10 | 2024-11-27 | 2024-12-04 |  |  |  | 2024-12-06 | 2024-12-23 | 2024-12-24 |  |  | 2025-01-16 | 2025-01-16 | Government of the Philippines (current year's budget) | 9857970 | 9857970 |  | 9825110 | 9825110 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2024-11-04 | 2024-11-08 | 2024-11-08 | 2024-11-10 | 2024-11-27 | 2025-01-16
320101100001000 | EPA-HFW-2025-001 Early Procurement Activity (EPA) CY2025, Procurement of Grocery Items for DSWD FOIX Home for Women | HFW | Yes | Competitive Bidding | 2024-10-17 | 2024-11-15 |  | 2024-11-22 | 2024-12-04 | 2024-12-04 |  | 2024-12-05 | 2024-12-13 | 2024-12-30 |  |  |  | 2025-01-20 | 2025-01-31 | 2025-01-31 |  |  | 2025-04-23 | 2025-04-23 | Government of the Philippines (current year's budget) | 3963155 | 3963155 |  | 3365359 | 3365359 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2024-11-22 | 2024-12-04 | 2024-12-05 | 2024-12-05 | 2024-12-13 | 2025-04-23
320101100001000 | EPA-HFW-2025-002 Early Procurement Activity (EPA) CY2025, Procurement of Frozen Goods for DSWD FOIX Home for Women | HFW | Yes | Competitive Bidding | 2024-10-17 | 2024-11-15 |  | 2024-11-22 | 2024-12-04 | 2024-12-04 |  | 2024-12-05 | 2024-12-13 | 2024-12-30 |  |  |  | 2025-01-20 | 2025-01-31 | 2025-01-31 |  |  | 2025-05-31 | 2025-05-31 | Government of the Philippines (current year's budget) | 4817120 | 4817120 |  | 4115720 | 4115720 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2024-11-22 | 2024-12-04 | 2024-12-05 | 2024-12-05 | 2024-12-13 | 2025-05-31
320101100001000 | EPA-HFW-2025-003 Early Procurement Activity (EPA) CY2025, Procurement of Fruits and Vegetables for DSWD FOIX Home for Women | HFW | Yes | Competitive Bidding | 2024-10-17 | 2024-11-15 |  | 2024-11-22 | 2024-12-04 | 2024-12-04 |  | 2024-12-05 | 2024-12-13 | 2024-12-30 |  |  |  | 2025-01-20 | 2025-01-31 | 2025-01-31 |  |  | 2025-04-23 | 2025-04-23 | Government of the Philippines (current year's budget) | 1833395 | 1833395 |  | 1503100 | 1503100 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2024-11-22 | 2024-12-04 | 2024-12-05 | 2024-12-05 | 2024-12-13 | 2025-04-23
320101100001000 | EPA-HFW-2025-004 Early Procurement Activity (EPA) CY2025, Procurement of Janitorial Supplies for DSWD FOIX Home for Women | HFW | Yes | Competitive Bidding | 2024-10-17 | 2024-11-15 |  | 2024-11-22 | 2024-12-04 | 2024-12-04 |  | 2024-12-05 | 2024-12-13 | 2024-12-30 |  |  |  | 2025-01-20 | 2025-01-31 | 2025-01-31 |  |  | 2025-02-12 | 2025-02-12 | Government of the Philippines (current year's budget) | 1031522 | 1031522 |  | 846960 | 846960 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2024-11-22 | 2024-12-04 | 2024-12-05 | 2024-12-05 | 2024-12-13 | 2025-02-12
320101100001000 | EPA-HFW-2025-005 Early Procurement Activity (EPA) CY2025, Procurement of Apparels, Personal Effects and Toiletries for DSWD FOIX Home for Women | HFW | Yes | Competitive Bidding | 2024-10-17 | 2024-11-15 |  | 2024-11-22 | 2024-12-04 | 2024-12-04 |  | 2024-12-05 | 2024-12-13 | 2024-12-30 |  |  |  | 2025-01-20 | 2025-01-31 | 2025-01-31 |  |  | 2025-04-23 | 2025-04-23 | Government of the Philippines (continuing budget) | 1485171 | 1485171 |  | 1187329 | 1187329 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2024-11-22 | 2024-12-04 | 2024-12-05 | 2024-12-05 | 2024-12-13 | 2025-04-23
320101100001000 | EPA-HFTE-2025-006 Early Procurement Activity (EPA) CY2025, Procurement of Personal Care Products for DSWD FOIX Home for the Elderly | HFE | Yes | Competitive Bidding | 2024-10-17 | 2024-11-15 |  | 2024-11-22 | 2024-12-04 | 2024-12-04 |  | 2024-12-05 | 2024-12-13 | 2024-12-30 |  |  |  | 2025-01-20 | 2025-01-31 | 2025-01-31 |  |  | 2025-02-10 | 2025-02-10 | Government of the Philippines (current year's budget) | 2055040 | 2055040 |  | 1857650 | 1857650 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2024-11-22 | 2024-12-04 | 2024-12-05 | 2024-12-05 | 2024-12-13 | 2025-02-10
320101100001000 | EPA-HFTE-2025-008 Early Procurement Activity (EPA) CY2025, Procurement of Grocery Items for DSWD FOIX Home for the Elderly | HFE | Yes | Competitive Bidding | 2024-10-17 | 2024-11-15 | 29 | 2024-11-22 | 2024-12-04 | 2024-12-04 | 19 | 2024-12-05 | 2024-12-13 | 2024-12-30 | 9 | 26 | 45 | 2025-01-20 | 2025-01-31 | 2025-01-31 |  |  | 2025-02-13 | 2025-02-13 | Government of the Philippines (current year's budget) | 4890540 | 4890540 |  | 4193004 | 4193004 |  | 0.14263 | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2024-11-22 | 2024-12-04 | 2024-12-05 | 2024-12-05 | 2024-12-13 | 2025-02-13 |  | FALSE | FALSE
320101100001000 | EPA-RRCY-2025-016 Early Procurement Activity (EPA) CY2025, Procurement of Fruits and Vegetables for DSWD FOIX RRCY | RRCY | Yes | Competitive Bidding | 2024-10-17 | 2024-11-22 |  | 2024-11-29 | 2024-12-11 | 2024-12-11 |  | 2024-12-11 | 2024-12-21 | 2024-12-30 |  |  |  | 2025-01-24 | 2025-01-31 | 2025-01-31 |  |  | 2025-02-04 | 2025-02-04 | Government of the Philippines (current year's budget) | 975420 | 975420 |  | 742550 | 742550 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2024-11-29 | 2024-12-11 | 2024-12-11 | 2024-12-11 | 2024-12-21 | 2025-02-04
320101100001000 | EPA-RRCY-2025-017 Early Procurement Activity (EPA) CY2025, Procurement of Frozen Goods for DSWD FOIX RRCY | RRCY | Yes | Competitive Bidding | 2024-10-17 | 2024-11-22 |  | 2024-11-29 | 2024-12-11 | 2024-12-11 |  | 2024-12-11 | 2024-12-21 | 2024-12-30 |  |  |  | 2025-01-24 | 2025-01-31 | 2025-01-31 |  |  | 2025-02-04 | 2025-02-04 | Government of the Philippines (current year's budget) | 3264700 | 3264700 |  | 2715700 | 2715700 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2024-11-29 | 2024-12-11 | 2024-12-11 | 2024-12-11 | 2024-12-21 | 2025-02-04
320101100001000 | EPA-RRCY-2025-018 Early Procurement Activity (EPA) CY2025, Procurement of Grocery Items for DSWD FOIX RRCY | RRCY | Yes | Competitive Bidding | 2024-10-17 | 2024-11-22 | 36 | 2024-11-29 | 2024-12-11 | 2024-12-11 | 19 | 2024-12-11 | 2024-12-21 | 2024-12-30 | 10 | 19 | 38 | 2025-01-24 | 2025-01-31 | 2025-01-31 |  |  | 2025-02-04 | 2025-02-04 | Government of the Philippines (current year's budget) | 1500240 | 1500240 |  | 1307000 | 1307000 |  | 0.12881 | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2024-11-29 | 2024-12-11 | 2024-12-11 | 2024-12-11 | 2024-12-21 | 2025-02-04 |  | FALSE | FALSE
320101100001000 | EPA-BDSK-2025-020 Early Procurement Activity (EPA) CY2025, Procurement of Frozen Goods for DSWD FOIX BDSK | BDSK | Yes | Competitive Bidding | 2024-11-21 | 2024-12-07 | 16 | 2024-12-14 | 2024-12-27 | 2024-12-27 | 20 | 2024-12-11 | 2024-12-30 | 2024-12-30 | 3 | 3 | 23 | 2025-01-24 | 2025-01-31 | 2025-01-31 |  |  | 2025-05-18 | 2025-05-18 | Government of the Philippines (current year's budget) | 2296190 | 2296190 |  | 2290000 | 2290000 |  | 0.0026958 | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2024-12-14 | 2024-12-27 | 2024-12-27 | 2024-12-11 | 2024-12-30 | 2025-05-18 |  | FALSE | FALSE
320101100001000 | EPA-BDSK-2025-021 Early Procurement Activity (EPA) CY2025, Procurement of Seafoods for DSWD FOIX BDSK | BDSK | Yes | Competitive Bidding | 2024-11-21 | 2024-12-07 | 16 | 2024-12-14 | 2024-12-27 | 2024-12-27 | 20 | 2024-12-11 | 2024-12-30 | 2024-12-30 | 3 | 3 | 23 | 2025-01-24 | 2025-01-31 | 2025-01-31 |  |  | 2025-06-05 | 2025-06-05 | Government of the Philippines (current year's budget) | 953800 | 953800 |  | 843750 | 843750 |  | 0.11538 | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2024-12-14 | 2024-12-27 | 2024-12-27 | 2024-12-11 | 2024-12-30 | 2025-06-05 |  | FALSE | FALSE
320101100001000 | EPA-BDSK-2025-022 Early Procurement Activity (EPA) CY2025, Procurement of Fruits and Vegetables for DSWD FOIX BDSK | BDSK | Yes | Competitive Bidding | 2024-11-21 | 2024-12-07 | 16 | 2024-12-14 | 2024-12-27 | 2024-12-27 | 20 | 2024-12-11 | 2024-12-30 | 2024-12-30 | 3 | 3 | 23 | 2025-01-24 | 2025-01-31 | 2025-01-31 |  |  | 2025-06-05 | 2025-06-05 | Government of the Philippines (current year's budget) | 1141700 | 1141700 |  | 1140000 | 1140000 |  | 0.001489 | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2024-12-14 | 2024-12-27 | 2024-12-27 | 2024-12-11 | 2024-12-30 | 2025-06-05 |  | FALSE | FALSE
320101100001000 | EPA-BDSK-2025-023 Early Procurement Activity (EPA) CY2025, Procurement of Grocery Items for DSWD FOIX BDSK | BDSK | Yes | Competitive Bidding | 2024-11-21 | 2024-12-07 | 16 | 2024-12-14 | 2024-12-27 | 2024-12-27 | 20 | 2024-12-11 | 2024-12-30 | 2024-12-30 | 3 | 3 | 23 | 2025-01-20 | 2025-01-31 | 2025-01-31 |  |  | 2025-02-13 | 2025-02-13 | Government of the Philippines (current year's budget) | 1900950 | 1900950 |  | 1688149 | 1688149 |  | 0.11194 | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2024-12-14 | 2024-12-27 | 2024-12-27 | 2024-12-11 | 2024-12-30 | 2025-02-13 |  | FALSE | FALSE
-
-
[25 empty] | Total Allotted Budget of Procurement Activities | 59441344 | 59441344 | 0 |  |  |  | 12.46%
[25 empty] | Total Contract Price of Procurement Activities Conducted |  |  |  | 52032243.39 | 52032243.39 | 0
[25 empty] | Total Savings (Total Allotted Budget - Total Contract Price) | 7409100.61 | [14 empty] | 2023-06-30
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Ave. No. of Days to Commence Procurement (Pre-Proc to Posting of IB) (i.3) | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Average No. of Days to open bid proposals (Posting of IB to Opening of Bids) (i.4) | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Accumulated Days in Evaluation of Bids (Opening of Bids to Post Qua) | Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) (i.5) | Average Number of Days to Conclude Procurement (IB to BAC Reso) (i.6) | Notice of Award | Contract Signing | Notice to Proceed | Average Number of Days to Issue Notice to Proceed (NOA to NTP) (i.7) | Average Days from (Posting of IB to NTP) (i.8) | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | % Variance | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP) | Column42
ONGOING PROCUREMENT ACTIVITIES | [31 empty] | -
320102100001000 | ITB-2024-11-039 REPUBLISHED - PROCUREMENT OF FOOD ITEMS FOR DSWD FOIX SFP 14TH CYCLE IMPLEMENTATION IN ZAMBOANGA CITY | SFP | No | Competitive Bidding | 2024-06-21 | 2024-11-06 |  | 2024-11-13 | 2024-11-26 | 2024-11-26 |  | 2024-11-28 | 2024-12-02 | 2024-12-02 |  |  |  | 2024-12-06 | [6 empty] | Government of the Philippines (current year's budget) | 21215691 | 21215691 |  | 3806842.39 | 3806842.39 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2024-11-13 | 2024-11-26 | 2024-11-26 | 2024-11-28 | 2024-12-02 |  | Ongoing Procurement Process
320102100001000 | NPCP-2024-002- PROCUREMENT OF FOOD ITEMS FOR DSWD FOIX SFP 14TH CYCLE IMPLEMENTATION IN TUKURAN, ZDS | SFP | No | Competitive Bidding |  | 2024-09-06 |  | 2024-09-09 | 2024-09-10 | 2024-09-10 |  | 2024-09-16 | 2024-09-23 | 2024-09-30 |  |  |  | 2024-10-04 | [6 empty] | Government of the Philippines (current year's budget) | 2628000 | 2628000 |  | 2551479 | 2551479 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2024-09-09 | 2024-09-10 | 2024-09-10 | 2024-09-16 | 2024-09-23 |  | Ongoing Procurement Process
320101100001000 | EPA-HFTE-2025-007 Early Procurement Activity (EPA) CY2025, Procurement of Vegetables and Fruits for DSWD FOIX Home for the Elderly. | HFE | Yes | Competitive Bidding | 2024-10-17 | 2024-11-15 |  | 2024-11-22 | 2024-12-04 | 2024-12-04 |  | 2024-12-05 | 2024-12-13 | 2024-12-30 |  |  |  | 2025-01-20 | 2025-01-31 | 2025-01-31 |  |  |  |  | Government of the Philippines (current year's budget) | 1976600 | 1976600 |  | 1677500 | 1677500 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2024-11-22 | 2024-12-04 | 2024-12-05 | 2024-12-05 | 2024-12-13 |  | Ongoing Procurement Process
320101100001000 | EPA-HFTE-2025-009 Early Procurement Activity (EPA) CY2025, Procurement of Meat and Frozen Goods for DSWD FOIX Home for the Elderly | HFE | Yes | Competitive Bidding | 2024-11-21 | 2024-11-21 | 0 | 2024-11-28 | 2024-12-10 | 2024-12-10 | 19 | 2024-12-11 | 2024-12-18 | 2024-12-30 | 8 | 20 | 39 | 2025-01-20 | 2025-01-31 | 2025-01-31 |  |  |  |  | Government of the Philippines (current year's budget) | 2785200 | 2785200 |  | 2480200 | 2480200 |  | 0.10951 | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2024-11-28 | 2024-12-10 | 2024-12-10 | 2024-12-11 | 2024-12-18 |  | Ongoing Procurement Process | FALSE | FALSE
320101100001000 | EPA-HFTE-2025-010 Early Procurement Activity (EPA) CY2025, Procurement of Seafoods for DSWD FOIX Home for the Elderly | HFE | Yes | Competitive Bidding | 2024-11-21 | 2024-11-21 |  | 2024-11-28 | 2024-12-10 | 2024-12-10 |  | 2024-12-11 | 2024-12-18 | 2024-12-30 |  |  |  | 2025-01-20 | 2025-01-31 | 2025-01-31 |  |  |  |  | Government of the Philippines (current year's budget) | 2190120 | 2190120 |  | 1867050 | 1867050 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2024-11-28 | 2024-12-10 | 2024-12-10 | 2024-12-11 | 2024-12-18 |  | Ongoing Procurement Process | FALSE | FALSE
320101100001000 | EPA-RSCC-2025-011 Early Procurement Activity (EPA) CY2025, Procurements of Janitorial Supplies for DSWD FOIX Reception and Study Center for Children | RSCC | Yes | Competitive Bidding | 2024-11-21 | 2024-11-21 | 0 | 2024-11-28 | 2024-12-10 | 2024-12-10 | 19 | 2024-12-11 | 2024-12-21 | 2024-12-30 | 11 | 20 | 39 | 2025-01-24 | 2025-01-31 | 2025-01-31 |  |  |  |  | Government of the Philippines (current year's budget) | 558200 | 558200 |  | 436900 | 436900 |  | 0.21731 | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2024-11-28 | 2024-12-10 | 2024-12-10 | 2024-12-11 | 2024-12-18 |  | Ongoing Procurement Process | FALSE | FALSE
320101100001000 | EPA-RSCC-2025-012 Early Procurement Activity (EPA) CY2025, Procurements of Personal Effects for DSWD FOIX Reception and Study Center for Children. | RSCC | Yes | Competitive Bidding | 2024-11-21 | 2024-11-21 |  | 2024-11-28 | 2024-12-10 | 2024-12-10 |  | 2024-12-11 | 2024-12-21 | 2024-12-30 |  |  |  | 2025-01-24 | 2025-01-31 | 2025-01-31 |  |  |  |  | Government of the Philippines (current year's budget) | 881075 | 881075 |  | 819600 | 819600 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2024-11-28 | 2024-12-10 | 2024-12-10 | 2024-12-11 | 2024-12-18 |  | Ongoing Procurement Process
320101100001000 | EPA-RSCC-2025-013 Early Procurement Activity (EPA) CY2025, Procurements of Fruits for DSWD FOIX Reception and Study Center for Children | RSCC | Yes | Competitive Bidding | 2024-11-21 | 2024-11-22 |  | 2024-11-28 | 2024-12-10 | 2024-12-10 |  | 2024-12-11 | 2024-12-18 | 2024-12-30 |  |  |  | 2025-01-20 | 2025-01-31 | 2025-01-31 |  |  |  |  | Government of the Philippines (current year's budget) | 886310 | 886310 |  | 827900 | 827900 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2024-11-28 | 2024-12-10 | 2024-12-10 | 2024-12-11 | 2024-12-18 |  | Ongoing Procurement Process
320101100001000 | EPA-RSCC-2025-014 Early Procurement Activity (EPA) CY2025, Procurements of Frozen Goods for DSWD FOIX Reception and Study Center for Children | RSCC | Yes | Competitive Bidding | 2024-11-21 | 2024-11-21 |  | 2024-11-28 | 2024-12-10 | 2024-12-10 |  | 2024-12-11 | 2024-12-18 | 2024-12-30 |  |  |  | 2025-01-20 | 2025-01-31 | 2025-01-31 |  |  |  |  | Government of the Philippines (current year's budget) | 2802900 | 2802900 |  | 2603130 | 2603130 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2024-11-28 | 2024-12-10 | 2024-12-10 | 2024-12-11 | 2024-12-18 |  | Ongoing Procurement Process
320101100001000 | EPA-RSCC-2025-015 Procurements of Grocery Items for DSWD FOIX Reception and Study Center for Children | RSCC | Yes | Competitive Bidding | 2024-11-21 | 2024-11-22 |  | 2024-11-29 | 2024-12-11 | 2024-12-11 |  | 2024-12-11 | 2024-12-21 | 2024-12-30 |  |  |  | 2025-01-24 | 2025-01-31 | 2025-01-31 |  |  |  |  | Government of the Philippines (current year's budget) | 2318682 | 2318682 |  | 1938820 | 1938820 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2024-11-29 | 2024-12-11 | 2024-12-11 | 2024-12-11 | 2024-12-21 |  | Ongoing Procurement Process
100000100001000 | EPA-GENSERV-2025-019 Early Procurement Activity (EPA) CY2025, Procurement of DSWD FO IX Janitorial and Security Services for CY 2025 | GENSERV | Yes | Competitive Bidding | 2024-11-29 | 2024-11-30 |  | 2024-12-07 | 2024-12-19 | 2024-12-26 |  | 2024-12-11 | 2024-12-28 | 2024-12-30 |  |  |  | 2025-01-01 | 2025-01-31 | 2025-01-31 |  |  |  |  | Government of the Philippines (current year's budget) | 32342853.12 | 32342853.12 |  | 32314389.08 | 32314389.08 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2024-12-07 | 2024-12-19 | 2024-12-19 | 2024-12-11 | 2024-12-30 |  | Ongoing Procurement Process
320101100001000 | EPA-HFTE-2025-024 Early Procurement Activity (EPA) CY2025, Procurement of Medicines and Medical Supplies for DSWD FOIX Home for the Elderly | BDSK | Yes | Competitive Bidding | 2024-10-17 | 2024-12-07 |  | 2024-12-14 | 2024-12-27 | 2024-12-27 |  | 2024-12-11 | 2024-12-30 | 2024-12-30 |  |  |  | 2025-01-07 | 2025-01-31 | 2025-01-31 |  |  |  |  | Government of the Philippines (current year's budget) | 1542334 | 1542334 |  | 1521379.75 | 1521379.75 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2024-12-14 | 2024-12-27 | 2024-12-27 | 2024-12-11 | 2024-12-30 |  | Ongoing Procurement Process
200000100001000 | ITB 2025-ICT-001 Procurement of Internet Services (Primary) for DSWD Field Office IX | ICTMS | No | Competitive Bidding | 2025-02-10 |  |  | 2025-02-20 | 2025-03-04 | 2025-03-04 |  | 2025-03-06 | 2025-03-14 | 2025-03-21 |  |  |  | 2025-03-27 | [6 empty] | Government of the Philippines (current year's budget) | 4806450 | 4806450 |  | 4272400 | 4272400 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2025-02-20 | 2025-03-04 | 2025-03-04 | 2025-03-06 | 2025-03-14 |  | Ongoing Procurement Process
200000100001000 | ITB 2025-ICT-002 Procurement of Internet Services (Secondary) for DSWD Field Office IX | ICTMS | No | Competitive Bidding | 2025-02-10 |  |  | 2025-02-20 | 2025-03-04 | 2025-03-04 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Government of the Philippines (current year's budget) | 2011235.58 | 2011235.58 |  | 0 |  |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2025-02-20 | 2025-03-04 | 2025-03-04 | n/a | n/a | n/a | Failed under Section 35.1 (b)
320102100001000 | ITB 2025-SFP-003 Procurement of Food Items for 2025 SFP 15th Cycle Implementation ZDN – Cluster B | SFP | No | Competitive Bidding | 2025-02-10 |  |  | 2025-02-20 | 2025-03-04 | 2025-03-04 |  | 2025-03-14 | 2025-03-21 | [11 empty] | Government of the Philippines (current year's budget) | 19777590 | 19777590 |  | 17404279.2 | 17404279.2 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2025-02-20 | 2025-03-04 | 2025-03-04 |  |  |  | Ongoing Procurement Process
320102100001000 | ITB 2025-SFP-004 Procurement of Food Items for 2025 SFP 15th Cycle Implementation ZDN – Cluster C | SFP | No | Competitive Bidding | 2025-02-10 |  |  | 2025-02-20 | 2025-03-04 | 2025-03-04 |  | 2025-03-14 | 2025-03-21 | [11 empty] | Government of the Philippines (current year's budget) | 18141578 | 18141578 |  | 15964588.64 | 15964588.64 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2025-02-20 | 2025-03-04 | 2025-03-04 |  |  |  | Ongoing Procurement Process
320102100001000 | ITB 2025-SFP-005 Procurement of Food Items for 2025 SFP 15th Cycle Implementation ZDN – Cluster D | SFP | No | Competitive Bidding | 2025-02-10 | 2025-03-30 |  | 2025-02-20 | 2025-03-04 | 2025-03-04 |  | 2025-03-14 | 2025-03-21 |  |  |  |  | 2025-03-27 | [6 empty] | Government of the Philippines (current year's budget) | 21092616 | 21092616 |  | 14269770 | 14269770 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2025-02-20 | 2025-03-04 | 2025-03-04 |  |  |  | Ongoing Procurement Process
320102100001000 | ITB 2025-SFP-006 Procurement of Food Items for 2025 SFP 15th Cycle Implementation ZDN – Cluster E | SFP | No | Competitive Bidding | 2025-02-10 |  |  | 2025-02-20 | 2025-03-04 | 2025-03-04 |  | 2025-03-14 | 2025-03-12 | [11 empty] | Government of the Philippines (current year's budget) | 12911036 | 12911036 |  | 11842357 | 11842357 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2025-02-20 | 2025-03-04 | 2025-03-04 |  |  |  | Ongoing Procurement Process
320102100001000 | ITB 2025-SFP-007 Procurement of Food Items for 2025 SFP 15th Cycle Implementation ZDS – Cluster B | SFP | No | Competitive Bidding | 2025-02-10 |  |  | 2025-02-20 | 2025-03-04 | 2025-03-04 |  | 2025-03-06 | 2025-03-11 | 2025-03-21 |  |  |  | 2025-03-27 | 2025-06-05 | 2025-06-05 |  |  |  |  | Government of the Philippines (current year's budget) | 14269770 | 14269770 |  | 14259863 | 14259863 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2025-02-20 | 2025-03-04 | 2025-03-04 | 2025-03-06 | 2025-03-11 |  | Ongoing Procurement Process
320102100001000 | ITB 2025-SFP-008 Procurement of Food Items for 2025 SFP 15th Cycle Implementation ZDS – Cluster C | SFP | No | Competitive Bidding | 2025-02-10 |  |  | 2025-02-20 | 2025-03-04 | 2025-03-04 |  | 2025-03-06 | 2025-03-11 | 2025-03-21 |  |  |  | 2025-03-27 | 2025-06-05 | 2025-06-05 |  |  |  |  | Government of the Philippines (current year's budget) | 12274502 | 12274502 |  | 12085821 | 12085821 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2025-02-20 | 2025-03-04 | 2025-03-04 | 2025-03-06 | 2025-03-11 |  | Ongoing Procurement Process
320102100001000 | ITB 2025-SFP-009 Procurement of Food Items for 2025 SFP 15th Cycle Implementation ZDS – Cluster D | SFP | No | Competitive Bidding | 2025-02-10 |  |  | 2025-02-20 | 2025-03-04 | 2025-03-04 |  | 2025-03-06 | 2025-03-11 | 2025-03-21 |  |  |  | 2025-03-27 | 2025-06-05 | 2025-06-05 |  |  |  |  | Government of the Philippines (current year's budget) | 14790456 | 14790456 |  | 14770025 | 14770025 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2025-02-20 | 2025-03-04 | 2025-03-04 | 2025-03-06 | 2025-03-11 |  | Ongoing Procurement Process
320102100001000 | ITB 2025-SFP-010 Procurement of Food Items for 2025 SFP 15th Cycle Implementation ZDS – Cluster E | SFP | No | Competitive Bidding | 2025-02-10 |  |  | 2025-02-20 | 2025-03-04 | 2025-03-04 |  | 2025-03-06 | 2025-03-11 | 2025-03-21 |  |  |  | 2025-03-27 | 2025-06-05 | 2025-06-05 |  |  |  |  | Government of the Philippines (current year's budget) | 14048496 | 14048496 |  | 14035885 | 14035885 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2025-02-20 | 2025-03-04 | 2025-03-04 | 2025-03-06 | 2025-03-11 |  | Ongoing Procurement Process
320102100001000 | ITB 2025-SFP-011 Procurement of Food Items for 2025 SFP 15th Cycle Implementation ZDS – Cluster F | SFP | No | Competitive Bidding | 2025-02-10 |  |  | 2025-02-20 | 2025-03-04 | 2025-03-04 |  | 2025-03-06 | 2025-03-11 | 2025-03-21 |  |  |  | 2025-03-27 | 2025-06-05 | 2025-06-05 |  |  |  |  | Government of the Philippines (current year's budget) | 11463977 | 11463977 |  | 11450129 | 11450129 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2025-02-20 | 2025-03-04 | 2025-03-04 |  |  |  | Ongoing Procurement Process
320102100001000 | ITB 2025-SFP-012 Procurement of Food Items for 2025 SFP 15th Cycle Implementation ZDN – Cluster A | SFP | No | Competitive Bidding | 2025-02-10 |  |  | 2025-02-21 | 2025-03-05 | 2025-03-05 |  | 2025-03-06 | 2025-03-11 | 2025-03-21 |  |  |  | 2025-03-27 | 2025-06-05 | 2025-06-05 |  |  |  |  | Government of the Philippines (continuing budget) | 15457226 | 15457226 |  | 15444140 | 15444140 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2025-02-21 | 2025-03-05 | 2025-03-05 | 2025-03-06 | 2025-03-11 |  | Ongoing Procurement Process
320102100001000 | ITB 2025-SFP-013 Procurement of Food Items for 2025 SFP 15th Cycle Implementation ZDS – Cluster A | SFP | No | Competitive Bidding | 2025-02-10 |  |  | 2025-02-21 | 2025-03-05 | 2025-03-05 |  | 2025-03-06 | 2025-03-11 | 2025-03-21 |  |  |  | 2025-03-27 | 2025-06-05 | 2025-06-05 |  |  |  |  | Government of the Philippines (current year's budget) | 17238646 | 17238646 |  | 17222628 | 17222628 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2025-02-21 | 2025-03-05 | 2025-03-05 | 2025-03-06 | 2025-03-11 |  | Ongoing Procurement Process
320102100001000 | ITB 2025-SFP-014 Procurement of Food Items for 2025 SFP 15th Cycle Implementation ZSP – Cluster A | SFP | No | Competitive Bidding | 2025-02-10 |  |  | 2025-02-21 | 2025-03-05 | 2025-03-05 |  | 2025-03-06 | 2025-03-11 | 2025-03-21 |  |  |  | 2025-03-27 | 2025-05-30 | 2025-05-30 |  |  |  |  | Government of the Philippines (current year's budget) | 20209720 | 20209720 |  | 20159440 | 20159440 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2025-02-21 | 2025-03-05 | 2025-03-05 | 2025-03-06 | 2025-03-11 |  | Ongoing Procurement Process
320102100001000 | ITB 2025-SFP-015 Procurement of Food Items for 2025 SFP 15th Cycle Implementation ZSP – Cluster B | SFP | No | Competitive Bidding | 2025-02-10 |  |  | 2025-02-21 | 2025-03-05 | 2025-03-05 |  | 2025-03-06 | 2025-03-14 |  |  |  |  | 2025-03-27 | [6 empty] | Government of the Philippines (current year's budget) | 15596078 | 15596078 |  | 13256666.3 | 13256666.3 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2025-02-21 | 2025-03-05 | 2025-03-05 |  |  |  | Ongoing Procurement Process
320102100001000 | ITB 2025-SFP-016 Procurement of Food Items for 2025 SFP 15th Cycle Implementation ZSP – Cluster C | SFP | No | Competitive Bidding | 2025-02-10 |  |  | 2025-02-21 | 2025-03-05 | 2025-03-05 |  | 2025-03-06 | 2025-03-14 |  |  |  |  | 2025-03-27 | [6 empty] | Government of the Philippines (current year's budget) | 18229654 | 18229654 |  | 15495205.9 | 15495205.9 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2025-02-21 | 2025-03-05 | 2025-03-05 |  |  |  | Ongoing Procurement Process
320102100001000 | ITB 2025-SFP-017 Procurement of Food Items for 2025 SFP 15th Cycle Implementation ZAMBO CITY – Cluster A | SFP | No | Competitive Bidding | 2025-02-10 |  |  | 2025-02-21 | 2025-03-05 | 2025-03-05 |  | 2025-03-06 | 2025-03-11 | 2025-03-21 |  |  |  | 2025-03-27 | [6 empty] | Government of the Philippines (current year's budget) | 15929280 | 15929280 |  | 15915120 | 15915120 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2025-02-21 | 2025-03-05 | 2025-03-05 | 2025-03-06 | 2025-03-11 |  | Ongoing Procurement Process
320102100001000 | ITB 2025-SFP-018 Procurement of Food Items for 2025 SFP 15th Cycle Implementation ZAMBO CITY – Cluster B | SFP | No | Competitive Bidding | 2025-02-10 |  |  | 2025-02-21 | 2025-03-05 | 2025-03-05 |  | 2025-03-06 | 2025-03-14 |  |  |  |  | 2025-03-27 | [6 empty] | Government of the Philippines (current year's budget) | 19169180 | 19169180 |  | 16293803 | 16293803 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2025-02-21 | 2025-03-05 | 2025-03-05 |  |  |  | Ongoing Procurement Process
320102100001000 | ITB 2025-SFP-019 Procurement of Food Items for 2025 SFP 15th Cycle Implementation Isabela City, Basilan | SFP | No | Competitive Bidding | 2025-02-10 |  |  | 2025-02-21 | 2025-03-05 | 2025-03-05 |  | 2025-03-14 | 2025-03-21 |  |  |  |  | 2025-03-27 | [6 empty] | Government of the Philippines (current year's budget) | 6697495 | 6697495 |  | 6161695 | 6161695 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2025-02-21 | 2025-03-05 | 2025-03-05 |  |  |  | Ongoing Procurement Process
320102100001000 | ITB 2025-SFP-020 Procurement of High Protein Biscuits for DSWD Field Office IX SFP Implementation | SFP | No | Competitive Bidding | 2025-02-10 |  |  | 02-21-2025 | 2025-03-05 | 2025-03-05 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Government of the Philippines (current year's budget) | 31269000 | 31269000 |  | 0 |  |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 02-21-2025 | 2025-03-05 | 2025-03-05 | n/a | n/a | n/a | Failed under Section 35.1 (b)
320102100001000 | ITB 2025-SFP-021 2nd Public Bidding-Procurement of High Protein Biscuits for DSWD Field Office IX SFP Implementation | SFP | No | Competitive Bidding | 2025-02-10 |  |  | 2025-03-25 | 2025-04-08 | 2025-04-08 |  | 2025-04-10 | 2025-04-15 |  |  |  |  | 2025-05-06 | 2025-05-30 | 2025-05-30 |  |  |  |  | Government of the Philippines (current year's budget) | 31269000 | 31269000 |  | 31206462 | 31206462 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2025-03-25 | 2025-04-08 | 2025-04-08 |  |  |  | Ongoing Procurement Process
200000100001000 | ITB 2025-ICT-022 2nd Public Bidding-Procurement of Internet Services (Secondary) for DSWD Field Office IX | ICTMS | No | Competitive Bidding | 2025-02-10 |  |  | 2025-03-28 | 2025-04-10 | 2025-04-10 |  | 2025-04-10 | 2025-04-15 |  |  |  |  | 2025-05-13 | 2025-06-04 | 2025-06-04 |  |  |  |  | Government of the Philippines (current year's budget) | 2011235.58 | 2011235.58 |  | 2008884 | 2008884 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2025-03-28 | 2025-04-10 | 2025-04-10 |  |  |  | Ongoing Procurement Process
200000100001000 | ITB 2025-ICT-023-Procurement of High End Laptop and Server for DSWD FOIX | ICTMS | No | Competitive Bidding | 2025-05-07 | 2025-05-09 |  | 2025-05-16 | 2025-05-28 | 2025-05-28 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Government of the Philippines (current year's budget) | 2660000 | 2660000 |  | 0 |  |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2025-05-16 | 2025-05-28 | 2025-05-28 | n/a | n/a | n/a | Failed under Section 35.1 (b)
310100100001000 | ITB 2025-4PS-024-Printing and Delivery Services for DSWD FOIX SWDI Forms across Region IX | PANTAWID | No | Competitive Bidding | 2025-05-07 | 2025-05-09 |  | 2025-05-16 | 2025-05-28 | 2025-05-28 | [14 empty] | Government of the Philippines (current year's budget) | 1410000 | 1410000 |  | 0 |  |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2025-05-16 | 2025-05-28 | 2025-05-28 |  |  |  | Ongoing Procurement Process
320105100002000 | ITB 2025-PCDP-025-Procurement of Medicine and Medical Kit for DSWD FOIX, PCDP Clients | PCDP | No | Competitive Bidding | 2025-05-07 | 2025-05-09 |  | 2025-05-16 | 2025-05-28 | 2025-05-28 |  | 05-29-2025 | 2025-06-04 | [11 empty] | Government of the Philippines (current year's budget) | 1307952 | 1307952 |  | 1280514 | 1280514 |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2025-05-16 | 2025-05-28 | 2025-05-28 | 05-29-2025 | 2025-06-04 |  | Ongoing Procurement Process
320105100002000 | ITB 2025-PCDP-026-Procurement of Frozen Goods for DSWD FOIX, PCDP Clients | PCDP | No | Competitive Bidding | 2025-05-07 | 2025-05-09 |  | 2025-05-16 | 2025-05-28 | 2025-05-28 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Government of the Philippines (current year's budget) | 3070000 | 3070000 |  | 0 |  |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2025-05-16 | 2025-05-28 | 2025-05-28 | n/a | n/a | n/a | Failed under Section 35.1 (b)
320105100002000 | ITB 2025-PCDP-027-Procurement of Grocery Items for DSWD FOIX- PCDP Clients | PCDP | No | Competitive Bidding | 2025-05-07 | 2025-05-09 |  | 2025-05-16 | 2025-05-28 | 2025-05-28 |  | 05-29-2025 | [12 empty] | Government of the Philippines (current year's budget) | 2637450 | 2637450 |  | 0 |  |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2025-05-16 | 2025-05-28 | 2025-05-28 |  |  |  | Ongoing Procurement Process
320105100002000 | ITB 2025-PCDP-028-Procurement of Family Food Pack for DSWD FOIX PCDP- Clients | PCDP | No | Competitive Bidding | 2025-05-07 | 2025-05-09 |  | 2025-05-16 | 2025-05-28 | 2025-05-28 |  | 05-29-2025 | [12 empty] | Government of the Philippines (current year's budget) | 1680000 | 1680000 |  | 0 |  |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2025-05-16 | 2025-05-28 | 2025-05-28 |  |  |  | Ongoing Procurement Process
320105100002000 | ITB 2025-PCDP-029 Procurement of Fruits and Vegetables for DSWD FOIX PCDP- Clients | PCDP | No | Competitive Bidding | 2025-05-07 | 2025-05-26 |  | 2025-06-02 | 2025-06-17 | 2025-06-17 |  | 2025-06-17 | [12 empty] | Government of the Philippines (current year's budget) | 1355300 | 1355300 |  | 0 |  |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2025-06-02 | 2025-06-17 | 2025-06-17 |  |  |  | Ongoing Procurement Process
320105100002000 | ITB 2025-PCDP-030 Procurement of Commercial Rice for DSWD FOIX PCDP- Clients | PCDP | No | Competitive Bidding | 2025-05-21 | 2025-05-26 |  | 2025-06-02 | 2025-06-17 | 2025-06-17 |  | 2025-06-17 | [12 empty] | Government of the Philippines (current year's budget) | 2800000 | 2800000 |  | 0 |  |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2025-06-02 | 2025-06-17 | 2025-06-17 |  |  |  | Ongoing Procurement Process
310100100001000 | ITB 2025-4PS-031 Procurement of DSWD Field Office IX Pantawid Advocacy Materials. | PANTAWID | No | Competitive Bidding | 2025-05-21 | 2025-05-26 |  | 2025-06-02 | 2025-06-17 | 2025-06-17 |  | 2025-06-17 | [12 empty] | Government of the Philippines (current year's budget) | 2295370 | 2295370 |  | 0 |  |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2025-06-02 | 2025-06-17 | 2025-06-17 |  |  |  | Ongoing Procurement Process
320101100001000 | ITB 2025-BDSK-032 Procurement of Personal Care Products for DSWD FOIX BDSK, Polanco ZDN, Client | BDSK | No | Competitive Bidding | 2025-05-21 | 2025-05-26 |  | 2025-06-02 | 2025-06-17 | 2025-06-17 |  | 2025-06-17 | [12 empty] | Government of the Philippines (current year's budget) | 2156813 | 2156813 |  | 0 |  |  |  | Commission of Audit (COA), Zamboanga Chamber of Commerce and Industry Foundation, Inc. and Tzu Chi Foundation | 2025-06-02 | 2025-06-17 | 2025-06-17 |  |  |  | Ongoing Procurement Process
2024-07-19
-
[7 empty] | 0 | [17 empty] | Total Allotted Budget of On-going Procurement Activities | 432165071.28 | 432165071.28 | 0 | 337644866.26 | 337644866.26 | 0 | 16.34%
|  | Prepared by: | [9 empty] | Recommended for Approval by: | [16 empty] | APPROVED:
|  | AL-WALID S. SAPPAYANI | [9 empty] | MA. SOCCORO S. MACASO | [16 empty] | RIDUAN P. HADJIMUDDIN, CESO III
|  | BAC Secretariat | [9 empty] | BAC Chairperson | [16 empty] | Head of the Procuring Entity

## Sheet1
45
23
18
18
18
20
10
40
2
20
20
234

## Tool 1-Processing (hidden)
Summary of Information for Processing of IRPP
Indicator 1: % of Processed Procurement Activities vs Planned in terms of amount |  | #REF!
Formula | Value | Remarks
Total Amount of APP as updated | #REF!
Divide by: Total Amount of ABC of procurement activities started | #REF! | ABC of awarded + ABC of on-going procurement projects (less ABC of Failure of Bids)
Indicator 2: Average % of Variance Between Contract Amount vs Approved Budget for the Contract |  | #REF!
Particular | Value | Remarks
Total Amount of ABC of procurement activities started | #REF!
Total Contact Cost | 343185370.81
Total Variance for Each Awarded Procurement Project | #REF! | Column shall be hidden
Divide by Number of Awarded Procurement Projects | 48
Indicator 3. Timeliness on the Conduct of Procurement
|  | Indicator 3.1 Average No. of Days to commence procurement (Pre-Proc to Posting of IB) |  | Indicator 3.2: Average No. of Days to open bid proposals (Posting of IB/ to Opening of Bids) |  | Indicator 3.3: Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) |  | Indicator 3.4: Average Number of Days to Conclude Procurement (Posting of IB to Recommend Award) |  | Indicator 3.5: Average Number of Days to Issue Notice to Proceed (from Issuance of NOA to Issuance of NTP) |  | Indicator 3.6: Accumulated Number of Days for the Procurement Process (Posting of IB to NTP)
Mode of Procurement | Total No. of Activities under subject modality | Total No. of Days from PreProc to IB | Average Days from Pre-Proc to Posting of IB | Total No. of Days from IB to Opening | Average Days from Posting of IB to Opening of Bids | Total No. of Days Opening to Recommend Award) | Average Days from Opening of Bids to Recommend Award | Total No. of Days from Posting of IB to Recommend Award | Average Days from Posting of IB to Recommend Award | Total No. of Days from Issuance of NOA to Issue NTP | Average Days from NOA to NTP | Total No. of Days from Posting of IB to Issue NTP | Average Days from Posting of IB to NTP
Competitive Bidding | 62 | 129 | 2.0806 | 156 | 2.0806 | 97 | 1.5645 | 253 | 4.0806 | 0 | 0 | 0 | 0
Limited Source Bidding | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Direct Contracting | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Repeat Order | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Shopping 52.1(a) - Unforeseen Contingency | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.1 Two Failed Biddings | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.2 Emergency Cases | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.3 Take-Over of Contracts | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.4 Adjacent or Contiguous | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.5 Agency-to-Agency | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.7 Highly Technical Consultants | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.8 Defense Cooperation Agreement | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.9 - Small Value Procurement | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.10 Lease of Real Property and Venue | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.11 NGO Participation | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.12 Community Participation | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Emergency Procurement under Bayanihan Act | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Foreign Guidelines - Competitive Bidding | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Foreign Guidelines - Alternative Method | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total | 62 | 5.6087 | 2.0806 | 6.7826 | 2.0806 | 4.2174 | 1.5645 | 11 | 4.0806 | 0 | 0 | 0 | 0
*formula for days interval for each procurement activity for each indicator are embedded in the PMR.
Indicator 4. Percentage of Amount and Volume by Tender and Award of Procurement Activities per Mode of Procurement
Mode of Procurement | Total No. of Activities | Total Number of Awarded | Total ABC | Total Contract Cost | %Vol of Awarded | %ABC of Awarded | Total Number of Failed | ABC of Failed
Competitive Bidding | 63 | 48 | 386123090.7 | 343185370.81 | 76.19% | 88.88% | 0 | 0
Limited Source Bidding | 0 | 0 | 0 | 0 |  |  | 0 | 0
Direct Contracting | 0 | 0 | 0 | 0 |  |  | 0 | 0
Repeat Order | 0 | 0 | 0 | 0 |  |  | 0 | 0
Shopping 52.1(a) - Unforeseen Contingency | 0 | 0 | 0 | 0 |  |  | 0 | 0
Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.1 Two Failed Biddings | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.2 Emergency Cases | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.3 Take-Over of Contracts | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.4 Adjacent or Contiguous | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.5 Agency-to-Agency | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.7 Highly Technical Consultants | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.8 Defense Cooperation Agreement | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.9 - Small Value Procurement | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.10 Lease of Real Property and Venue | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.11 NGO Participation | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.12 Community Participation | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | 0 | 0 | 0 | 0 |  |  | 0 | 0
Emergency Procurement under Bayanihan Act | 0 | 0 | 0 | 0 |  |  | 0 | 0
Foreign Guidelines - Competitive Bidding | 0 | 0 | 0 | 0 |  |  | 0 | 0
Foreign Guidelines - Alternative Method | 0 | 0 | 0 | 0 |  |  | 0 | 0
Total | 63 | 48 | 386123090.7 | 386123090.7 | 76.19% | 88.88% | 0 | 0
Total for Alternative Mode of Procurement | 0 | 0 | 0 | 0 | #DIV/0! | #DIV/0! | 0 | 0
Indicator 5: Accumulated No. of Days for On-going Procurement Activities
Timeline | No. of Procurement Activities | %
Exceeds 180 days | 0 | 0%
Within 91 to 180 days | 0 | 0%
Within 45 to 90 days | 0 | 0%
Within 0 to 44 days | 0 | 0%
Total | 0 | 0%
*Validation shall be provided for the PMR so that the PMO can easily select and determined the total count
Indicator 6. Distribution of On-going, Awarded, and Failed procurement Activities
Status | No. of Procurement Activities | % by No. of Procurement of Activities | ABC Amount of Activities | % by ABC | Contract Cost | Contract/ABC | Variance
Awarded | 0 | 0% | 0 | 0% | 0 | 0% | #DIV/0!
Completed | 0 | 0% | 0 | 0% | 0 | 0% | #DIV/0!
Failed | 0 | 0% | 0 | 0% | 0 | 0% | #DIV/0!
Ongoing | 40 | 100% | 393154835.7 | 100% | 337644866.26 | 100% | 0.14119
Total | 40 | 100% | 393154835.7 | 100% | 337644866.26 | 100% | 0.14119
*Validation shall be provided for the PMR so that the PMO can easily select and determined the total count
Indicator 7a: % of Number of Procurement activities conducted under early procurement |  |  | 38.71%
Indicator 7b: % of ABC of Procurement activities conducted under early procurement |  |  | 16.46%
Particular | No. of Procurement Activities | ABC Amount of Activities
Under EPA | 24 | 80393217.12
Regular Procurement | 38 | 407975998.16
Total | 62 | 488369215.28
Indicator 8a: Percentage of Number of Awarded Contracts under EPA |  |  | 0%
Indicator 8b: Percentage of Contract Cost of EPA against the total ABC under EPA |  |  | #VALUE!
Formula | No. of Procurement Activities | Amount of ABC Procurement Activities | Contract Cost of Procurement Activities | Percentage Variance
Total Contracts Awarded under EPA* | 0 | 0 | 0 | 0%
Total Contracts Completed under EPA* | 0 | 0 | 0 | 0%
Total Failed Bid under EPA* | 0 | 0 | 0 | 0%
Total Ongoing Activities under EPA* | 10 | 48284274.12 | #VALUE! | #VALUE!
Total Procurement Activities under EPA | 24 | 48284274.12 | #VALUE!
To compute for the total, a separate sheet may be created of the PMO may simply filter the cells to capture the total number.
Indicator 9: Stages where failure of bidding are encountered
Particular | No. of Procurement Activities | Amount of ABC | Vol. % | Amount %
Invitation To Bid | 0 | 0 | 0% | 0%
Pre-bidding Conference | 0 | 0 | 0% | 0%
Opening of Bids | 0 | 0 | 0% | 0%
Bid Evaluation | 0 | 0 | 0% | 0%
Post-Qualification | 0 | 0 | 0% | 0%
BAC Resolution | 0 | 0 | 0% | 0%
Award | 0 | 0 | 0% | 0%
Cancelled | 0 | 0 | 0% | 0%
TOTAL | 0 | 0

## Validation Menu (hidden)
REMARKS | STATUS | STAGE OF PROCUREMENT | Source of Funds
Awarded with issued Notice of Award | Awarded | Invitation To Bid | Government of the Philippines (current year's budget)
Completed | Completed | Pre-bidding Conference | Government of the Philippines (continuing budget)
Ongoing Procurement Process | Failed | Opening of Bids | Government of the Philippines (current year's and continuing budget)
Failed under Section 32.2.1 (a) | Ongoing | Bid Evaluation | Grant by an International Financing Institution
Failed under Section 35.1 (a) |  | Post-Qualification | Loan from an International Financing Institution
Failed under Section 35.1 (b) |  | BAC Resolution
Failed under Section 35.1 (c) |  | Award
Failed under Section 41 (b) |  | Cancelled
Failed under Section 41 (c)
Contract was extended
Contract was renewed
Cancelled
Others, please encode directly on the cell